## 00 Cover
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
DOCUMENT TITLE | Rick Miller SME Standard — Canada 2026 Mining Heavy Civil Estimating Manual & Rate Library
DOCUMENT NUMBER | RMM-CIVIL-CANADA-2026-MANUAL-REV4
REVISION | Rev 4 — Full Build-Up Reconciliation + CGL/Builders Risk Lines + Green Audit Highlights
PREPARED BY | Rick Miller, Senior Project Director / EPCM
PURPOSE | Provide an internally-maintained, contractor-grade Schedule of Rates and bid-support package for Canadian mining heavy civil projects. Supports budgetary estimates (Class 5/4), feasibility estimates (Class 3), AFE/sanction estimates (Class 2), tender support, contractor benchmarking, bid evaluation, change pricing and unit-rate validation.
BASE CURRENCY | Canadian Dollar (CAD) ¦ Q2 2026
ESTIMATE CLASS — BASIS | AACE 18R-97 Class 3 Benchmark (±20% / +30%); Class 2 and Class 1 conversion factors provided in Section 14
ESCALATION BASIS | Ausenco go-by Q2-2020 escalated x1.25 (BCPI cumulative midpoint) to Q2-2026
DIESEL — ATLANTIC | $2.13–$2.21 / L (NS ERB May 2026)
DIESEL — ALBERTA | $1.68–$1.78 / L (NRCan May 2026)
DIESEL — BC METRO | $2.15–$2.35 / L (NRCan May 2026)
USD/CAD | 1.36 – 1.37 (Bank of Canada May 2026)
CBSA TARIFF | 25% surtax — Chinese structural steel and rebar (CBSA Notices 24-26 / 25-22, Oct 2024 ongoing)
DATA SOURCE | Consolidated from RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 (Contractor Bid Tool) and RMM-CIVIL-CANADA-2026-REV0 (EPCM Benchmark Estimator) — both authored by Rick Miller
INTENDED USERS | Contractor estimators, EPCM cost engineers, owner cost teams, bid evaluators, project controls
INTENDED USE | Internal reference / bid-support / sense-check tool. Not a public quotation. Do not issue cells as fixed pricing without project-specific validation.
WORKBOOK CELL COLOUR LEGEND
White / no shading | Reference data extracted directly from the Rev G and Rev E source workbooks (baseline).
Light yellow (italic grey text) | [TEMPLATE] section — industry-standard framework provided as scaffolding to be populated per project.
Light blue | [INPUT] cell — user enters a project-specific quantity, rate, or factor.
Light green | [CALCULATED] cell — driven by formula from inputs; do not overwrite.
Light green + bold green text | [REV 4 AUDIT] — Sheet 08 build-up cell back-calculated in Rev 4 from (Unit MH × Crew $/hr) + Total Low/High reconciliation. Used for transparency on items where the source workbook provided only Total Low/High.
Navy bar | Section or sub-section header.

## 01 Contents
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
# | Section | Description
00 | Cover | Document control, basis, currency, source workbooks, cell legend.
01 | Contents | Tab index and navigation map (this sheet).
02 | Executive Summary | One-page summary of the package, intended use, and key benchmarks.
03 | Estimating Standards | AACE 18R-97 classes, accuracy ranges, design growth, escalation, exchange basis.
04 | Crew Compositions | 12 crew codes (B1–N1), 2020 vs 2026 escalated all-in rates, crew sizing.
05 | Labour Rates | 27 positions fully burdened, Camp/LOA flags, classification, 2026 low/high.
06 | Equipment Rates | 30 fleet items, fully operated rate, fuel burn, mob/demob, availability.
07 | Equipment Spreads | [TEMPLATE] Typical spreads by scope (mass earth, fill placement, road, liner).
08 | Schedule of Rates — Master | ~120 line-item consolidated SoR (Heavy Civil + Contractor scope) with build-up columns.
09 | Unit Rate Build-Up Calculator | [TEMPLATE] Working calculator — assemble new unit rates from crew × MH + equip + mat + sub + indirects.
10 | Bid Screening Floors & Ceilings | 29 benchmark $/m3, $/m2, $/m sense-checks for tender evaluation.
11 | Contractor Indirects (CDI) | Field office, PM staff, QC, environmental, mob/demob, head office allocation.
12 | Bonding & Insurance | Surety, CGL, WCB by province, Builder's Risk, contractor equipment floater.
13 | Standby & Schedule | Equipment & labour standby, OT/shift premiums, winter costs, owner-caused delay.
14 | SME Factors | Design growth (Class 4–1), wastage, regional adjustors (11 zones), escalation, accuracy.
15 | Bid Cost Structure (Markup Stack) | 6-layer markup model: Direct → CDI → OH → Bond/Ins → Contingency → Profit.
16 | Mob / Demob Logic | Equipment-specific mob/demob rules, fleet vs single-piece, remote site logic.
17 | Constructability Assumptions | [TEMPLATE] Execution philosophy, sequencing, access, productivity, work calendar.
18 | Scope Inclusions / Exclusions | [TEMPLATE] Discipline-by-discipline inclusion / exclusion / clarification register.
19 | Bid Leveling Comparison | [TEMPLATE] Side-by-side tender evaluation worksheet (3 bidders + benchmark).
20 | Change Order Pricing | [TEMPLATE] CCDC-style change order build-up: T&M, unit-rate, lump-sum methodologies.
21 | Project Estimate Roll-Up | [TEMPLATE] WBS roll-up sheet — direct + CDI + OH + bond + contingency + profit = total bid.
22 | Risk & Contingency Register | [TEMPLATE] Project risk log with cost/schedule impact and contingency allocation.
23 | Glossary & Abbreviations | Terms, acronyms, units of measure used throughout the manual.
24 | Sources & References | AACE, BCPI, NRCan, CBSA, WCB sources, supplier quotes, internal benchmarks.
25 | Real Market Benchmark | [Rev 2] SME ranges cross-referenced vs Alberta Transportation 2026 Unit Price Averages (weighted avg of 3 low bids, May 2024 – Sep 2025) and BC Road Builders 2026 awards. Variance % flagged.

## 02 Executive Summary
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
PURPOSE
This manual is a consolidated, internally-maintained estimating standard and rate library for Canadian mining heavy civil work. It is designed to be used by contractors, EPCMs, and owners for budgetary pricing, feasibility-class estimates, tender support, bid evaluation, and change pricing.
WHAT IS INCLUDED — BASELINE (FROM SOURCE WORKBOOKS)
• 12 crew codes (B1–N1) with 2020-to-2026 escalation; • 27 fully-burdened labour positions; • 30 fully-operated equipment items with fuel burn and mob/demob flags; • ~78 Heavy Civil unit rates across 8 sections (earthworks → closure); • ~22 contractor-scope unit rates (blasting → crushing); • 29 bid-screening floors/ceilings; • 19 bonding & insurance lines (WCB by province); • 25 overhead lines; • 19 standby & schedule items; • SME factors: design growth, wastage, 10 regional zones, escalation, AACE accuracy ranges.
WHAT IS INCLUDED — FRAMEWORK TEMPLATES (AUTHORED HERE)
Scaffolding sections clearly marked [TEMPLATE]: • Equipment spreads; • Unit rate build-up calculator; • Constructability & execution assumptions; • Scope inclusions/exclusions register; • Bid leveling comparison; • Change order pricing; • Project estimate roll-up; • Risk & contingency register. These are blank/sample structures — populate per project.
INTENDED ESTIMATE CLASSES
Class 5/4 (screening / budgetary) — use floor/ceiling ranges and apply +15–20% design growth. Class 3 (feasibility / budget) — THIS DOCUMENT'S BASELINE. Apply +10–15% design growth. Class 2 (sanction / AFE / pre-FID) — use mid-range rates with +5–10% design growth. Class 1 (tender check / detailed) — use low end of range or project-specific quotes; +2–5% design growth.
HOW TO USE
1) Identify scope and WBS items. 2) Pull unit rates from Sheet 08 (Master SoR). 3) Apply quantity × rate. 4) Add Contractor Indirects (Sheet 11) and apply markup stack (Sheet 15). 5) Apply regional adjustor (Sheet 14). 6) Sense-check against Sheet 10 floors/ceilings. 7) Roll up in Sheet 21.
KEY 2026 BENCHMARKS
Mass earthworks rock (blasted): $55–$120/m3. Engineered fill: $22–$45/m3. Haul road full build: $65–$120/m2. TMF embankment Zone A/B: $22–$45/m3. HDPE 2mm liner (S+I+CQA): $28–$55/m2. CSP culvert 1200mm: $1,000–$1,600/m. Concrete wall/grade beam: $2,500–$3,200/m3. Rebar (S+I): $4,000–$6,500/tonne (CBSA 25% surtax exposure). Performance bond medium contract: 1.0–1.8% of contract.
REGIONAL ADJUSTOR RANGE
MB/SK 1.00–1.08 (baseline) → Yukon/NWT/Nunavut 1.30–1.55 (extreme remote). Winter premium: 10–25% all Canada.
DO NOT USE FOR
• Public/fixed quotations without project-specific validation; • Lump-sum tender submission without supplier confirmation; • Class 1 detailed estimates without complete IFC drawings and supplier RFQs; • Projects outside Canadian mining heavy civil scope without re-baselining.

## 03 Estimating Standards
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
AACE 18R-97 — ESTIMATE CLASSIFICATION FRAMEWORK (mining heavy civil interpretation)
AACE Class | Project Stage | Definition Level (% project def.) | Methodology | Accuracy Low | Accuracy High | Typical Use
Class 5 | Concept screening | 0%–2% | Stochastic / parametric / per-unit-capacity factors | -50% | +100% | Order of magnitude; screening; ROM
Class 4 | Pre-feasibility / study | 1%–15% | Mostly stochastic; equipment factored; some unit rates | -30% | +50% | Concept evaluation; site selection
Class 3 | Feasibility / budget | 10%–40% | Semi-detailed; mostly unit rates; MTOs from PFD/general arr. | -20% | +30% | Budget authorization; this baseline
Class 2 | Sanction / AFE | 30%–75% | Detailed unit rates; near-complete MTOs; firm quotes on long-leads | -10% | +20% | FID / sanction approval
Class 1 | Tender / check | 65%–100% | Detailed; IFC drawings; firm RFQ pricing; full crew/equip build-up | -5% | +10% | Tender bid; check estimate
DESIGN GROWTH ALLOWANCES (by class) — SOURCE: SME Factors tab
Class | Discipline / Scope | Design Growth Low | Design Growth High | Notes
Class 5/4 | Earthworks / civil | 15% | 20% | Limited geotech; preliminary drawings
Class 3 | Earthworks / civil (this baseline) | 10% | 15% | Standard level for feasibility / budget
Class 2 | Earthworks / civil | 5% | 10% | Pre-FID; IFC packages near complete
Class 1 | Earthworks / civil | 2% | 5% | Full detailed design completed
All | Concrete works (additive) | +5% | +5% | Add 5% incremental to earthworks DG
WASTAGE FACTORS — SOURCE: SME Factors tab
Material | Wastage Low | Wastage High | Basis
Granular aggregate | 5% | 10% | Rounding + delivery variance
Concrete (formed) | 8% | 12% | Pump waste + edge loss
Rebar | 3% | 7% | Cutting waste; depends on bar size and complexity
Geomembrane liner | 5% | 10% | Panel overlaps + anchor trench + QA sampling
Geotextile | 10% | 15% | ASTM D4439 6-inch overlap minimum
ESCALATION & MARKET BASIS — Q2-2026 — SOURCE: SME Factors tab
Item | Low | High | Basis / Source
Go-by Q2-2020 → Q2-2026 cumulative escalation factor | x1.23 | x1.27 | BCPI cumulative; use x1.25 midpoint
Labour CBA escalation 2024–2026 (NL trades) | 3.5% | 5.5% | Per trade; see Sheet 05
Diesel — Nova Scotia (May 2026) | $2.13/L | $2.21/L | NS Energy Regulatory Board
Diesel — Alberta (May 2026) | $1.68/L | $1.78/L | NRCan
Diesel — BC Metro (May 2026) | $2.15/L | $2.35/L | NRCan
USD/CAD exchange rate (May 2026) | 1.36 | 1.37 | Bank of Canada
CBSA surtax — Chinese structural steel | 25% | 25% | CBSA Notices 24-26/25-22 (Oct 2024 ongoing)
CBSA surtax — Chinese rebar | 25% | 25% | Verify supplier origin certificate

## 04 Crew Compositions
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION CREW RATES — CANADA 2026 (CAD/HR) — SOURCE: Rev E Crew Rates tab
Code | Crew Description | Avg Size | Lab. 2020 ($/hr) | Equip 2020 ($/hr) | Total 2020 ($/hr) | Esc. Factor | Lab. 2026 ($/hr) | Equip 2026 ($/hr) | Total 2026 ($/hr) | Source / Basis
B1 | Civil Works — Light (strip, grade, compact light) | 26.1 | 90.9 | 36.6 | 127.5 | x1.25 | 113.62 | 45.75 | 159.37 | Ausenco go-by Q2-2020 x1.25 BCPI
B2 | Civil Works — Medium (cut, fill, haul <2km) | 28.1 | 90.7 | 68.2 | 158.9 | x1.25 | 113.38 | 85.25 | 198.63 | Ausenco go-by Q2-2020 x1.25 BCPI
B3 | Civil Works — Heavy (mass earth, rock, blast) | 37.7 | 90.2 | 71.1 | 161.3 | x1.25 | 112.75 | 88.88 | 201.63 | Ausenco go-by Q2-2020 x1.25 BCPI
B4 | Civil Liner & Pipeline (HDPE, geomem, culverts) | 28.1 | 92.8 | 23.3 | 116.1 | x1.25 | 116 | 29.12 | 145.12 | Ausenco go-by Q2-2020 x1.25 BCPI
C1 | Concrete (slab, wall, pier, footing all-in) | 22.6 | 88.6 | 20.8 | 109.4 | x1.25 | 110.75 | 26 | 136.75 | Ausenco go-by Q2-2020 x1.25 BCPI
D1 | Structural Steel (erect, weld, bolt-up) | 17.6 | 91.9 | 22.2 | 114.1 | x1.25 | 114.88 | 27.75 | 142.63 | Ausenco go-by Q2-2020 x1.25 BCPI
E1 | Architectural (cladding, doors, windows) | 19.6 | 89.4 | 10.9 | 100.3 | x1.25 | 111.75 | 13.62 | 125.37 | Ausenco go-by Q2-2020 x1.25 BCPI
G1 | Mechanical Services (HVAC, plumbing, utility) | 17.65 | 95.8 | 15.5 | 111.3 | x1.25 | 119.75 | 19.38 | 139.13 | Ausenco go-by Q2-2020 x1.25 BCPI
H1 | Mechanical Equipment (install, align, grout) | 23.55 | 102.3 | 13.5 | 115.8 | x1.25 | 127.88 | 16.88 | 144.76 | Ausenco go-by Q2-2020 x1.25 BCPI
J1 | Piping | 13.7 | 95.7 | 14.8 | 110.5 | x1.25 | 119.62 | 18.5 | 138.12 | Ausenco go-by Q2-2020 x1.25 BCPI
K1 | Electrical | 10.75 | 103.4 | 14.4 | 117.8 | x1.25 | 129.25 | 18 | 147.25 | Ausenco go-by Q2-2020 x1.25 BCPI
N1 | Instrumentation | 10.35 | 106.2 | 17.6 | 123.8 | x1.25 | 132.75 | 22 | 154.75 | Ausenco go-by Q2-2020 x1.25 BCPI
DR1 | Surface Drilling Crew (Rev G blasting + rock anchor scope) | 6 | 78.4 | 25.6 | 104 | Rev 4 | 98 | 32 | 130 | Rev 4 SME — surface drilling crew; resolves Rev G 'D1' code ambiguity
UC1 | Underground — Shaft Sinking (driller+blaster+mucker) | 18 | 108 | 52 | 160 | Rev 3 | 135 | 65 | 200 | Rev 3 SME — specialty shaft sinking crew
UC2 | Underground — Drift Dev / Ground Support | 16 | 104 | 40 | 144 | Rev 3 | 130 | 50 | 180 | Rev 3 SME — drift + bolting + shotcrete
UC3 | Underground — Raise Bore Specialty | 10 | 112 | 64 | 176 | Rev 3 | 140 | 80 | 220 | Rev 3 SME — Atlas/Strata raise borer
UC4 | Underground — Paste / Backfill | 8 | 96 | 40 | 136 | Rev 3 | 120 | 50 | 170 | Rev 3 SME — paste plant + UG distribution
DI1 | Dam Instrumentation (piezo / inclino / survey) | 6 | 94.4 | 33.6 | 128 | Rev 3 | 118 | 42 | 160 | Rev 3 SME — VW piezo + inclinometer install
HDD | HDD Horizontal Directional Drilling (specialty sub) | 8 | 128 | 112 | 240 | Rev 3 | 160 | 140 | 300 | Rev 3 SME — pipeline crossing specialty
MEC | Mechanical Equipment Install (process plant) | 20 | 100 | 20 | 120 | Rev 3 | 125 | 25 | 150 | Rev 3 SME — mill / thickener / flotation install
ST1 | Steel Erection — Bridge Crew | 15 | 91.9 | 36.6 | 128.5 | Rev 3 | 114.88 | 45.75 | 160.63 | Rev 3 SME — bridge steel erection (heavier lifts)
Notes: Crew rates are average all-in (labour + equipment) per crew-hour. Productivity (Prod Factor) is applied at the unit-rate level (see Sheet 08). Crew composition by trade is shown on Sheet 05 and 06 — these crews are SME averages for benchmarking, not a fixed roster.

## 05 Labour Rates
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION LABOUR RATES — CANADA 2026 FULLY BURDENED (CAD/HR) — SOURCE: Rev E Labour Rates tab
Ref | Trade / Position | Classification | 2026 Low (CAD/hr) | 2026 High (CAD/hr) | Camp/LOA | SME Notes
S1 | General Superintendent | Supervisor | 154 | 172 | LOA+Camp | All burdens+O&P. Remote mining site.
S2 | Superintendent | Supervisor | 136 | 155 | LOA+Camp
S3 | General Foreman | Supervisor | 125 | 140 | LOA+Camp
C1 | Civil Work Lead | Civil | 116 | 132 | LOA+Camp
C2 | Equip Operator — Heavy Duty (dozer/exc/grader) | Civil | 110 | 128 | LOA+Camp | D8/336/140M class. 2026 burdened.
C3 | Equip Operator — Medium Duty (loader/backhoe) | Civil | 101 | 116 | LOA+Camp | 930M/320D class
C4 | Equip Operator — Light Duty (skidsteer/roller) | Civil | 93 | 106 | LOA+Camp
C5 | Labourer — Journeyman | Civil | 82 | 95 | LOA+Camp | Base civil crew rate
C6 | Labourer — 2yr Apprentice | Civil | 73 | 84 | LOA+Camp
C7 | Labourer — 1st yr Apprentice | Civil | 64 | 74 | LOA+Camp
D1 | Driller — Journeyman (blast hole) | Civil/Blast | 93 | 108 | LOA+Camp | Licensed; Atlas/Sandvik rig
D2 | Blaster — Journeyman | Civil/Blast | 93 | 108 | LOA+Camp | Provincial certificate required
M1 | Mechanic — Heavy Duty | Mechanical | 84 | 98 | LOA+Camp | Plant/fleet mechanic
M2 | Mechanic — Medium Duty | Mechanical | 92 | 106 | LOA+Camp
T1 | Carpenter — Journeyman (formwork) | Trades | 109 | 125 | LOA+Camp
T3 | Concrete Lead | Trades | 125 | 140 | LOA+Camp
T4 | Concrete Finisher — Journeyman | Trades | 95 | 108 | LOA+Camp
T5 | Ironworker — Journeyman (rebar/structural) | Trades | 115 | 132 | LOA+Camp
T6 | Welder/Pipefitter — Journeyman | Trades | 113 | 130 | LOA+Camp
T8 | Rodman — Reinforcement Journeyman | Trades | 94 | 108 | LOA+Camp
E1 | Electrician — Journeyman | Electrical | 127 | 145 | LOA+Camp | 2026 shortage premium applied
I1 | Instrumentation Tech — Journeyman | Instrumentation | 127 | 145 | LOA+Camp
P1 | Project Engineer — Field | PM/Eng | 109 | 125 | LOA+Camp
P2 | Project Engineer — Senior Field | PM/Eng | 123 | 140 | LOA+Camp
O1 | Safety Officer (NCSO certified) | HSE | 110 | 125 | LOA+Camp | NCSO cert + site-specific induction
O2 | Camp — all-in per person/day | Indirect | 220 | 300 | Included | Bunk, food, laundry, rec. Remote mine.
O3 | LOA subsistence — non-camp | Indirect | 180 | 250 | N/A | Per-diem where camp not provided
Labour rates are fully burdened: base wage + statutory burdens (CPP, EI, EHT, vacation, stat holidays) + employer benefits + WCB (province-specific, see Sheet 12) + small tools allowance + supervision ratio. Camp/LOA is shown as an additive per-person cost; subsistence is per-diem where camp not provided. Use Sheet 12 to validate WCB rate by province before pricing.

## 06 Equipment Rates
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION EQUIPMENT RATES — CANADA 2026 FULLY OPERATED (CAD/HR) — SOURCE: Rev E Equipment Rates tab
Cat. | Equipment | Size / Capacity | 2026 Low ($/hr) | 2026 High ($/hr) | Fuel (L/hr) | Mob/Demob | Availability | SME Notes
HT | Tandem dump truck | 18-20T | 140 | 165 | 45-65 | Required | 85% | Fully operated; Canada-wide May 2026
HT | Tri-axle dump truck | 25T | 155 | 180 | 55-75 | Required | 85%
HT | Wiggle wagon / Super B | 45T | 185 | 215 | 65-90 | Required | 80% | Field confirmed Q2-2026
HT | Off-road haul truck | 40-100T | 320 | 500 | 80-140 | Included | 85% | Komatsu/CAT; payload class dependent
EX | Hydraulic excavator | Cat 320 20-25T | 250 | 330 | 18-25 | Required | 85% | Production dig/load
EX | Hydraulic excavator | Cat 336 35-40T | 340 | 430 | 25-35 | Required | 85% | Rock + bulk earthworks
EX | Hydraulic excavator | Cat 390 50-65T | 460 | 580 | 38-50 | Required | 82% | Mass excavation
EX | Long-reach excavator | 20T 18m reach | 290 | 380 | 18-25 | Required | 82% | Pond, ditch, shoreline
DO | Track dozer | Cat D6N 17T | 250 | 320 | 20-30 | Required | 88% | Clear, rough grade, push
DO | Track dozer | Cat D8T 37T | 380 | 480 | 35-48 | Required | 88% | Production push, rip rock
DO | Track dozer | Cat D10T 58T | 520 | 650 | 50-68 | Required | 85% | Mass earthworks, stripping
GR | Motor grader | Cat 140M | 280 | 360 | 18-26 | Required | 88% | Road maint, final grade
GR | Motor grader | Cat 16M large | 360 | 450 | 22-32 | Required | 88% | Large platform grading
CP | Vib. roller single drum | Cat CS56B 12T | 200 | 270 | 15-22 | Required | 88% | 200-300mm lift
CP | Padfoot compactor | Cat CS74B 17T | 240 | 310 | 18-26 | Required | 88% | Cohesive soils
CP | Plate compactor / jumping jack | 0.5-1T | 45 | 75 | 5-8 | By truck | 90% | Trench zones, tight access
WL | Wheel loader | Cat 930M 10T | 200 | 270 | 18-26 | Required | 87% | Aggregate load, general
WL | Wheel loader | Cat 950M 16T | 250 | 320 | 22-30 | Required | 87% | General load-out
WL | Wheel loader | Cat 980M 22T | 320 | 400 | 28-38 | Required | 87% | High production
DR | Rotary drill rig | Atlas 120mm hole | 550 | 750 | 35-50 | Included | 80% | Blast hole drilling
SK | Skid steer | Cat 262D | 95 | 135 | 10-15 | By truck | 90% | Tight access, site clean
WP | Diesel submersible pump | 4-inch 150mm | 55 | 85 | 10-16 | By truck | 90% | Site dewatering
WP | Diesel submersible pump | 8-inch 200mm | 120 | 180 | 20-30 | By truck | 90% | Large dewatering
CR | Rough terrain crane | Grove RT 60T | 650 | 900 | 30-45 | Required | 80% | Lifts, precast, equip set
CR | Lattice boom crawler crane | Liebherr 150T | 1800 | 2600 | 60-90 | Included | 78% | Heavy lift
MI | Rock breaker / hyd hammer | Cat 345 + hammer | 480 | 620 | 28-40 | Required | 80% | Rock fragmentation
MI | Air compressor diesel towable | 375 cfm | 75 | 110 | 12-18 | By truck | 90% | Drill assist, pneumatics
MI | Light tower diesel | 8-10 kW | 35 | 55 | 5-8 | By truck | 95% | Nightshift / portal safety
MI | Fuel tanker site supply | 10,000L | 180 | 250 | 30-40 | Required | 90% | Incl. driver
MI | Water truck dust suppression | 10,000L | 160 | 220 | 30-40 | Required | 90% | Incl. driver
Equipment rates are fully operated (operator wage already burdened; see Sheet 05 for standalone labour). Fuel is shown in L/hr; multiply by site diesel price (Sheet 03) for fuel-cost portion. Availability % drives effective hours per shift. Mob/demob: 'Required' = additional cost per Sheet 16; 'Included' = built into hourly rate; 'By truck' = transport on flatbed at nominal cost.

## 07 Equipment Spreads
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
TYPICAL EQUIPMENT SPREADS BY SCOPE [TEMPLATE — verify against project conditions]
Scope / Operation | Spread Description | Primary Equipment | Support Equipment | Crew Code | Productivity Range | Util. | Notes
Mass earthworks — rock | Drill + blast + load + haul | 1x DR rotary, 1x EX Cat 390, 4-6x off-road 40-100T | 1x D10T, 1x water truck, 1x grader | B3 | 800-1,500 m3/shift | 75% | Rock blasted/m3; cycle <2km
Mass earthworks — common | Cut/fill/place/compact | 1x EX Cat 336, 4-6x tandem/tri-axle | 1x D8T, 1x CS56B roller, 1x water truck | B3 | 1,200-2,000 m3/shift | 80% | Engineered fill <250mm
Engineered fill placement | Lift placement and compaction | 1x EX Cat 320 or WL 950M, 2-4x tandem | 1x D6N, 1x CS74B padfoot, 1x water truck | B2 | 600-1,000 m3/shift | 82% | 300mm lift; Zone A/B; nuclear density
Haul road build | Sub-grade → surface course | 1x D8T (sub-base), 1x grader 140M (surface) | 1x CS56B roller, 1x water truck | B2 | 150-300 m/day full build | 82% | 8m wide single lane; all lifts
HDPE liner install (TMF) | Panel deploy + weld + CQA | 1x WL 930M (panel handling), 1x SK | 1x air compressor 375cfm | B4 | 1,500-3,000 m2/day | 75% | Specialty sub; CQA per project
Culvert install (≥900 mm CSP) | Trench, bed, install, backfill | 1x EX Cat 320, 1x WL 930M, 2x tandem | 1x plate compactor, 1x dewatering pump | B4 | 20-40 m/day | 75% | Cofferdam + dewatering if creek live
Buried services trenching | Trench, bed, lay, backfill | 1x EX Cat 320, 1x tandem, 1x WL 930M | 1x plate compactor, 1x trench box | B4 | 60-120 m/day | 78% | HDPE 150-200mm; depth <2.5m
Concrete pour — foundation | Form, place, pour, finish | 1x crane RT 60T (if precast/heavy form) | 1x concrete pump, 1x vibrator | C1 | 12-25 m3/day | 75% | Formed walls / grade beams
Rock support — shotcrete | Apply 50-100mm with mesh | 1x shotcrete pump, 1x EX (mesh handling) | 1x SK (mix supply) | C1 | 120-250 m2/day | 70% | Fibre or wire mesh embedded
Drill+blast rock anchors | Drill, install, grout, tension | 1x drill rig (anchor-specific), 1x EX | 1x grout plant | D1 | 8-15 anchors/day | 70% | Active tensioned 32mm strand
Buried HDPE forcemain | Trench, bed, fuse, lay, backfill | 1x EX Cat 320, 1x WL, 1x fusion machine, 1x tandem | 1x plate compactor | B4 | 80-150 m/day | 78% | Site dewatering may be required
Demolition / strip and grub | Clear, grub, stockpile | 1x D8T, 1x EX Cat 336 | 1x tandem (haul) | B3 | 0.5-1.5 ha/day | 78% | Light bush; rock/timber additive
[TEMPLATE — verify per project] These are typical SME spreads for Class 3 estimating. Validate fleet sizing against site access, haul distance, geotechnical conditions, climate window, and crew availability before committing to a bid.

## 08 SoR Master
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
MASTER SCHEDULE OF RATES — HEAVY CIVIL + CONTRACTOR SCOPE — CANADA 2026 (CAD) — SOURCE: Rev E HCUR + Rev G Missing Unit Rates
Section | WBS Ref | Item Description | UOM | Unit MH | Prod Factor | Unit Labour | Unit Equip | Unit Material | Unit Subcon. | CDI % | Total LOW (CAD) | Total HIGH (CAD) | DG % | Wastage % | Crew | Pricing Source / Basis
A — EARTHWORKS & MASS EXCAVATION
A — EARTHWORKS & MASS EXCAVATION | C-10-002 | Excavation common soil — stockpile haul 1-3km | m3 | 0.1 | 0.91 | 9.35 | 12.89 | 0 | 0 | 6% | 24 | 32 | 10% | 0% | B3 | Longer haul cycle
A — EARTHWORKS & MASS EXCAVATION | C-10-003 | Backfill common — spread and compact | m3 | 0.11 | 0.91 | 9.99 | 13.77 | 0 | 0 | 6% | 22 | 28 | 10% | 0% | B2 | Go-by x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-004 | Backfill Type 1 <250mm — spread and compact | m3 | 0.1 | 0.91 | 8.58 | 12.32 | 16.35 | 0 | 6% | 40 | 52 | 10% | 5% | B2 | Mat=$13.08 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-005 | Backfill Type 2 <100mm — spread and compact | m3 | 0.11 | 0.91 | 9.99 | 13.77 | 27.5 | 0 | 6% | 55 | 68 | 10% | 5% | B2 | Mat=$22.00 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-006 | Backfill Type 3 engineered — spread and compact | m3 | 0.21 | 0.91 | 19.09 | 26.31 | 18.96 | 0 | 6% | 72 | 88 | 10% | 5% | B2 | Mat=$15.17 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-007 | Rock excavation — blasted and loaded to truck | m3 | 0.35 | 0.88 | 31.83 | 43.88 | 0 | 0 | 6% | 38 | 58 | 10% | 0% | B3 | SME benchmark; drill+blast separate
A — EARTHWORKS & MASS EXCAVATION | C-10-008 | Overburden strip — doze + rip + stockpile | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 18 | 28 | 10% | 5% | B3 | Dozer push
A — EARTHWORKS & MASS EXCAVATION | C-10-009 | Granular A base <19mm — supply+place+compact | m3 | 0.25 | 0.91 | 22.73 | 31.31 | 43.75 | 0 | 6% | 105 | 135 | 5% | 5% | B2 | Mat=$35 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-010 | Granular B sub-base <75mm — supply+place+compact | m3 | 0.2 | 0.91 | 18.19 | 25.07 | 37.5 | 0 | 6% | 88 | 115 | 5% | 5% | B2 | Mat=$30 x1.25 avg
A — EARTHWORKS & MASS EXCAVATION | C-10-011 | Sand bedding layer — supply+place+compact | m3 | 0.22 | 0.91 | 20.01 | 27.57 | 52.5 | 0 | 6% | 115 | 145 | 5% | 0% | B2 | Mat=$42 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-012 | Topsoil placement — supply+spread | m3 | 0.35 | 0.91 | 31.83 | 43.88 | 20 | 0 | 6% | 55 | 80 | 5% | 5% | B1 | Supply+spread; seed separately
A — EARTHWORKS & MASS EXCAVATION | C-10-013 | Seeding and restoration — hydraulic | m2 | 0.02 | 0.91 | 1.82 | 1.25 | 1.5 | 0 | 5% | 4 | 8 | 5% | 0% | B1 | Per provincial restoration spec
A — EARTHWORKS & MASS EXCAVATION | C-10-014 | Cut-fill balanced earthworks — large-scale | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 22 | 30 | 10% | 0% | B3 | On-site haul <1km; GPS
A — EARTHWORKS & MASS EXCAVATION | C-10-015 | Settling pond / water management excavation | m3 | 0.09 | 0.91 | 8.19 | 11.28 | 0 | 0 | 6% | 22 | 28 | 10% | 0% | B3 | No mob/demob assumed
A — EARTHWORKS & MASS EXCAVATION | C-10-016 | Drill and blast — holes only (excav separate) | m3 | 0.3 | 0.88 | 27.28 | 37.59 | 4.5 | 0 | 6% | 42 | 65 | 10% | 0% | B3 | Explosives approx $3.60/m3 x1.25
B — WATER MANAGEMENT / SWM & ESC
B — WATER MANAGEMENT / SWM & ESC | C-20-002 | Riprap D50 150mm entrance/exit — supply+place | m3 | 0.4 | 0.88 | 36.38 | 50.13 | 0 | 0 | 6% | 65 | 100 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-003 | Riprap D50 300mm — supply+place | m3 | 0.5 | 0.88 | 45.47 | 62.66 | 0 | 0 | 6% | 75 | 120 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-004 | Riprap D50 600mm heavy — supply+place | m3 | 0.6 | 0.88 | 54.56 | 75.19 | 0 | 0 | 6% | 85 | 140 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-005 | Energy dissipator riprap — full supply+place | m3 | 0.75 | 0.88 | 68.19 | 93.98 | 50 | 0 | 6% | 120 | 200 | 5% | 0% | B3 | Incl. quarried rock supply
B — WATER MANAGEMENT / SWM & ESC | C-20-006 | 10oz non-woven geotextile cushion — S+I | m2 | 0.05 | 0.91 | 4.55 | 1.3 | 3.75 | 0 | 6% | 4 | 9 | 0% | 10% | B4 | Mat per supply quote Jan-2026
B — WATER MANAGEMENT / SWM & ESC | C-20-007 | 6oz non-woven geotextile separator — S+I | m2 | 0.04 | 0.91 | 3.64 | 1.04 | 2.5 | 0 | 6% | 3 | 6 | 0% | 10% | B4
B — WATER MANAGEMENT / SWM & ESC | C-20-008 | Silt fence heavy duty — supply+install | m | 0.15 | 0.91 | 13.64 | 3.9 | 6.25 | 0 | 6% | 18 | 28 | 5% | 0% | B1
B — WATER MANAGEMENT / SWM & ESC | C-20-009 | Straw bale flow check dam — supply+install | m | 0.2 | 0.91 | 18.19 | 5.2 | 8 | 0 | 5% | 22 | 32 | 5% | 0% | B1 | Temp ESC measure
B — WATER MANAGEMENT / SWM & ESC | C-20-010 | Sediment dewatering bag — supply+install | ea | 4 | 0.85 | 336 | 48 | 550 | 0 | 5% | 1200 | 1600 | 5% | 0% | B4 | Supply dominant cost
B — WATER MANAGEMENT / SWM & ESC | C-20-011 | Temp pump diesel submersible 8-week rental | ea | 0 | 0 | 0 | 0 | 0 | 7500 | 5% | 7500 | 9500 | 5% | 0% | N/A | Subcontract / dry hire
C — ROADS, PADS & WORKING SURFACES
C — ROADS, PADS & WORKING SURFACES | C-30-002 | Haul road — sub-grade preparation only | m2 | 0.12 | 0.91 | 10.91 | 15.04 | 0 | 0 | 6% | 14 | 22 | 10% | 0% | B2 | Cut+fill+compact 95% Proctor
C — ROADS, PADS & WORKING SURFACES | C-30-003 | Granular sub-base 300mm — supply+place+compact | m2 | 0.2 | 0.91 | 18.19 | 25.07 | 12 | 0 | 6% | 32 | 45 | 5% | 5% | B2
C — ROADS, PADS & WORKING SURFACES | C-30-004 | Granular surface course 150mm — supply+place | m2 | 0.15 | 0.91 | 13.64 | 18.8 | 9 | 0 | 6% | 22 | 32 | 5% | 5% | B2
C — ROADS, PADS & WORKING SURFACES | C-30-005 | Asphalt paving 50mm HL3 surface course | m2 | 0.2 | 0.91 | 18.19 | 25.07 | 18 | 0 | 5% | 45 | 62 | 5% | 2% | B2 | NS/ON/BC hot mix plant avail.
C — ROADS, PADS & WORKING SURFACES | C-30-006 | Equipment pad granular 600mm — heavy duty | m2 | 0.45 | 0.91 | 40.93 | 56.42 | 22 | 0 | 8% | 50 | 70 | 10% | 5% | B2 | Process plant; 98% Proctor
C — ROADS, PADS & WORKING SURFACES | C-30-007 | Equipment pad concrete 300mm slab on grade | m2 | 2.5 | 0.9 | 218.75 | 54 | 95 | 0 | 8% | 185 | 265 | 10% | 10% | C1 | Gran base+rebar+pour+cure
C — ROADS, PADS & WORKING SURFACES | C-30-008 | Geotextile separation under road base — S+I | m2 | 0.03 | 0.91 | 2.73 | 0.78 | 1.88 | 0 | 5% | 3 | 5 | 5% | 10% | B4 | 5oz woven
C — ROADS, PADS & WORKING SURFACES | C-30-009 | Road crown and ditching — motor grader finish | m | 0.06 | 0.91 | 5.46 | 7.52 | 0 | 0 | 5% | 5 | 10 | 5% | 0% | B1 | Shoulder ditch included
D — WRSA / TMF EMBANKMENT
D — WRSA / TMF EMBANKMENT | C-40-002 | TMF embankment common fill Zone A/B | m3 | 0.11 | 0.91 | 10 | 13.78 | 0 | 0 | 6% | 22 | 32 | 10% | 0% | B2 | 300mm lift; nuclear density; Dam Safety
D — WRSA / TMF EMBANKMENT | C-40-003 | TMF embankment random rockfill Zone C | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 18 | 28 | 10% | 0% | B3 | 500mm lift; vibrating roller
D — WRSA / TMF EMBANKMENT | C-40-004 | HDPE 2mm (80mil) liner — full S+I+CQA | m2 | 0.2 | 0.91 | 18.19 | 5.2 | 20 | 0 | 5% | 30 | 48 | 5% | 5% | B4 | Full scope incl. Ind. CQA
D — WRSA / TMF EMBANKMENT | C-40-005 | HDPE 1.5mm liner — full S+I+CQA | m2 | 0.18 | 0.91 | 16.37 | 4.68 | 14 | 0 | 5% | 22 | 34 | 5% | 5% | B4 | Secondary / lower-risk pond
D — WRSA / TMF EMBANKMENT | C-40-006 | Filter zone drainage blanket 19mm — supply+place | m3 | 0.45 | 0.91 | 40.93 | 56.42 | 62.5 | 0 | 6% | 120 | 175 | 10% | 0% | B4 | Clean crushed behind liner
D — WRSA / TMF EMBANKMENT | C-40-007 | Geonet / geocomposite drainage layer — S+I | m2 | 0.08 | 0.91 | 7.28 | 2.08 | 8.75 | 0 | 5% | 16 | 24 | 5% | 5% | B4 | Leachate/drainage over liner
D — WRSA / TMF EMBANKMENT | C-40-008 | Protective cover soil over liner — place+compact | m3 | 0.22 | 0.91 | 20.01 | 27.57 | 0 | 0 | 6% | 30 | 45 | 5% | 0% | B2 | 600mm min. cover
D — WRSA / TMF EMBANKMENT | C-40-009 | TMF perimeter ditch — cut+shape+riprap lined | m | 1.2 | 0.88 | 109.13 | 150.38 | 35 | 0 | 6% | 280 | 420 | 10% | 5% | B3 | Incl. riprap lining
E — DRAINAGE, CULVERTS & PIPING
E — DRAINAGE, CULVERTS & PIPING | C-50-002 | CSP culvert 750mm — supply+install+bedding | m | 2 | 0.91 | 181.88 | 51.98 | 368.75 | 0 | 8% | 580 | 750 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-003 | CSP culvert 900mm — supply+install+bedding | m | 2.5 | 0.91 | 227.35 | 64.97 | 437.5 | 0 | 8% | 680 | 880 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-004 | CSP culvert 1050mm — supply+install+bedding | m | 3 | 0.91 | 272.82 | 77.97 | 537.5 | 0 | 8% | 800 | 1020 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-005 | CSP culvert 1200mm — supply+install+bedding | m | 3.5 | 0.91 | 318.28 | 90.96 | 787.5 | 0 | 8% | 1100 | 1400 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-006 | CSP flow guard 600mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 2750 | 0 | 8% | 2500 | 3200 | 5% | 0% | B4 | Armtec Dec-2025
E — DRAINAGE, CULVERTS & PIPING | C-50-007 | CSP flow guard 750mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 11375 | 0 | 8% | 10500 | 13000 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-008 | CSP flow guard 900mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 15750 | 0 | 8% | 14000 | 17500 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-009 | CSP flow guard 1200mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 9500 | 0 | 8% | 8500 | 10500 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-010 | HDPE 100mm DR11 buried — excav+install+backfill | m | 1.5 | 0.91 | 136.41 | 38.98 | 68.75 | 0 | 8% | 310 | 400 | 5% | 0% | B4 | Trench+bedding+install+BF
E — DRAINAGE, CULVERTS & PIPING | C-50-011 | HDPE 150mm DR11 above grade + insulation | m | 1.2 | 0.91 | 109.13 | 31.18 | 275 | 0 | 8% | 250 | 330 | 5% | 0% | B4 | NE Jan-2026 supply +15% install
E — DRAINAGE, CULVERTS & PIPING | C-50-012 | HDPE 200mm DR11 above grade + insulation | m | 1.5 | 0.91 | 136.41 | 38.98 | 330 | 0 | 8% | 295 | 380 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-013 | HDPE 600mm DR17 above grade + insulation | m | 2 | 0.91 | 181.88 | 51.98 | 297.5 | 0 | 8% | 280 | 370 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-014 | HDPE 1200mm inlet piping — supply+install | m | 4 | 0.88 | 363.75 | 501.25 | 1137.5 | 0 | 8% | 1500 | 1900 | 5% | 0% | B4 | Vendor quote x1.10 +install
E — DRAINAGE, CULVERTS & PIPING | C-50-015 | Clear stone discharge pipe 450mm — S+I | m | 1.8 | 0.91 | 163.69 | 46.78 | 312.5 | 0 | 8% | 400 | 520 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-016 | Discharge trench clear stone — supply+place | m3 | 0.4 | 0.91 | 36.38 | 50.13 | 75 | 0 | 6% | 135 | 175 | 5% | 0% | B4 | 10% mat markup
F — CONCRETE
F — CONCRETE | C-60-002 | Concrete wall and grade beam — supply+pour+cure | m3 | 14.57 | 0.9 | 1310.63 | 409.78 | 854.03 | 0 | 6% | 2500 | 3200 | 10% | 10% | C1
F — CONCRETE | C-60-003 | Concrete pier — drill+form+pour | m3 | 25.49 | 0.9 | 2294.1 | 726.28 | 639.59 | 0 | 6% | 3600 | 4500 | 10% | 10% | C1
F — CONCRETE | C-60-004 | Concrete footing — continuous/isolated | m3 | 14.77 | 0.9 | 1329.63 | 409.78 | 666.74 | 0 | 6% | 2400 | 3000 | 10% | 10% | C1
F — CONCRETE | C-60-005 | Shotcrete rock reinforcement 50mm | m2 | 0.8 | 0.9 | 72 | 18.72 | 25 | 0 | 6% | 90 | 140 | 5% | 5% | C1 | Portal + slope reinforcement
F — CONCRETE | C-60-006 | Rebar Grade 400 — supply+install | tonne | 20 | 0.9 | 1800 | 500 | 2000 | 0 | 6% | 4000 | 6000 | 0% | 5% | D1 | CBSA 25% surtax Chinese rebar
G — STRUCTURAL STEEL
G — STRUCTURAL STEEL | C-70-002 | Steel beams medium 26-65 kg/m — supply+erect | tonne | 28 | 0.9 | 2561.2 | 621.6 | 4500 | 0 | 6% | 8000 | 9000 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-003 | Steel beams heavy 66-125 kg/m — supply+erect | tonne | 22 | 0.9 | 2012 | 488.4 | 4250 | 0 | 6% | 7500 | 8500 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-004 | Steel columns extra-heavy — supply+erect | tonne | 24 | 0.9 | 2194.4 | 532.8 | 4500 | 0 | 6% | 8000 | 9000 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-005 | Steel grating 32x4.8mm — supply+install | m2 | 3.5 | 0.9 | 322.5 | 77.7 | 275 | 0 | 6% | 660 | 750 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-006 | Handrail incl. toe plate and fasteners | m | 4 | 0.9 | 369 | 88.8 | 175 | 0 | 6% | 440 | 500 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-007 | Stairs — stringers and treads (less handrail) | m | 4.5 | 0.9 | 415.13 | 99.9 | 200 | 0 | 6% | 540 | 620 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-008 | Metal roof deck 22ga 76mm — supply+erect | m2 | 2 | 0.9 | 178 | 44.4 | 125 | 0 | 6% | 320 | 380 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-009 | Metal cladding 22ga prefinished — supply+erect | m2 | 1.8 | 0.9 | 160.2 | 38.48 | 100 | 0 | 6% | 265 | 320 | 0% | 0% | D1
H — CLOSURE & RECLAMATION
H — CLOSURE & RECLAMATION | C-80-002 | Riprap closure cap D50 300mm — supply+place | m3 | 0.55 | 0.88 | 50.02 | 68.93 | 40 | 0 | 5% | 90 | 150 | 5% | 0% | B3 | Long-term erosion protection
H — CLOSURE & RECLAMATION | C-80-003 | Cover system compacted clay 600mm | m3 | 0.35 | 0.91 | 31.83 | 43.88 | 12 | 0 | 8% | 58 | 95 | 10% | 0% | B2 | Perm ≤1x10-7 cm/s; nuclear density
H — CLOSURE & RECLAMATION | C-80-004 | Topsoil replacement — spread+seed | m2 | 0.05 | 0.91 | 4.55 | 1.3 | 3.75 | 0 | 5% | 5 | 12 | 10% | 5% | B1 | 300mm depth; provincial spec
H — CLOSURE & RECLAMATION | C-80-005 | HDPE cap liner 2mm — supply+install+CQA | m2 | 0.2 | 0.91 | 18.19 | 5.2 | 20 | 0 | 5% | 30 | 48 | 5% | 5% | B4 | Closure liner; same as TMF
I — BLASTING (FULL SCOPE)
I — BLASTING (FULL SCOPE) | B-01-002 | Drill blast hole 89-115mm — rotary drill | m | 0.25 | — | 26.92 | 8.79 | 0 | 0 | 6% | 25 | 45 | 10% | 0% | DR1 | Rate per lineal metre of hole
I — BLASTING (FULL SCOPE) | B-01-003 | Rock blasting — drill+charge+blast+clear (all-in) | m3 | 0.65 | — | 80.54 | 63.49 | 0 | 0 | 6% | 45 | 85 | 10% | 0% | B3 | Full scope; self-perform or sub
I — BLASTING (FULL SCOPE) | B-01-004 | Controlled blasting near structures — presplit | m | 0.8 | — | 86.15 | 28.13 | 0 | 0 | 6% | 55 | 95 | 10% | 0% | DR1 | Presplit perimeter holes
I — BLASTING (FULL SCOPE) | B-01-005 | Secondary breakage / pop shooting | ea | 2 | — | 219.78 | 61.54 | 0 | 0 | 6% | 250 | 550 | 5% | 0% | D2 | Large boulders
J — PERMANENT DEWATERING
J — PERMANENT DEWATERING | B-02-002 | Submersible pump station — small <50 L/s | ea | — | — | — | — | — | 65000 | 5% | 45000 | 85000 | 10% | 0% | B4 | Prepackaged wet well
J — PERMANENT DEWATERING | B-02-003 | Submersible pump station — large >50 L/s | ea | — | — | — | — | — | 185000 | 5% | 120000 | 250000 | 10% | 0% | B4 | Civil structure + mechanical
J — PERMANENT DEWATERING | B-02-004 | Forcemain HDPE 150mm buried — S+I | m | 1.5 | — | 191.21 | 48 | 62.68 | — | 6% | 320 | 420 | 8% | 0% | B4 | Trench+bedding+install+BF
J — PERMANENT DEWATERING | B-02-005 | Forcemain HDPE 200mm buried — S+I | m | 2 | — | 254.95 | 64 | 39.54 | — | 6% | 380 | 500 | 8% | 0% | B4
J — PERMANENT DEWATERING | B-02-006 | Wellpoint dewatering system — install+operate 4wk | LS | — | — | — | — | — | 50000 | 5% | 35000 | 65000 | 5% | 0% | B4 | Temp system; open excav near water table
K — BURIED SERVICES
K — BURIED SERVICES | B-03-002 | Water line HDPE 150mm buried — S+I | m | 2 | — | 254.95 | 64 | 39.54 | — | 6% | 380 | 500 | 8% | 0% | B4
K — BURIED SERVICES | B-03-003 | Water line HDPE 200mm buried — S+I | m | 2.5 | — | 318.68 | 80 | 25.85 | — | 6% | 450 | 620 | 8% | 0% | B4
K — BURIED SERVICES | B-03-004 | Sanitary sewer PVC 150mm buried — S+I | m | 1.8 | — | 229.45 | 57.6 | 71.44 | — | 6% | 380 | 520 | 8% | 0% | B4 | Incl. trench, bedding, pipe, BF
K — BURIED SERVICES | B-03-005 | Sanitary manhole precast 1200mm — S+I | ea | 8 | — | 1019.78 | 256 | 2969.5 | — | 6% | 4500 | 7500 | 8% | 0% | B4 | Incl. excavation, bedding, frame+cover
K — BURIED SERVICES | B-03-006 | Concrete thrust block — supply+form+pour | ea | 4 | — | 486.81 | 114.29 | 530.98 | — | 6% | 1200 | 2500 | 8% | 10% | C1 | At each bend/tee on pressure main
K — BURIED SERVICES | B-03-007 | Gate valve 150mm buried — S+I | ea | 3 | — | 382.42 | 96 | 1597.05 | — | 6% | 2200 | 3500 | 5% | 0% | B4 | Incl. valve box and operating nut
K — BURIED SERVICES | B-03-008 | Hydrant — supply+install | ea | 6 | — | 764.84 | 192 | 7062.03 | — | 6% | 8500 | 14000 | 5% | 0% | B4 | Incl. service line, valve, concrete pad
L — CONCRETE PAVING & CURBING
L — CONCRETE PAVING & CURBING | B-04-002 | Concrete paving 250mm reinforced — S+P | m2 | 4.5 | — | 547.66 | 128.57 | 0 | 0 | 6% | 220 | 300 | 8% | 8% | C1 | Heavy traffic; light rebar mat
L — CONCRETE PAVING & CURBING | B-04-003 | Concrete curb and gutter — S+F+P | m | 2.5 | — | 304.26 | 71.43 | 0 | 0 | 6% | 185 | 265 | 5% | 8% | C1 | Incl. forming, pour, cure
L — CONCRETE PAVING & CURBING | B-04-004 | Concrete wheel wash pad — supply+construct | ea | 40 | — | 4868.13 | 1142.86 | 10970.14 | — | 6% | 18000 | 35000 | 5% | 5% | C1 | Truckwash; grate+sump+recirculate pump
M — FENCING, SECURITY & WILDLIFE
M — FENCING, SECURITY & WILDLIFE | B-05-002 | Chain link fence 2.4m security — S+I | m | 1 | — | 124.86 | 50.27 | 0 | 0 | 6% | 110 | 165 | 5% | 0% | B1 | Security grade; top barbed wire
M — FENCING, SECURITY & WILDLIFE | B-05-003 | Wildlife exclusion fence 2.4m electrified | m | 1.5 | — | 187.29 | 75.41 | 0 | 0 | 6% | 165 | 260 | 5% | 0% | B1 | Grizzly/caribou/wildlife; energizer sep.
M — FENCING, SECURITY & WILDLIFE | B-05-004 | Fence gate single swing 4m — S+I | ea | 4 | — | 499.43 | 201.1 | 997.58 | — | 6% | 1800 | 3200 | 5% | 0% | B1
M — FENCING, SECURITY & WILDLIFE | B-05-005 | Fence gate double swing 8m — S+I | ea | 6 | — | 749.14 | 301.65 | 2251.1 | — | 6% | 3500 | 6500 | 5% | 0% | B1 | Truck gate; drop rod + lock
N — SITE SIGNAGE & TRAFFIC MGMT
N — SITE SIGNAGE & TRAFFIC MGMT | B-06-002 | Traffic control — flagging (per shift) | shift | 10 | — | 1248.57 | 502.75 | 0 | 0 | 6% | 850 | 1200 | 5% | 0% | B1 | 2-person crew with truck; per 10hr shift
N — SITE SIGNAGE & TRAFFIC MGMT | B-06-003 | Dust suppression — calcium chloride application | tonne | 0.1 | — | 12.49 | 5.03 | 407.01 | — | 6% | 450 | 650 | 5% | 0% | B1 | Effective 6-8 weeks per application
O — ROCK ANCHORS & STABILIZATION
O — ROCK ANCHORS & STABILIZATION | B-07-002 | Rock anchor active tensioned 32mm strand | ea | 8 | — | 861.54 | 281.32 | 1215.63 | — | 6% | 2500 | 5500 | 10% | 0% | DR1 | Pre-stressed; headplate; torqued to spec
O — ROCK ANCHORS & STABILIZATION | B-07-003 | Wire mesh rockfall protection — supply+pin | m2 | 0.6 | — | 74.34 | 58.6 | 0 | 0 | 6% | 65 | 120 | 10% | 5% | B3 | Double-twist hex mesh; portal/cut slope
O — ROCK ANCHORS & STABILIZATION | B-07-004 | Shotcrete with fibre 75mm — supply+apply | m2 | 1.2 | — | 146.04 | 34.29 | 0 | 0 | 6% | 120 | 195 | 5% | 5% | C1 | Steel or polypropylene fibre
O — ROCK ANCHORS & STABILIZATION | B-07-005 | Shotcrete with wire mesh 100mm — supply+apply | m2 | 1.8 | — | 219.07 | 51.43 | 0 | 0 | 6% | 165 | 250 | 5% | 5% | C1 | Welded wire mesh embedded; heavy support
P — CULVERT STRUCTURES
P — CULVERT STRUCTURES | B-08-002 | Precast box culvert 2400x1800mm — S+I | m | 18 | — | 2294.51 | 576 | 3261.57 | — | 6% | 6500 | 10500 | 8% | 0% | B4 | Large watercourse crossing
P — CULVERT STRUCTURES | B-08-003 | Precast arch culvert 3000mm span — S+I | m | 14 | — | 1784.62 | 448 | 2012.66 | — | 6% | 4500 | 8500 | 8% | 0% | B4 | Fish habitat; open bottom design
P — CULVERT STRUCTURES | B-08-004 | Headwall concrete — supply+form+pour | ea | 24 | — | 2920.88 | 685.71 | 4412.28 | — | 6% | 8500 | 16000 | 8% | 10% | C1 | Poured in place; per end per culvert
Q — AGGREGATE CRUSHING ON-SITE
Q — AGGREGATE CRUSHING ON-SITE | B-09-002 | Crushing — quarry to Granular A/B | tonne | 0.02 | — | 2.48 | 1.95 | 0 | 0 | 6% | 4.5 | 9.5 | 5% | 0% | B3 | Operating cost only; excl. mob/demob
Q — AGGREGATE CRUSHING ON-SITE | B-09-003 | Crushing — quarry to rip-rap D50 150-600mm | tonne | 0.02 | — | 2.48 | 1.95 | 0.76 | — | 6% | 5.5 | 12 | 5% | 0% | B3 | Incl. scalping and grading
R — UNDERGROUND CIVIL
R — UNDERGROUND CIVIL | U-10-001 | Shaft sinking 6m dia — D&B incl. ground support | m | 45 | — | 6675.82 | 3214.29 | 23128.76 | — | 6% | 35000 | 65000 | 15% | 0% | UC1 | Specialty shaft sinking contractor; vertical advance rate 1.5-3 m/day
R — UNDERGROUND CIVIL | U-10-002 | Shaft sinking 7m dia — D&B incl. ground support | m | 55 | — | 8159.34 | 3928.57 | 30364.92 | — | 6% | 45000 | 85000 | 15% | 0% | UC1 | Larger production / service shaft
R — UNDERGROUND CIVIL | U-10-003 | Lateral development 5×5 m drift — D&B incl. mucking | m | 18 | — | 2571.43 | 989.01 | 2571.64 | — | 6% | 6500 | 12500 | 15% | 0% | UC2 | Advance rate 4-8 m/day depending on rock and ground support
R — UNDERGROUND CIVIL | U-10-004 | Lateral development 5×6 m drift — D&B incl. mucking | m | 22 | — | 3142.86 | 1208.79 | 3667.22 | — | 6% | 8500 | 16000 | 15% | 0% | UC2 | Larger cross-section; ramp / production drift
R — UNDERGROUND CIVIL | U-10-005 | Raise bore 3m dia (vent / ore pass) | m | 12 | — | 1846.15 | 1054.95 | 1344.18 | — | 6% | 4500 | 8500 | 10% | 0% | UC3 | Specialty rig (Atlas/Strata); raise length up to 600 m
R — UNDERGROUND CIVIL | U-10-006 | Raise bore 5m dia (intake / exhaust raise) | m | 20 | — | 3076.92 | 1758.24 | 4127.1 | — | 6% | 9500 | 18000 | 10% | 0% | UC3 | Large diameter; longer reaming time
R — UNDERGROUND CIVIL | U-10-007 | Ground support — rock bolts 2.4m resin-grouted | ea | 0.5 | — | 71.43 | 27.47 | 0 | 0 | 6% | 85 | 165 | 10% | 0% | UC2 | Standard pattern bolting; 1.0-1.5 m grid
R — UNDERGROUND CIVIL | U-10-008 | Ground support — shotcrete with mesh 75-100mm UG | m2 | 1.5 | — | 214.29 | 82.42 | 0 | 0 | 6% | 185 | 320 | 10% | 5% | UC2 | Wet-mix shotcrete with robot arm; mesh embedded
R — UNDERGROUND CIVIL | U-10-009 | Ground support — fibre shotcrete 75mm UG | m2 | 1 | — | 142.86 | 54.95 | 0 | 0 | 6% | 145 | 240 | 10% | 5% | UC2 | Steel or polypropylene fibre; no mesh
R — UNDERGROUND CIVIL | U-10-010 | Cable bolts 12m twin-strand grouted | ea | 4.5 | — | 642.86 | 247.25 | 0 | 0 | 6% | 650 | 1250 | 10% | 0% | UC2 | Long-term ground support; intersections, large openings
R — UNDERGROUND CIVIL | U-10-011 | Mucking and tramming — load and haul UG 1-2 km | tonne | 0.1 | — | 14.29 | 5.49 | 0 | 0 | 6% | 18 | 32 | 10% | 0% | UC2 | LHD scoop + truck haul to ore pass / shaft
R — UNDERGROUND CIVIL | U-10-012 | Stope backfill — paste fill placement | m3 | 0.15 | — | 19.78 | 8.24 | 14.43 | — | 6% | 45 | 95 | 10% | 0% | UC4 | From surface paste plant; piped distribution
S — TAILINGS DAM ZONED CONSTRUCTION
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-001 | Starter dam — Zone A core (low-perm clay) | m3 | 0.15 | 0.91 | 18.69 | 14.05 | 3.11 | — | 6% | 38 | 65 | 10% | 5% | B2 | 300mm lifts; nuclear density; Atterberg + perm tests
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-002 | Starter dam — Zone B filter fine (transition) | m3 | 0.2 | 0.91 | 24.92 | 18.74 | 8.23 | — | 6% | 55 | 95 | 10% | 5% | B2 | Filter rule compliant; processed quarry sand
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-003 | Starter dam — Zone C filter coarse (drainage) | m3 | 0.18 | 0.91 | 22.43 | 16.86 | 22.03 | — | 6% | 65 | 115 | 10% | 5% | B2 | Clean crushed; >5x Zone B D85
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-004 | Starter dam — Zone D random rockfill (downstream) | m3 | 0.1 | 0.91 | 12.39 | 9.77 | 0 | 0 | 6% | 22 | 38 | 10% | 0% | B3 | Site-won rockfill; 500mm lifts; vibrating roller
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-005 | Dam raise — centerline construction per lift | m3 | 0.12 | 0.91 | 14.87 | 11.72 | 0 | 0 | 6% | 28 | 48 | 10% | 5% | B3 | Subsequent raises; mixed zone construction
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-006 | Dam raise — downstream construction per lift | m3 | 0.11 | 0.91 | 13.63 | 10.74 | 0 | 0 | 6% | 25 | 42 | 10% | 0% | B3 | Most conservative; preferred for high-risk dams
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-007 | Internal drainage — chimney drain construction | m3 | 0.4 | 0.88 | 52.73 | 13.24 | 37.8 | — | 6% | 110 | 180 | 10% | 0% | B4 | Vertical drain chimney; clean crushed; geotextile wrap
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-008 | Toe drain — supply+install with geotextile sock | m | 1 | 0.91 | 127.47 | 32 | 0 | 0 | 6% | 165 | 285 | 10% | 10% | B4 | Perforated HDPE in clean crushed; outflow monitoring
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-009 | Dam instrumentation — VW piezometer installation | ea | 16 | — | 2074.73 | 738.46 | 488.7 | — | 6% | 3500 | 6500 | 10% | 0% | DI1 | Geokon vibrating wire; surface readout
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-010 | Dam instrumentation — inclinometer installation | ea | 24 | — | 3112.09 | 1107.69 | 3799.09 | — | 6% | 8500 | 16000 | 10% | 0% | DI1 | Slope-displacement monitoring; up to 50m casing
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-011 | Dam instrumentation — survey monument installation | ea | 6 | — | 778.02 | 276.92 | 0 | 0 | 6% | 850 | 1650 | 10% | 0% | DI1 | Prism + concrete pin; monthly survey
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-012 | Spillway — concrete-lined emergency overflow | m2 | 6 | 0.9 | 738.33 | 173.33 | 0 | 0 | 6% | 450 | 750 | 10% | 10% | C1 | Reinforced concrete; designed for PMF or 1:10000
S — TAILINGS DAM ZONED CONSTRUCTION | T-20-013 | Reclaim barge — supply+install (tailings pond) | ea | — | — | — | — | — | 1125000 | 5% | 750000 | 1500000 | 10% | 0% | MEC | Floating barge with vertical turbine pump; mech sub
T — HEAP LEACH PAD CONSTRUCTION
T — HEAP LEACH PAD CONSTRUCTION | H-30-001 | Pad sub-grade prep — cut/fill/compact to 95% Proctor | m2 | 0.15 | 0.91 | 18.69 | 14.05 | 0 | 0 | 6% | 18 | 32 | 10% | 0% | B2 | Surface tolerance ±15mm; nuclear density
T — HEAP LEACH PAD CONSTRUCTION | H-30-002 | Low-perm clay liner 300mm (secondary containment) | m2 | 0.3 | 0.91 | 37.38 | 28.1 | 0 | 0 | 6% | 28 | 48 | 10% | 5% | B2 | K ≤1×10⁻⁹ m/s; nuclear density + perm tests
T — HEAP LEACH PAD CONSTRUCTION | H-30-003 | Primary HDPE liner 80 mil — supply+install+CQA | m2 | 0.2 | 0.91 | 25.49 | 6.4 | 0 | 0 | 6% | 32 | 55 | 5% | 5% | B4 | Double-textured; LLDPE for slopes; full CQA
T — HEAP LEACH PAD CONSTRUCTION | H-30-004 | Secondary HDPE liner 60 mil — supply+install+CQA | m2 | 0.18 | 0.91 | 22.95 | 5.76 | 0 | 0 | 6% | 24 | 42 | 5% | 5% | B4 | Double-liner system; leak detection between
T — HEAP LEACH PAD CONSTRUCTION | H-30-005 | Geonet drainage layer between liners — S+I | m2 | 0.08 | 0.91 | 10.2 | 2.56 | 4.22 | — | 6% | 18 | 28 | 5% | 5% | B4 | Leak detection drainage path
T — HEAP LEACH PAD CONSTRUCTION | H-30-006 | Drain rock cover 300mm — supply+place over primary | m3 | 0.3 | 0.91 | 38.24 | 9.6 | 4.05 | — | 6% | 55 | 95 | 10% | 0% | B4 | Clean crushed 19-50mm; placed by low-ground-pressure dozer
T — HEAP LEACH PAD CONSTRUCTION | H-30-007 | HDPE perforated collection manifold 150-200mm — S+I | m | 1.5 | 0.91 | 191.21 | 48 | 0 | 0 | 6% | 220 | 360 | 8% | 5% | B4 | In drain rock layer; piped to PLS pond
T — HEAP LEACH PAD CONSTRUCTION | H-30-008 | Pregnant solution (PLS) pond construction — multi-liner | m2 | 0.5 | 0.91 | 63.74 | 16 | 0.45 | — | 6% | 85 | 145 | 10% | 10% | B4 | Same multi-liner system; tertiary GCL
T — HEAP LEACH PAD CONSTRUCTION | H-30-009 | Solution piping HDPE 200mm — S+I (header to pad) | m | 1.5 | 0.91 | 191.21 | 48 | 39.09 | — | 6% | 295 | 445 | 5% | 0% | B4 | Above-grade; insulated for cold climates
T — HEAP LEACH PAD CONSTRUCTION | H-30-010 | Drip irrigation network — supply+install per ha | ha | — | — | — | — | — | 107500 | 5% | 75000 | 140000 | 10% | 5% | B4 | Per hectare of pad surface; emitter density site-specific
U — PROCESS PLANT CIVIL
U — PROCESS PLANT CIVIL | P-40-001 | Mill foundation — large mat (semi-autogenous) | m3 | 14 | 0.9 | 1722.78 | 404.44 | 514.29 | — | 6% | 2800 | 3800 | 10% | 10% | C1 | Mass concrete pour; cooling pipes; 40 MPa min
U — PROCESS PLANT CIVIL | P-40-002 | Mill foundation — ball mill (smaller) | m3 | 13 | 0.9 | 1599.72 | 375.56 | 524.72 | — | 6% | 2650 | 3500 | 10% | 10% | C1 | Reinforced mat; vibration design
U — PROCESS PLANT CIVIL | P-40-003 | Primary crusher foundation — pier + mat | m3 | 18 | 0.9 | 2215 | 520 | 283.87 | — | 6% | 3200 | 4500 | 10% | 10% | C1 | Heavy reinforcement; isolation joints
U — PROCESS PLANT CIVIL | P-40-004 | SAG mill apron feeder pit excavation + concrete | m3 | 16 | 0.9 | 1968.89 | 462.22 | 399.08 | — | 6% | 3000 | 4200 | 10% | 10% | C1 | Below-grade structure; dewatering required
U — PROCESS PLANT CIVIL | P-40-005 | Conveyor gallery footings — incl. excavation+concrete | ea | 28 | — | 3407.69 | 800 | 7113.06 | — | 6% | 12000 | 22000 | 10% | 10% | C1 | Per support; spacing 18-30m typical
U — PROCESS PLANT CIVIL | P-40-006 | Conveyor head pulley structure — pad+drainage | ea | — | — | — | — | — | 70000 | 5% | 45000 | 95000 | 10% | 10% | C1 | Includes drainage trench + access
U — PROCESS PLANT CIVIL | P-40-007 | Ore stockpile reclaim tunnel — cast-in-place concrete | m | — | — | — | — | — | 25000 | 5% | 18000 | 32000 | 10% | 10% | C1 | 5×6 m internal; rebar heavy; designed for stockpile load
U — PROCESS PLANT CIVIL | P-40-008 | Thickener foundation — circular ring beam + center column | ea | — | — | — | — | — | 265000 | 5% | 180000 | 350000 | 10% | 10% | C1 | Per thickener; size-dependent (30-60m dia)
U — PROCESS PLANT CIVIL | P-40-009 | Flotation cell foundation — multi-cell platform | m2 | 5 | 0.9 | 615.28 | 144.44 | 0 | 0 | 6% | 285 | 450 | 10% | 10% | C1 | Reinforced slab on elevated structural steel
U — PROCESS PLANT CIVIL | P-40-010 | Tank farm containment — secondary bund (oil/reagent) | m2 | 4 | 0.91 | 486.81 | 114.29 | 0 | 0 | 6% | 220 | 380 | 10% | 10% | C1 | Concrete walls + coated floor; spill volume design
U — PROCESS PLANT CIVIL | P-40-011 | Process building slab on grade — 250mm with rebar mat | m2 | 2.5 | 0.9 | 307.64 | 72.22 | 0 | 0 | 6% | 195 | 285 | 10% | 10% | C1 | Industrial slab; trench drains + sumps
V — SLURRY / CONCENTRATE / FUEL PIPELINE
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-001 | Pipeline ROW clearing + grading per km | km | — | — | — | — | — | 46500 | 5% | 28000 | 65000 | 10% | 0% | B3 | 30m corridor; light bush; remove timber
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-002 | Pipeline trench 1.5m depth — excavation only | m | 0.2 | 0.91 | 24.78 | 19.53 | 0 | 0 | 6% | 45 | 85 | 10% | 0% | B3 | Common soil; rock additive
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-003 | HDPE slurry pipe 250mm SDR 11 — supply | m | — | — | — | — | — | 215 | 5% | 165 | 265 | 5% | 0% | B4 | PE100 PE4710; abrasion-resistant grade
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-004 | HDPE slurry pipe 400mm SDR 11 — supply | m | — | — | — | — | — | 502.5 | 5% | 385 | 620 | 5% | 0% | B4 | Larger diameter; project-specific RFQ
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-005 | Steel slurry pipe 300mm Sch 80 (high pressure) | m | — | — | — | — | — | 585 | 5% | 450 | 720 | 5% | 0% | B4 | Carbon steel; for >12 bar service
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-006 | Pipeline install incl. fusion/weld + lay | m | 1.2 | 0.88 | 158.18 | 39.71 | 0 | 0 | 6% | 140 | 240 | 8% | 0% | B4 | Trench-lay + tie-in; varies by pipe size/material
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-007 | Pipeline pigging launcher/receiver station | ea | — | — | — | — | — | 125000 | 5% | 85000 | 165000 | 10% | 0% | B4 | Skid-mounted; flanged tie-in; concrete pad
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-008 | Pipeline valve station incl. concrete pad + fence | ea | — | — | — | — | — | 85000 | 5% | 55000 | 115000 | 10% | 0% | B4 | Block + actuator valves; typically every 5-10 km
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-009 | Pipeline cathodic protection system — per km | km | — | — | — | — | — | 26500 | 5% | 18000 | 35000 | 10% | 0% | E1 | Sacrificial anodes + test stations; carbon steel only
V — SLURRY / CONCENTRATE / FUEL PIPELINE | SP-50-010 | River / road crossing — horizontal directional drill | m | — | — | — | — | — | 2000 | 5% | 1200 | 2800 | 15% | 0% | HDD | Specialty sub; rates per length of bore
W — MINE SITE BRIDGES & CROSSINGS
W — MINE SITE BRIDGES & CROSSINGS | BR-60-001 | Modular steel bridge ≤20 m span — S+I | ea | — | — | — | — | — | 280000 | 5% | 180000 | 380000 | 10% | 0% | ST1 | Bailey-style or fabricated; light vehicle
W — MINE SITE BRIDGES & CROSSINGS | BR-60-002 | Cast-in-place concrete bridge 15-25 m span — S+I | m2 deck | — | — | — | — | — | 6000 | 5% | 4500 | 7500 | 10% | 10% | C1 | Single span; concrete abutments + deck
W — MINE SITE BRIDGES & CROSSINGS | BR-60-003 | Mine haul road bridge 30-50 m — S+I | m2 deck | — | — | — | — | — | 8750 | 5% | 6500 | 11000 | 15% | 10% | ST1 | Heavy axle load design; reinforced abutments
W — MINE SITE BRIDGES & CROSSINGS | BR-60-004 | Bridge abutment — concrete cast-in-place (each) | m3 | 18 | 0.9 | 2215 | 520 | 0 | 0 | 6% | 2800 | 4200 | 10% | 10% | C1 | Heavy reinforcement; soil pressure design
W — MINE SITE BRIDGES & CROSSINGS | BR-60-005 | Bridge pier — concrete cast-in-place (each) | m3 | 22 | 0.9 | 2707.22 | 635.56 | 0 | 0 | 6% | 3200 | 4800 | 10% | 10% | C1 | Pier + cap; underwater work additive
W — MINE SITE BRIDGES & CROSSINGS | BR-60-006 | Large precast box culvert 3000×2400 mm — S+I | m | 20 | 0.85 | 2729.41 | 685.18 | 6962.77 | — | 6% | 11000 | 18500 | 8% | 0% | B4 | Heavy lift; crane + bedding; per linear m
X — POWER LINE & SUBSTATION CIVIL
X — POWER LINE & SUBSTATION CIVIL | EL-70-001 | Tower foundation — concrete pier (138 kV transmission) | ea | 24 | — | 2920.88 | 685.71 | 13374.54 | — | 6% | 18000 | 32000 | 10% | 10% | C1 | Per tower; 4-leg lattice; pier+cap typical
X — POWER LINE & SUBSTATION CIVIL | EL-70-002 | Tower foundation — concrete pier (240 kV transmission) | ea | 32 | — | 3894.51 | 914.29 | 19719.5 | — | 6% | 26000 | 48000 | 10% | 10% | C1 | Larger; deeper footing; engineered per tower
X — POWER LINE & SUBSTATION CIVIL | EL-70-003 | Distribution pole foundation — drilled + concrete | ea | 6 | — | 749.14 | 301.65 | 694.49 | — | 6% | 1850 | 3500 | 5% | 5% | B1 | Per pole; ≤25 m distribution lines
X — POWER LINE & SUBSTATION CIVIL | EL-70-004 | Substation pad — granular sub-base + crushed surface | m2 | 0.4 | 0.91 | 49.84 | 37.47 | 0 | 0 | 6% | 55 | 90 | 10% | 5% | B2 | Per substation footprint; resistivity-controlled
X — POWER LINE & SUBSTATION CIVIL | EL-70-005 | Substation control building slab + foundation | m2 | 3.5 | 0.9 | 430.69 | 101.11 | 0 | 0 | 6% | 285 | 450 | 10% | 10% | C1 | Industrial slab with cable trenches
X — POWER LINE & SUBSTATION CIVIL | EL-70-006 | Substation grounding grid — copper mat install | m2 | 0.05 | 0.91 | 6.14 | 0.75 | 10.09 | — | 6% | 18 | 32 | 5% | 5% | E1 | Cu cable grid + ground rods; tested resistivity
X — POWER LINE & SUBSTATION CIVIL | EL-70-007 | Transmission line ROW clearing 50 m wide per km | km | — | — | — | — | — | 55000 | 5% | 35000 | 75000 | 10% | 0% | B3 | Light bush; remove timber to sale; access trail
Y — HYDRAULIC STRUCTURES
Y — HYDRAULIC STRUCTURES | HY-80-001 | Diversion channel excavation common soil — trapezoidal | m3 | 0.1 | 0.91 | 12.39 | 9.77 | 0 | 0 | 6% | 18 | 32 | 10% | 0% | B3 | Designed channel cross-section; bottom grade controlled
Y — HYDRAULIC STRUCTURES | HY-80-002 | Diversion channel — riprap class A (D50 150mm) lining | m3 | 0.45 | 0.88 | 57.66 | 45.45 | 0 | 0 | 6% | 85 | 140 | 5% | 0% | B3 | Slope and bed armouring
Y — HYDRAULIC STRUCTURES | HY-80-003 | Diversion channel — riprap class B (D50 300mm) lining | m3 | 0.55 | 0.88 | 70.47 | 55.55 | 0 | 0 | 6% | 105 | 175 | 5% | 0% | B3 | Higher velocity channel
Y — HYDRAULIC STRUCTURES | HY-80-004 | Diversion channel — riprap class C (D50 600mm) lining | m3 | 0.65 | 0.88 | 83.28 | 65.65 | 0 | 0 | 6% | 135 | 220 | 5% | 0% | B3 | Extreme flow protection; large quarry-run
Y — HYDRAULIC STRUCTURES | HY-80-005 | Energy dissipator — concrete chute with baffles | m3 | 12 | 0.9 | 1476.67 | 346.67 | 629.49 | — | 6% | 2600 | 4200 | 10% | 10% | C1 | Stilling basin or baffle chute; engineered geometry
Y — HYDRAULIC STRUCTURES | HY-80-006 | Spillway weir — concrete crest with rebar | m3 | 14 | 0.9 | 1722.78 | 404.44 | 561.46 | — | 6% | 2850 | 4500 | 10% | 10% | C1 | Ogee or broad-crested; engineered to design flow
Y — HYDRAULIC STRUCTURES | HY-80-007 | Diversion inlet structure — concrete + trash rack | ea | — | — | — | — | — | 100000 | 5% | 65000 | 135000 | 10% | 10% | C1 | Per inlet; size-dependent (typ 2-5 m wide)
Y — HYDRAULIC STRUCTURES | HY-80-008 | Geotextile underlayer under riprap (filter fabric) | m2 | 0.04 | 0.91 | 5.1 | 1.28 | 0 | 0 | 6% | 5 | 9 | 5% | 10% | B4 | 12 oz non-woven; ASTM AOS-spec
Y — HYDRAULIC STRUCTURES | HY-80-009 | Diversion ditch — small unlined common section | m | 0.25 | 0.91 | 31.15 | 23.42 | 0 | 0 | 6% | 25 | 45 | 10% | 0% | B2 | Field ditches; minor catchment
Notes: 'Total LOW/HIGH' = all-in unit price already including labour + equipment + material + subcontract + CDI (where shown). For Rev G items (sections I–Q) build-up columns are not decomposed in source — use the Unit Rate Build-Up Calculator (Sheet 09) to reverse-engineer if required. 'DG %' = design growth (apply to quantity, see Sheet 03). 'Wastage %' = apply to material take-off. 'Crew' = SME-typical crew code (Sheet 04).

## 09 Unit Rate Calculator
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
UNIT RATE BUILD-UP CALCULATOR [TEMPLATE — enter inputs in blue cells]
Field | Input / Value | Source / Reference
WBS reference (e.g. C-30-002) | <enter> | Project WBS code
Item description | <enter> | Plain English
Unit of measure (UOM) | m3 | m3, m2, m, tonne, ea, LS
Crew code (B1–N1) | B3 | From Sheet 04
Crew total rate ($/hr) | 201.63 | From Sheet 04 — 2026 Total
Unit MH per UOM | 0.1 | Time per unit; SME baseline 0.08-0.50
Productivity factor (0.80–1.00) | 0.91 | Reduces idealized output to realistic
Crew cost per unit ($) [calculated] | 0 | = Unit MH / Prod × Crew $/hr
Unit material cost ($) | 0 | Supplied + delivered
Material wastage (%) | 0.05 | From Sheet 03 — 0% to 15% typical
Adjusted material cost ($) [calc] | 0 | = Mat × (1+wastage)
Unit subcontract cost ($) | 0 | Per sub quote; bare cost
Contractor Distributable Indirect (CDI) % | 0.06 | From Sheet 11 — 6-10% typical
Subtotal direct + CDI ($) [calc] | 0 | = (Crew+Mat+Sub) × (1+CDI)
Design growth (Class 3 baseline) % | 0.1 | From Sheet 03 — 2-20% by class
Regional adjustor (e.g. 1.10) | 1 | From Sheet 14 — 1.00 to 1.55
FINAL UNIT RATE BEFORE MARKUP STACK ($) [calc] | 0 | = Subtotal × (1+DG) × Regional adjustor
[TEMPLATE] This calculator builds a single direct unit rate. The 6-layer markup stack (OH, Bond/Ins, Contingency, Profit) is applied at project roll-up (Sheet 21). For Sheet 08 entries already include CDI in the LOW/HIGH columns. For subcontract-dominant work (e.g. blasting, liner) set Unit MH=0 and place sub quote in Subcontract row.

## 10 Bid Screening
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID SCREENING — UNIT COST SENSE-CHECKS — CANADA 2026 — SOURCE: Rev G Bid Screening tab
Category | Benchmark Item | UOM | Floor (CAD) | Ceiling (CAD) | Bid Screening Guidance
EARTHWORKS | Mass earthworks — rock (blasted) | $/m3 | 55 | 120 | Includes drill, blast, load, haul 1km
EARTHWORKS | Engineered fill compacted Zone A/B | $/m3 | 22 | 45 | Material, place, compact, test
EARTHWORKS | Granular road base 150mm | $/m2 | 22 | 42 | Supply+place+compact; material included
EARTHWORKS | Haul road full build (sub-grade to surface) | $/m2 | 65 | 120 | 8m wide single lane; all lifts
EARTHWORKS | Strip and grub per hectare | $/ha | 8500 | 18000 | Light bush; add for rock; add for timber
WRSA / TMF | TMF embankment engineered fill | $/m3 | 22 | 45 | Zone A/B compacted; nuclear density testing
WRSA / TMF | HDPE liner 2mm supply+install | $/m2 | 28 | 55 | Full scope incl. CQA; verify CQA included
WRSA / TMF | TMF perimeter ditch riprap lined | $/m | 280 | 500 | If below $280 likely missing riprap lining
DRAINAGE | CSP culvert 1200mm supply+install | $/m | 1000 | 1600
DRAINAGE | HDPE 150mm above grade insulated | $/m | 230 | 380 | If below $230 check insulation is included
DRAINAGE | Flow guard 600mm supply+install | $/ea | 2200 | 3500
DRAINAGE | Flow guard 1200mm supply+install | $/ea | 8000 | 12000
CONCRETE | Concrete foundation/wall | $/m3 | 2200 | 3500 | Formed; higher labour content
CONCRETE | Shotcrete with fibre 75mm | $/m2 | 90 | 160 | If below $90 check mix design and CQA
CONCRETE | Rebar supply+install | $/tonne | 3800 | 6500 | CBSA 25% surtax; verify Canadian/US source
BLASTING | Pre-blast survey per structure | $/struct | 3000 | 9000 | Mandatory; missing = liability exposure
FENCING | Wildlife exclusion electrified 2.4m | $/m | 150 | 280 | Energizer and monitoring system separate
BURIED SERVICES | Sanitary manhole precast 1200mm | $/ea | 4000 | 8000 | Incl. excavation, bedding, frame+cover
OVERHEAD CHECK | Contractor OH+profit — $50M project | % of dir. | 14% | 22% | Scale efficiency on larger projects
OVERHEAD CHECK | Performance + L&M bond (>$25M) | % of cont. | 0.75% | 1.25% | Check surety capacity and history

## 11 Contractor Indirects
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONTRACTOR INDIRECTS (CDI) & OVERHEAD BUILD-UP — CANADA 2026 — SOURCE: Rev G Overhead Build-Up tab
Category | Item | UOM | 2026 Low (CAD) | 2026 High (CAD) | SME Notes
FIELD OFFICE & SITE ESTABLISHMENT
FIELD OFFICE & SITE ESTABLISHMENT | Site trailer — lunchroom/dryroom | month | 1500 | 2500
FIELD OFFICE & SITE ESTABLISHMENT | Temporary power — generator 100kW diesel | month | 4500 | 8500 | Incl. fuel; or hook-up to utility sep.
FIELD OFFICE & SITE ESTABLISHMENT | Temp power — 250kW generator large camp | month | 9500 | 16000
FIELD OFFICE & SITE ESTABLISHMENT | Site IT, internet and communication | month | 850 | 2500 | Starlink or repeater; rural mine sites
FIELD OFFICE & SITE ESTABLISHMENT | Site vehicle — project truck leased | month | 1200 | 1800 | Per PU truck; fuel separate
FIELD OFFICE & SITE ESTABLISHMENT | Site vehicle — crew bus leased | month | 3500 | 6500 | 20-seat; daily crew transport
FIELD OFFICE & SITE ESTABLISHMENT | Mob/demob — site setup and teardown | LS | 35000 | 85000 | All temp facilities; charged once
PROJECT MANAGEMENT STAFF
PROJECT MANAGEMENT STAFF | Senior Project Engineer | month | 14000 | 20000
PROJECT MANAGEMENT STAFF | Field Engineer / QC Engineer | month | 11000 | 16000
PROJECT MANAGEMENT STAFF | Site Safety Officer (NCSO certified) | month | 12000 | 17000 | Dedicated; mandatory >20 workers
PROJECT MANAGEMENT STAFF | Senior Superintendent | month | 16000 | 24000
PROJECT MANAGEMENT STAFF | General Foreman | month | 13000 | 19000
PROJECT MANAGEMENT STAFF | Document Controller / Field Admin | month | 7500 | 11000
QUALITY CONTROL & TESTING
QUALITY CONTROL & TESTING | Nuclear density testing — crew/day | day | 850 | 1500 | One tech; one nuclear gauge
QUALITY CONTROL & TESTING | Concrete cylinder testing — per set | set | 185 | 350 | 4 cylinders; 28-day break; per pour
QUALITY CONTROL & TESTING | Aggregate gradation testing | test | 250 | 450 | Per material source change or 500 tonne
QUALITY CONTROL & TESTING | Geomembrane weld testing (spark test) | m weld | 2.5 | 4.5 | 100% of seams; third-party CQA
QUALITY CONTROL & TESTING | Survey control — survey crew/day | day | 2500 | 4500 | Layout, grades, as-builts
ENVIRONMENTAL COMPLIANCE
ENVIRONMENTAL COMPLIANCE | Spill kit and containment supplies | month | 350 | 750 | Per site regulation; replenished monthly
ENVIRONMENTAL COMPLIANCE | Environmental monitoring (water sampling) | sample | 450 | 950 | Lab analysis; site discharge monitoring
ENVIRONMENTAL COMPLIANCE | Environmental coordinator (part-time) | month | 5500 | 9500 | Required near watercourse crossings
COMPANY HEAD OFFICE OVERHEAD
COMPANY HEAD OFFICE OVERHEAD | Warranty/deficiency holdback allowance | % of cont. | 0.5% | 1.0% | 12-month deficiency period
CDI typical totals at bid stage: 12-18% of direct cost for mid-size mining civil. Overhead (Sheet 15 markup) is additional. Camp/LOA cost (see Sheet 05 O2/O3) is shown separately when used and is not duplicated here.

## 12 Bonding & Insurance
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BONDING & INSURANCE RATES — CANADA 2026 — SOURCE: Rev G Bonding & Insurance tab
Category | Item | Basis | Rate Low | Rate High | SME Notes
SURETY BONDS
SURETY BONDS | Performance Bond — small contract (<$5M) | % of contract | 1.5% | 2.5% | Higher rate for smaller contracts
SURETY BONDS | Performance Bond — medium ($5-$25M) | % of contract | 1.0% | 1.8% | Mid-tier; established contractor
SURETY BONDS | Performance Bond — large (>$25M) | % of contract | 0.75% | 1.25% | Volume discount; strong surety history
SURETY BONDS | Labour & Material Payment Bond | % of contract | 0.5% | 1.0% | Required CCDC 2; bundled w/ perf bond
SURETY BONDS | Maintenance/Warranty Bond — 12 month | % of contract | 0.5% | 1.0% | Some mining owners require
SURETY BONDS | Surety capacity rule of thumb | Max single contract | 10x NWC | — | Surety evaluates Character/Capacity/Capital
LIABILITY INSURANCE
LIABILITY INSURANCE | Commercial General Liability (CGL) | Per $1,000 payroll | $5 | $8 | Standard mining-civil contractor CGL; bid-stage rate
LIABILITY INSURANCE | Excess / Umbrella Liability | Annual policy | $8,500 | $22,000 | $5M–$25M limits common on mining heavy civil
LIABILITY INSURANCE | Contractor's Pollution Liability | Annual policy | $1,500 | $3,500 | Fuel/chemical spill; liner failure; contamination
LIABILITY INSURANCE | Builder's Risk / Course of Construction | % of contract value | 0.15% | 0.35% | Owner often requires; covers in-progress works
WCB
WCB | Labourer — Alberta WCB Industry 41 | Per $100 payroll | $3.80 | $5.20 | Lower than eastern provinces
WCB | Labourer — BC WorkSafeBC Class 711001 | Per $100 payroll | $4.50 | $6.00 | 2026 WorkSafeBC
WCB | Labourer — NS WCB NS | Per $100 payroll | $3.80 | $5.50 | Atlantic Canada
WCB | Labourer — NL WorkplaceNL | Per $100 payroll | $4.00 | $5.80 | 2026 WorkplaceNL
WCB | Labourer — Quebec CNESST | Per $100 payroll | $5.50 | $8.00 | Higher than national average
WCB | Labourer — Ontario WSIB Class G1 (heavy civil) | Per $100 payroll | $5.20 | $6.80 | 2026 WSIB; mining-civil rate group
WCB | Equipment Operator — all provinces | Per $100 payroll | $3.50 | $5.00 | Lower risk class than labourer
WCB | Blaster / Driller — elevated risk | Per $100 payroll | $5.50 | $8.00 | Elevated risk classification
PROPERTY INSURANCE
PROPERTY INSURANCE | Contractor's Equipment Floater | % of fleet repl/yr | 0.5% | 1.2% | Check if already in equipment hourly rate
Typical bid stage: Bonding 1.5-3.0% of contract (perf + L&M + warranty bundled); General Liability ~$5-$8 / $1,000 payroll; Builder's Risk 0.15-0.35% of contract value. WCB is province-specific — confirm classification and base rate before pricing.

## 13 Standby & Schedule
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
STANDBY RATES & SCHEDULE COST DRIVERS — CANADA 2026 — SOURCE: Rev G Standby & Schedule tab
Category | Item | UOM | 2026 Low (CAD) | 2026 High (CAD) | SME Notes
EQUIPMENT STANDBY RATES
EQUIPMENT STANDBY RATES | Excavator 20-25T (Cat 320) — standby | hr | 110 | 155
EQUIPMENT STANDBY RATES | Excavator 35-40T (Cat 336) — standby | hr | 140 | 200
EQUIPMENT STANDBY RATES | Track dozer D8T — standby | hr | 155 | 215
EQUIPMENT STANDBY RATES | Motor grader Cat 140M — standby | hr | 110 | 155
EQUIPMENT STANDBY RATES | Rough terrain crane RT 60T — standby | hr | 320 | 480 | Minimum 4hr call-out
EQUIPMENT STANDBY RATES | Crawler crane 150T — standby | hr | 850 | 1300 | Minimum 4hr call-out; rigging crew separate
EQUIPMENT STANDBY RATES | Tandem dump truck — standby | hr | 65 | 95 | Operator + idle truck; per hour
EQUIPMENT STANDBY RATES | Tri-axle dump truck — standby | hr | 75 | 110 | Operator + idle truck; per hour
EQUIPMENT STANDBY RATES | Wheel loader Cat 950M — standby | hr | 90 | 135 | Operator + idle equipment
EQUIPMENT STANDBY RATES | Compactor / roller — standby | hr | 70 | 100 | Operator + idle equipment
LABOUR STANDBY RATES
LABOUR STANDBY RATES | Equipment operator — standby | hr | 93 | 128 | Full burdened; equipment idle alongside
LABOUR STANDBY RATES | Labourer — standby | hr | 82 | 95 | Full burdened; weather/owner hold
LABOUR STANDBY RATES | Foreman / lead — standby | hr | 116 | 140 | Full burdened; site retained during hold
LABOUR STANDBY RATES | Project Manager — holding cost per week | week | 14000 | 20000 | Senior PE/PM retained per Sheet 11; full burdened
LABOUR STANDBY RATES | Superintendent — holding cost per week | week | 16000 | 24000 | Senior super retained per Sheet 11
LABOUR STANDBY RATES | Crew standby — B3 heavy civil crew of 10 | day | 7000 | 10000 | Full crew retained; weather hold or owner delay
DELAY / ACCELERATION PREMIUMS
DELAY / ACCELERATION PREMIUMS | Overtime premium — time-and-a-half (1.5x) | % add | 50% | 50% | Hours 9-12 in 12hr shift; Saturday
DELAY / ACCELERATION PREMIUMS | Overtime premium — double time (2x) | % add | 100% | 100% | Sunday + statutory holidays
DELAY / ACCELERATION PREMIUMS | Shift premium — afternoon shift | % add | 5% | 10% | Per CBA; project specific
DELAY / ACCELERATION PREMIUMS | Shift premium — night shift | % add | 10% | 15% | Per CBA; project specific
DELAY / ACCELERATION PREMIUMS | Cold weather heating — LP heaters | day | 450 | 850 | Propane salamander or torpedo heater
DELAY / ACCELERATION PREMIUMS | Cold weather enclosure — concrete pour | m2 enclosed | 8 | 18 | Poly tarp + frame + heat; per pour area
DELAY / ACCELERATION PREMIUMS | Winter freeze protection — earthworks | m3 thaw | 3.5 | 8.5 | Steam or ground thaw blankets
OWNER-CAUSED DELAY
OWNER-CAUSED DELAY | Equipment demob + remob — per event | event | 15000 | 65000 | Equipment size dependent
OWNER-CAUSED DELAY | Extended project overhead — per week | week | 12000 | 35000 | All site OH: trailer, IT, vehicles, staff
OWNER-CAUSED DELAY | Material restocking / escalation impact | % of mat. | 2% | 8% | If materials ordered and delay >3 months

## 14 SME Factors
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SME ESTIMATING FACTORS — CANADA 2026 — SOURCE: Rev E SME Factors tab
Category | Factor / Item | Low | High | SME Notes / Basis
INDIRECT / GC MARKUPS
INDIRECT / GC MARKUPS | Mob/demob — major earthwork fleet (% of equip) | 2% | 5% | Or flat LS per fleet assembly
INDIRECT / GC MARKUPS | Mob/demob — rough terrain crane RT 60T | $4,000 | $8,000 | Flat rate per mob
INDIRECT / GC MARKUPS | Mob/demob — crawler crane 150T | $25,000 | $55,000 | Incl. partial disassembly
INDIRECT / GC MARKUPS | Camp/LOA markup on direct labour | 8% | 12% | Add for remote sites
INDIRECT / GC MARKUPS | Small tools and consumables on direct labour | 2.5% | 4% | Blades, hoses, bits, PPE consumables
INDIRECT / GC MARKUPS | Supervision markup on direct labour | 8% | 12% | Foreman + superintendent ratio
INDIRECT / GC MARKUPS | Contractor distributable (CDI) on direct cost | 6% | 10% | Temp facilities, insurance, site admin
DESIGN GROWTH — AACE 18R-97
DESIGN GROWTH — AACE 18R-97 | Class 4 study (screening/feasibility prep) | 15% | 20% | Limited geotech; prelim drawings
DESIGN GROWTH — AACE 18R-97 | Class 3 budget (feasibility study) | 10% | 15% | THIS DOCUMENT standard level
DESIGN GROWTH — AACE 18R-97 | Class 2 sanction / AFE (pre-FID) | 5% | 10% | Good definition; IFC packages near complete
DESIGN GROWTH — AACE 18R-97 | Class 1 check / tender (detailed design) | 2% | 5% | Full detailed design completed
DESIGN GROWTH — AACE 18R-97 | Concrete works — add to above | +5% | +5% | Add 5% incremental to earthworks DG
WASTAGE FACTORS
WASTAGE FACTORS | Granular aggregate — over-order allowance | 5% | 10% | Rounding + delivery variance
WASTAGE FACTORS | Concrete — over-pour allowance | 8% | 12% | Formed concrete; pump waste + edge loss
WASTAGE FACTORS | Rebar — cutting waste | 3% | 7% | Depends on bar size and cutting complexity
WASTAGE FACTORS | Geomembrane liner — overlap + waste | 5% | 10% | Panel overlaps + anchor trench + QA sampling
WASTAGE FACTORS | Geotextile — overlap + waste | 10% | 15% | 6-inch overlaps min per ASTM D4439
REGIONAL ADJUSTMENTS — CANADA 2026
REGIONAL ADJUSTMENTS — CANADA 2026 | Ontario (Greater Toronto / Ottawa) | 1.05 | 1.15 | Labour + material premium
REGIONAL ADJUSTMENTS — CANADA 2026 | Ontario (Northern — Thunder Bay / Sudbury) | 1.02 | 1.10 | Remote factor; fly-in camp adds $50-80/mhday
REGIONAL ADJUSTMENTS — CANADA 2026 | Quebec (Montreal) | 1.03 | 1.12 | Union density; CCQ wage rates
REGIONAL ADJUSTMENTS — CANADA 2026 | Quebec (Northern — Chibougamau / James Bay) | 1.08 | 1.22 | Remote + northern premium
REGIONAL ADJUSTMENTS — CANADA 2026 | Manitoba / Saskatchewan | 1.00 | 1.08 | Moderate; open-shop market available
REGIONAL ADJUSTMENTS — CANADA 2026 | Alberta (Edmonton / Calgary) | 1.05 | 1.18 | Boom/bust volatility; CLAC + union mix
REGIONAL ADJUSTMENTS — CANADA 2026 | Alberta (Oil Sands / Fort McMurray) | 1.15 | 1.35 | Boom market premium; remote camp intensity
REGIONAL ADJUSTMENTS — CANADA 2026 | British Columbia (Metro Vancouver) | 1.10 | 1.20 | Labour premium; IBEW/UA rates higher
REGIONAL ADJUSTMENTS — CANADA 2026 | British Columbia (Interior / Northern) | 1.15 | 1.30 | Remote + northern premium; winter factor
REGIONAL ADJUSTMENTS — CANADA 2026 | Yukon / NWT / Nunavut | 1.30 | 1.55 | Extreme remote; fly-in; northern allowances
REGIONAL ADJUSTMENTS — CANADA 2026 | Winter construction premium — all Canada | 10% | 25% | Heating, snow clearing, reduced productivity
ESCALATION — CANADA 2026
ESCALATION — CANADA 2026 | Go-by Q2-2020 to Q2-2026 applied factor | x1.23 | x1.27 | BCPI cumulative; use x1.25 midpoint
ESCALATION — CANADA 2026 | Labour CBA escalation 2024-2026 NL trades | 3.5% | 5.5% | Per trade; see Sheet 05
ESCALATION — CANADA 2026 | Diesel — NS May 2026 (NRCan) | $2.13/L | $2.21/L | NS Energy Regulatory Board
ESCALATION — CANADA 2026 | Diesel — AB May 2026 (NRCan) | $1.68/L | $1.78/L | Lower tax base
ESCALATION — CANADA 2026 | Diesel — BC Metro May 2026 (NRCan) | $2.15/L | $2.35/L | Carbon levy + higher base
ESCALATION — CANADA 2026 | USD/CAD exchange rate May 2026 | 1.36 | 1.37 | Bank of Canada
ESCALATION — CANADA 2026 | CBSA surtax — Chinese structural steel (25%) | 25% | 25% | CBSA Notices 24-26/25-22
ESCALATION — CANADA 2026 | CBSA surtax — Chinese rebar (25%) | 25% | 25% | Verify current supplier origin cert.
ACCURACY RANGES — AACE 18R-97
ACCURACY RANGES — AACE 18R-97 | Class 4 study | -30% | +50% | Screening/feasibility
ACCURACY RANGES — AACE 18R-97 | Class 3 budget / feasibility | -20% | +30% | THIS DOCUMENT — standard benchmark
ACCURACY RANGES — AACE 18R-97 | Class 2 sanction / AFE | -10% | +20% | Pre-FID; good definition
ACCURACY RANGES — AACE 18R-97 | Class 1 check / tender | -5% | +10% | Full detailed design completed

## 15 Bid Cost Structure
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID COST STRUCTURE — 6-LAYER CONTRACTOR MARKUP MODEL — SOURCE: Rev G Bid Summary tab
Layer | Bid Cost Element | Basis / Method | Typical Low | Typical High | % of Direct | SME Notes
1 — DIRECT FIELD COSTS
1 — DIRECT FIELD COSTS | 1.1 Earthworks & Mass Excavation | Unit rates × MTO quantities | — | — | 20-40% | Largest single direct line for most mining civil
1 — DIRECT FIELD COSTS | 1.2 SWM, ESC & Water Management | Unit rates × MTO quantities | — | — | 5-10%
1 — DIRECT FIELD COSTS | 1.3 Roads, Pads & Working Surfaces | Unit rates × MTO quantities | — | — | 8-15%
1 — DIRECT FIELD COSTS | 1.4 WRSA / TMF Embankment | Unit rates × MTO quantities | — | — | 10-20% | Dam Safety requirements additive
1 — DIRECT FIELD COSTS | 1.5 Drainage, Culverts & Piping | Unit rates × MTO quantities | — | — | 5-10% | Long lead items; confirm supply
1 — DIRECT FIELD COSTS | 1.6 Concrete — Civil | Unit rates × MTO quantities | — | — | 5-12%
1 — DIRECT FIELD COSTS | 1.7 Structural Steel & Building Enclosure | Unit rates × MTO quantities | — | — | 3-8% | CBSA tariff risk — Chinese origin
1 — DIRECT FIELD COSTS | 1.8 Geosynthetics & Liner Systems | Unit rates × MTO quantities | — | — | 3-8% | Specialist sub; include CQA
1 — DIRECT FIELD COSTS | 1.9 Blasting (drill+charge+blast+clear) | Unit rates × MTO quantities | — | — | 2-5% | Licensed sub or self-perform
1 — DIRECT FIELD COSTS | 1.10 Buried Services | Unit rates × MTO quantities | — | — | 2-5%
1 — DIRECT FIELD COSTS | 1.11 Fencing, Security & Wildlife | Unit rates × MTO quantities | — | — | 1-2% | Required all Canadian mine sites
1 — DIRECT FIELD COSTS | 1.12 Permanent Dewatering Systems | Unit rates × MTO quantities | — | — | 1-3%
1 — DIRECT FIELD COSTS | 1.13 Closure & Reclamation | Unit rates × MTO quantities | — | — | 2-5% | If in scope
1 — DIRECT FIELD COSTS | SUBTOTAL — DIRECT FIELD COSTS | Sum above | — | — | 100% | Basis for all markup calculations
2 — CONTRACTOR FIELD INDIRECTS (CDI)
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.1 Site establishment / mobilization | Project LS | 1% | 3% | 1-3% | Per Sheet 16 mob/demob logic; remote/fly-in higher
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.2 Temp facilities (offices, lunchrooms) | LS allowance | 0.5% | 1.5% | 0.5-1.5%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.3 Field supervision | 8-12% of direct labour | 8% | 12% | 8-12% of lab | PM, QC, safety officer
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.4 Small tools and consumables | 2.5-4% of direct labour | 2.5% | 4.0% | 2.5-4%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.5 Quality control and testing | 0.5-1.5% of direct | 0.5% | 1.5% | 0.5-1.5% | Nuclear density, concrete cyl, geotech
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.6 Environmental compliance (SWPPP) | 0.3-0.8% of direct | 0.3% | 0.8% | 0.3-0.8% | Monitoring, spill kits, inspection
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.7 Demobilization and site cleanup | 0.5-1.5% | 0.5% | 1.5% | 0.5-1.5%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.8 Camp setup and operating costs | See Sheet 11 | — | — | Project-specific | Separate line — not in labour rate
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.9 Pre-blast surveys | $3,500-$8,500/struct | $3,500 | $8,500 | LS | Required before blasting near structures
2 — CONTRACTOR FIELD INDIRECTS (CDI) | CDI SUBTOTAL | Typically 12-18% of direct | 12% | 18% | 12-18%
3 — COMPANY OVERHEAD
3 — COMPANY OVERHEAD | 3.1 Head office overhead allocation | % of contract value | 3% | 6% | 3-6% | Allocated executive, accounting, legal, IT, facility
3 — COMPANY OVERHEAD | 3.2 Bid and proposal costs | 0.5-1.5% | 0.5% | 1.5% | 0.5-1.5%
3 — COMPANY OVERHEAD | 3.3 Warranty allowance — 12 month | 0.5-1.0% of contract | 0.5% | 1.0% | 0.5-1%
3 — COMPANY OVERHEAD | OVERHEAD SUBTOTAL | Typically 6-12% of direct | 6% | 12% | 6-12%
4 — BONDING & INSURANCE
4 — BONDING & INSURANCE | 4.2 Performance bond | 0.5-1.5% of contract | 0.5% | 1.5% | 0.5-1.5% | CCDC 2 standard requirement
4 — BONDING & INSURANCE | 4.3 Labour & Material Payment bond | 0.5-1.0% of contract | 0.5% | 1.0% | 0.5-1% | Required CCDC 2
4 — BONDING & INSURANCE | 4.4 General liability insurance | $5-$8 per $1,000 payroll | $5 | $8 | / $1K payroll
4 — BONDING & INSURANCE | 4.5 Workers Compensation — labourers | $4.50-$6.00 per $100 | $4.50 | $6.00 | / $100 payroll
4 — BONDING & INSURANCE | 4.6 Builder's Risk / Course of Const. | 0.15-0.35% of contract | 0.15% | 0.35% | 0.15-0.35%
4 — BONDING & INSURANCE | BONDING & INSURANCE SUBTOTAL | Typically 2-4% of contract | 2% | 4% | 2-4%
5 — CONTINGENCY & RISK
5 — CONTINGENCY & RISK | 5.1 Quantity / scope risk (MTO uncertainty) | % of direct | 2% | 5% | 2-5% | Design growth from MTO variance; per AACE class
5 — CONTINGENCY & RISK | 5.2 Ground conditions / geotech risk | 3-8% of earthworks direct | 3% | 8% | 3-8% of earth | Unforeseen rock, contamination, groundwater
5 — CONTINGENCY & RISK | 5.3 Weather / schedule risk | 2-5% of total | 2% | 5% | 2-5% | Productivity loss; winter and spring
5 — CONTINGENCY & RISK | 5.4 Escalation / commodity price risk | 3-8% of materials | 3% | 8% | 3-8% of mat. | Diesel, aggregate, steel — long contracts
5 — CONTINGENCY & RISK | 5.5 Subcontractor default risk | 1-3% of sub spend | 1% | 3% | 1-3% of sub $
5 — CONTINGENCY & RISK | CONTINGENCY SUBTOTAL | Typically 8-15% of direct | 8% | 15% | 8-15%
6 — CONTRACTOR PROFIT
6 — CONTRACTOR PROFIT | 6.1 Profit — open competitive market | 5-10% of all costs | 5% | 10% | 5-10% | Standard market-rate bid; multiple bidders
6 — CONTRACTOR PROFIT | 6.2 Profit — sole source / preferred | 8-12% of all costs | 8% | 12% | 8-12% | Pre-qualified or sole-source scenario
6 — CONTRACTOR PROFIT | 6.3 Profit — high risk / remote | 10-15% of all costs | 10% | 15% | 10-15% | Northern, fly-in, first-time client
6 — CONTRACTOR PROFIT | TOTAL BID = Direct + CDI + OH + B/I + Contingency + Profit | Bottom-up; sense-check $/m3 or $/m2 | — | — | — | Cross-check with Sheet 10 floors/ceilings

## 16 Mob Demob Logic
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
MOBILIZATION & DEMOBILIZATION LOGIC — CANADA 2026 — SOURCE: Rev E SME Factors + standard practice
Category | Asset / Activity | Basis | Low (CAD) | High (CAD) | SME Notes
EARTHWORK FLEET
EARTHWORK FLEET | Major earthwork fleet mob/demob | % of total equip value | 2% | 5% | Or flat LS per fleet; round-trip
EARTHWORK FLEET | Heavy haul move per low-bed trip | Per round-trip | $1,800 | $3,500 | Within 300 km radius
EARTHWORK FLEET | Off-road haul truck (40-100T) move | Per unit / round-trip | $8,000 | $18,000 | May require permit, escort
CRANES
CRANES | Rough terrain crane RT 60T | Flat per mob | $4,000 | $8,000 | Single-truck low-bed
CRANES | Lattice boom crawler 150T | Flat per mob (incl. disassembly) | $25,000 | $55,000 | Partial disassembly; 5-10 trailer loads
CAMPS
CAMPS | Camp setup — fly-in remote (40-bed) | LS | $250,000 | $500,000 | Mob crew + freight + assembly
CAMPS | Camp setup — drive-in (40-bed) | LS | $120,000 | $220,000
SITE TEMP FACILITIES
SITE TEMP FACILITIES | Trailer offices + lunchrooms + IT | LS | $35,000 | $85,000 | From Sheet 11
SPECIALTY SUBS
SPECIALTY SUBS | HDPE liner sub (incl. CQA crew) | LS | $25,000 | $60,000 | Specialty equipment + technicians
SPECIALTY SUBS | Blasting sub (drill + powder magazine) | LS | $35,000 | $90,000 | Includes permit fees, magazine, powder
SPECIALTY SUBS | Aggregate crushing plant | LS | $150,000 | $400,000 | Move, set, commission
INSURANCE / WCB REG
INSURANCE / WCB REG | Provincial registration + WCB account | LS | $5,000 | $15,000 | Multi-province jobs
Mob/demob is typically priced as a separate LS line — not absorbed in unit rates. For remote/fly-in sites add freight allowance. For multi-phase work, charge re-mob per phase. Confirm haul permit and escort costs for over-dimensional moves in NS/NB/QC/ON/MB. Sheet 13 (Standby & Schedule) handles owner-caused remob.

## 17 Constructability
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTABILITY & EXECUTION ASSUMPTIONS [TEMPLATE — populate per project]
Category | Assumption / Decision | Project-Specific Notes
WORK CALENDAR
WORK CALENDAR | Site works 10-hr shift, 14-on / 7-off (FIFO) OR 4-on / 3-off (drive-in) | <populate>
WORK CALENDAR | Effective hours per shift after breaks & travel: 8.5-9.0 productive hr | <populate>
WORK CALENDAR | Winter weather window (no work): Nov-Mar productivity factor 0.70-0.85 | <populate>
WORK CALENDAR | Spring break-up moratorium (haul road restrictions): early Apr to mid-May | <populate>
ACCESS & LOGISTICS
ACCESS & LOGISTICS | Primary access road condition (paved / gravel / seasonal) and weight rating | <populate>
ACCESS & LOGISTICS | Fly-in vs drive-in — confirm chartered air freight cost & frequency | <populate>
ACCESS & LOGISTICS | Material laydown sufficient for 60-90 days inventory at site | <populate>
ACCESS & LOGISTICS | Fuel resupply schedule — confirm tanker turnaround & on-site storage capacity | <populate>
SEQUENCING
SEQUENCING | Earthworks completion before liner install (no traffic post-liner) | <populate>
SEQUENCING | Concrete cure times: 7 days form-strip; 28 days full strength; cold weather double | <populate>
SEQUENCING | Steel erection cannot proceed until anchor bolts surveyed and accepted | <populate>
SEQUENCING | Culvert installs during low-flow window per provincial fisheries authorization | <populate>
GEOTECHNICAL
GEOTECHNICAL | Bedrock encountered at depth X m — drill+blast assumption from elevation Y | <populate>
GEOTECHNICAL | Water table at depth X m — dewatering required for excavations deeper than Y m | <populate>
GEOTECHNICAL | Acid-generating waste rock requires segregation and encapsulation (geomembrane base) | <populate>
ENVIRONMENTAL
ENVIRONMENTAL | Fish habitat compensation work in Year 1 — site-specific permits required | <populate>
ENVIRONMENTAL | SWPPP / ESCP plan controlling discharge to receiving water; weekly inspection minimum | <populate>
ENVIRONMENTAL | Wildlife protocol (bear/caribou/grizzly) — daily site clearance | <populate>
CONSTRUCTION METHODS
CONSTRUCTION METHODS | Roll-on / roll-off compaction at 95% Std Proctor; 98% for process pads | <populate>
CONSTRUCTION METHODS | Concrete supplied from on-site batch plant (if vol >2,000 m3) else ready-mix from <X> km | <populate>
CONSTRUCTION METHODS | Aggregate supplied from on-site quarry/crusher (if vol >50,000 t) else from <X> km | <populate>
CONSTRUCTION METHODS | Blasting confined per pattern; pre-blast survey for structures within 500m radius | <populate>
INTERFACE
INTERFACE | Owner-supplied items: <list> (e.g. process plant equipment) | <populate>
INTERFACE | Existing facility tie-ins coordinated during scheduled outage windows | <populate>
LABOUR / IR
LABOUR / IR | Open shop / CLAC / Building Trades — confirm market and CBA obligations | <populate>
LABOUR / IR | Indigenous community engagement commitment — % local hire / IBA obligations | <populate>
HSE
HSE | Site induction 4 hr per worker; site-specific safety standards apply | <populate>
HSE | Fire watch protocol for hot work; permit-to-work system in operation | <populate>
HSE | Critical lifts > 75% chart capacity require lift plan + engineer approval | <populate>
PRODUCTIVITY
PRODUCTIVITY | Apply 0.85-0.95 productivity factor for first 4 weeks of project (learning curve) | <populate>
PRODUCTIVITY | Confined working areas: derate output by 10-30% depending on access | <populate>
QUALITY
QUALITY | All concrete pours: nuclear density + 4-cyl set per pour (Sheet 11) | <populate>
QUALITY | All HDPE liner seams: 100% non-destructive (spark / vacuum) + destructive sample 1/150m | <populate>

## 18 Inclusions Exclusions
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SCOPE INCLUSIONS, EXCLUSIONS & CLARIFICATIONS REGISTER [TEMPLATE — populate per bid]
Discipline | Item | Status (Incl. / Excl. / Clar.) | Description / Reference
EARTHWORKS
EARTHWORKS | Mass excavation common soil | INCLUDED | Per Sheet 08 C-10-002; balanced cut/fill assumed
EARTHWORKS | Rock excavation including drill & blast | INCLUDED | Per Sheet 08 C-10-007 + B-01-003
EARTHWORKS | Removal of contaminated soil | EXCLUDED | Owner responsibility; treated separately
EARTHWORKS | Temporary site dewatering | CLARIFY | Included only where shown on dewatering plan
WATER MGMT
WATER MGMT | Permanent stormwater pond construction | INCLUDED | Per pond MTO
WATER MGMT | Operating sediment treatment chemicals | EXCLUDED | Owner-supplied per operating procedure
ROADS
ROADS | Haul road sub-base + surface course | INCLUDED | Per Sheet 08 C-30-002/3/4
ROADS | Permanent asphalt paving | CLARIFY | Included only on access road; not on haul roads
WRSA/TMF
WRSA/TMF | TMF embankment construction Zones A, B, C | INCLUDED | Per Sheet 08 C-40-002/3
WRSA/TMF | HDPE 2mm liner with CQA | INCLUDED | Per Sheet 08 C-40-004; specialty sub
WRSA/TMF | Dam Safety Officer (DSO) services | EXCLUDED | Owner's appointed DSO; we provide construction records
DRAINAGE
DRAINAGE | CSP culverts up to 1200mm diameter | INCLUDED | Per culvert schedule
DRAINAGE | Precast box / arch culverts > 1500mm | CLARIFY | Included only if drawing shows; supply long-lead
CONCRETE
CONCRETE | Cast-in-place foundations, walls, footings | INCLUDED | Per concrete MTO; ready-mix from <X> km plant
CONCRETE | Precast concrete (process plant) | EXCLUDED | Owner-supplied for plant scope
STEEL
STEEL | Structural steel building enclosures + equipment platforms | INCLUDED | Per steel MTO; supplier TBD
STEEL | Process plant structural steel | EXCLUDED | Owner / mechanical contractor scope
GEOSYNTHETICS
GEOSYNTHETICS | HDPE liner systems (TMF, ponds, closure cap) | INCLUDED | Includes installation + CQA
GEOSYNTHETICS | Geomembrane CQA Engineer of Record | EXCLUDED | Owner-appointed independent
BLASTING
BLASTING | Drill, blast, clear of rock excavation | INCLUDED | Self-perform or licensed sub
BLASTING | Pre-blast condition surveys of nearby structures | INCLUDED | Sheet 11; >500m radius scope
BURIED SVCS
BURIED SVCS | Site potable water, sewer, process water mains | INCLUDED | Per Sheet 08 K series
BURIED SVCS | Electrical / instrumentation underground | EXCLUDED | Per electrical contractor scope
FENCING
FENCING | Site perimeter chain link + wildlife exclusion | INCLUDED | Per Sheet 08 M series
FENCING | Process plant area security fencing | EXCLUDED | By process contractor
CLOSURE
CLOSURE | Final cover system + topsoil + seeding | INCLUDED | Per Sheet 08 H series; one-time cap
CLOSURE | Long-term water treatment infrastructure | EXCLUDED | Owner's operating responsibility
INDIRECTS
INDIRECTS | Site offices, lunchrooms, dryrooms | INCLUDED | Per Sheet 11
INDIRECTS | Camp accommodation (incl. food) | CLARIFY | Included only if remote; sheet 05 O2
INDIRECTS | Owner inspection / EPCM offices on site | EXCLUDED | By owner / EPCM
PERMITS
PERMITS | Routine construction permits (excavation, hot work) | INCLUDED | Standard practice
PERMITS | Environmental authorization (EA, water license) | EXCLUDED | Owner responsibility
PERMITS | Provincial blasting permits, magazine licenses | INCLUDED | Sub responsibility for blasting
WARRANTY
WARRANTY | 12-month material + workmanship warranty | INCLUDED | Standard CCDC 2
WARRANTY | Extended warranty beyond 12 months | EXCLUDED | By negotiation
EXCLUSIONS
EXCLUSIONS | Owner-furnished materials of any kind | EXCLUDED | Receive, store and install only if priced separately
EXCLUSIONS | Force majeure or unknown ground conditions | EXCLUDED | Per CCDC general conditions

## 19 Bid Leveling
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID LEVELING — TENDER COMPARISON [TEMPLATE — enter bidder pricing in blue cells]
WBS Ref | Item Description | UOM | Quantity | Bidder A ($/unit) | Bidder B ($/unit) | Bidder C ($/unit) | SME Benchmark ($/unit)
C-10-003 | Backfill common — spread and compact | m3 | <qty> | <enter $> | <enter $> | <enter $> | 25
C-10-007 | Rock excavation — blasted and loaded | m3 | <qty> | <enter $> | <enter $> | <enter $> | 48
C-30-002 | Haul road — sub-grade preparation | m2 | <qty> | <enter $> | <enter $> | <enter $> | 18
C-30-005 | Asphalt paving 50mm HL3 | m2 | <qty> | <enter $> | <enter $> | <enter $> | 54
C-40-002 | TMF embankment Zone A/B | m3 | <qty> | <enter $> | <enter $> | <enter $> | 27
C-40-004 | HDPE 2mm liner with CQA | m2 | <qty> | <enter $> | <enter $> | <enter $> | 39
C-50-005 | CSP culvert 1200mm | m | <qty> | <enter $> | <enter $> | <enter $> | 1250
C-60-002 | Concrete wall / grade beam | m3 | <qty> | <enter $> | <enter $> | <enter $> | 2850
C-60-006 | Rebar Grade 400 | tonne | <qty> | <enter $> | <enter $> | <enter $> | 5000
B-01-003 | Rock blasting all-in | m3 | <qty> | <enter $> | <enter $> | <enter $> | 65
B-05-003 | Wildlife exclusion fence 2.4m elec. | m | <qty> | <enter $> | <enter $> | <enter $> | 213
B-08-002 | Precast box culvert 2400x1800mm | m | <qty> | <enter $> | <enter $> | <enter $> | 8500
[TEMPLATE] Convert bidder Forms of Tender into common UOM and apply: Variance vs SME benchmark (%) = (Bidder $/unit − Benchmark $/unit) / Benchmark $/unit. Flag any item more than ±20% from benchmark for clarification. Use Sheet 10 floors/ceilings for hard out-of-range flags. Append clarifications and exclusions from each bidder to a deviation log.

## 20 Change Order Pricing
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CHANGE ORDER PRICING METHODOLOGIES — CCDC-STYLE [TEMPLATE]
Method | When to Use | Build-Up Formula | Markup Low | Markup High | SME Notes
Unit-rate based | Quantum is well-defined and existing unit rate covers the work scope | Qty × existing unit rate × (1 + design growth) | 0% | 5% | Preferred where unit rates exist (Sheet 08)
Time & Materials (T&M) | Scope is uncertain and / or schedule-critical; no firm quantum | Crew hr × crew $/hr + Equip hr × equip $/hr + Mat × (1+wastage) + Sub × (1+markup) + OH% | 10% | 15% | Daily LEM log signed by owner rep
Lump-sum quotation | Discrete, well-defined work that can be quoted firm | Direct (build up per Sheet 09) + Indirect (10-15%) + OH+P (10-20%) | 15% | 25% | Submit detailed breakdown; client accepts LS
Negotiated rates | Recurring change category (e.g. additional culvert sizes) | Pre-agreed rate schedule × Qty | 5% | 10% | Capture in change order schedule
Force account | Disputed scope; owner directs work pending resolution | T&M as above + auditable records + retention of receipts | 10% | 15% | Subject to subsequent audit
CHANGE ORDER STANDARD MARKUP STACK (per CCDC 2 GC 6.2.4)
Layer | Element | % of Direct | Apply To | Notes
1 | Direct labour + equip + material | 100% | Cost of work | Build up per Sheet 09
2 | Contractor field overhead | 8-12% | Direct labour | If work managed by existing PM team — lower
3 | Head office overhead | 5-10% | Total direct + CFO | Bid-stage % less if scope handled by existing OH
4 | Contractor profit / fee | 8-15% | Total direct + OH | Project complexity / risk
5 | Bond + insurance adjustment | 1.5-3% | Total contract increase | Only if change increases bonded contract value
6 | Sub-tier markup (if subbed) | 5-10% | Sub price | On flow-through subs only
[TEMPLATE] Methodology selection should be agreed with Contract Administrator at project start. Daily T&M sheets must be co-signed within 48 hours. Lump-sum change quotations to include itemised buildup of LEMSC + indirect + OH+P. Time impact analysis required if change affects critical path (CCDC 2 GC 6.5).

## 21 Project Roll-Up
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
PROJECT ESTIMATE ROLL-UP [TEMPLATE — enter values in blue cells; green cells calculated]
Layer | Item | Amount (CAD) | Notes / Reference
1 — DIRECT FIELD COSTS
1.1 | Earthworks & mass excavation | 0 | From Sheet 08 section A; Σ Qty × Rate
1.2 | SWM, ESC & water management | 0 | From Sheet 08 section B
1.3 | Roads, pads & working surfaces | 0 | From Sheet 08 section C
1.4 | WRSA / TMF embankment | 0 | From Sheet 08 section D
1.5 | Drainage, culverts & piping | 0 | From Sheet 08 section E
1.6 | Concrete — civil | 0 | From Sheet 08 section F
1.7 | Structural steel & enclosure | 0 | From Sheet 08 section G
1.8 | Geosynthetics & liners | 0 | From Sheet 08 section D liner items
1.9 | Blasting (all-in) | 0 | From Sheet 08 section I
1.10 | Buried services | 0 | From Sheet 08 section K
1.11 | Fencing, security & wildlife | 0 | From Sheet 08 section M
1.12 | Permanent dewatering | 0 | From Sheet 08 section J
1.13 | Closure & reclamation | 0 | From Sheet 08 section H
| SUBTOTAL DIRECT | 0
2 — CONTRACTOR FIELD INDIRECTS (CDI)
2.1 | CDI % of direct (input) | 0.15 | Typical 12-18% Sheet 11/15
| CDI AMOUNT | 0 | = Direct × CDI %
3 — COMPANY OVERHEAD
3.1 | Company OH % of direct (input) | 0.08 | Typical 6-12% Sheet 15
| COMPANY OH AMOUNT | 0 | = Direct × OH %
4 — BONDING & INSURANCE
4.1 | Bond + Insurance % of contract (input) | 0.03 | Typical 2-4% Sheet 12/15
| BOND + INSURANCE AMOUNT | 0 | = (Direct + CDI + OH) × B+I %
5 — CONTINGENCY & RISK
5.1 | Contingency % of direct (input) | 0.12 | Typical 8-15% Sheet 15
| CONTINGENCY AMOUNT | 0 | = Direct × Contingency %
6 — CONTRACTOR PROFIT
6.1 | Profit % of all costs (input) | 0.1 | Typical 8-15% Sheet 15
| PROFIT AMOUNT | 0 | = (Direct + CDI + OH + B+I + Cont.) × Profit %
TOTAL BID (CAD) |  | 0 | Cross-check $/m3 or $/m2 against Sheet 10
[TEMPLATE] Populate Direct lines from MTO × unit rates (Sheet 08). Adjust % markups within the bands shown in Sheet 15. For Class 3 baseline use mid-range %. Apply regional adjustor (Sheet 14) to direct cost lines before summing if site is outside MB/SK baseline.

## 22 Risk Register
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
RISK & CONTINGENCY REGISTER [TEMPLATE — populate per project]
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Cost Impact (CAD) | Schedule Impact (wk) | Mitigation / Allocation
R-01 | Geotechnical | Unforeseen rock below estimated quantity | 4 | 4 | 750000 | 4 | Apply 3-8% earthworks contingency; rate adjustment per CCDC GC 6.4
R-02 | Geotechnical | Acid-generating waste rock encountered | 3 | 5 | 1200000 | 6 | Owner-led environmental management; allow 1-3% allowance
R-03 | Weather | Extended winter shutdown / spring break-up beyond plan | 4 | 3 | 350000 | 3 | Apply 2-5% weather contingency; review work calendar
R-04 | Market / Escalation | Diesel price >15% above bid basis over project life | 3 | 3 | 280000 | 0 | Apply 3-8% materials escalation; index fuel surcharge
R-05 | Market / Tariff | CBSA 25% surtax on Chinese steel/rebar extended | 3 | 3 | 420000 | 0 | Source Canadian/US; allow 5-10% on steel
R-06 | Subcontractor | Specialty sub (liner / blasting) default or delay | 2 | 4 | 600000 | 4 | Apply 1-3% sub default contingency; pre-qualify alts
R-07 | Permits | Environmental permit delay for fish habitat work | 3 | 4 | 400000 | 6 | Phase work; engage authority early
R-08 | Labour | Skilled trades shortage — Electrician / Welder | 4 | 3 | 250000 | 4 | Lock supply via early subcontracts; carry 5% labour premium
R-09 | Indigenous | IBA / community engagement delay | 3 | 4 | 350000 | 6 | Engage early; capture commitment in schedule
R-10 | Owner | Owner-supplied materials late | 3 | 4 | 500000 | 6 | Daily T&M / standby for owner-caused delay (Sheet 13)
R-11 | Quality / Rework | HDPE liner CQA failures requiring re-weld / re-install | 2 | 3 | 180000 | 2 | Pre-qualify installer; require third-party CQA
R-12 | HSE | Major incident causing site stop-work | 1 | 5 | 1500000 | 8 | Strong safety culture; carry incident allowance per insurer
[TEMPLATE] Likelihood × Impact = risk score. Items scoring ≥12 require explicit cost allocation. Total cost-weighted exposure (Σ Likelihood × Cost / 5) drives recommended contingency carry. Cross-reference Sheet 15 Layer 5 (Contingency & Risk) allocations.

## 23 Glossary
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
GLOSSARY, ABBREVIATIONS & UNITS OF MEASURE
Term / Abbreviation | Definition
AACE | Association for the Advancement of Cost Engineering International
AACE 18R-97 | Cost Estimate Classification System — process industries (5-class system used here for mining heavy civil)
AFE | Authorization for Expenditure — owner approval at sanction (typically Class 2)
BCPI | Building Construction Price Index (Statistics Canada) — used for escalation
CAD | Canadian Dollar
CBSA | Canada Border Services Agency — administers steel/rebar surtax
CDI | Contractor Distributable Indirects — site indirects allocated across project (offices, supervision, etc.)
CGL | Commercial General Liability insurance
CLAC | Christian Labour Association of Canada — open shop / alternate to Building Trades
CCDC | Canadian Construction Documents Committee — standard forms (CCDC 2 = stipulated sum)
CMS | Construction Management Standard
CQA | Construction Quality Assurance (typically third-party)
DRYROOM | Heated change facility for clothing / gear storage
DR-11 / DR-17 | HDPE pipe Dimension Ratio (wall thickness class)
EHT | Employer Health Tax (Ontario / BC)
EPCM | Engineering, Procurement and Construction Management
ESC | Erosion & Sediment Control
FID | Final Investment Decision
FIFO | Fly-in / Fly-out (typically 14-on / 7-off rotation)
HDPE | High-Density Polyethylene
HSE | Health, Safety, Environment
IBA | Impact Benefit Agreement (Indigenous communities)
IFC | Issued For Construction (drawing status)
LOA | Living Out Allowance (per-diem) for non-camp remote work
MTO | Material Take-Off (quantity survey from drawings)
NCSO | National Construction Safety Officer (Canadian certification)
NRCan | Natural Resources Canada (publishes diesel + commodity pricing)
ROM | Rough Order of Magnitude (Class 5/4 estimate)
SoR | Schedule of Rates
SWM | Stormwater Management
SWPPP | Stormwater Pollution Prevention Plan
TMF | Tailings Management Facility
WBS | Work Breakdown Structure
WCB / WSIB | Workers' Compensation Board / Ontario Workplace Safety & Insurance Board
WRSA | Waste Rock Storage Area
Std Proctor | Standard Proctor density (ASTM D698)
Crew code Bx/Cx | SME crew classifications (see Sheet 04)
Unit MH | Unit Man-Hours per UOM (productivity input)
UOM | Unit of Measure (m, m2, m3, tonne, ea, LS)
LS | Lump Sum
S+I | Supply + Install
S+F+P | Supply + Form + Pour
Std / SoR floor | Lower benchmark in Sheet 10 below which bid is suspect
Std / SoR ceiling | Upper benchmark in Sheet 10 above which bid is suspect

## 24 References
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SOURCES, REFERENCES & DATA PROVENANCE
Category | Reference | Use in Manual
STANDARDS
STANDARDS | AACE International Recommended Practice 18R-97 — Cost Estimate Classification System | Sheet 03 — Class 5 through Class 1 framework
STANDARDS | ASTM D698 — Standard Proctor; ASTM D1557 — Modified Proctor | Sheet 17 — earthworks compaction acceptance
STANDARDS | ASTM D4439 — Geosynthetics terminology | Sheet 03 / 08 — geotextile overlap allowances
STANDARDS | CCDC 2 — Stipulated Sum Contract (Canadian Construction Documents Committee) | Sheets 12, 18, 20 — bond, warranty, change order provisions
STANDARDS | Canadian Dam Association Dam Safety Guidelines | Sheet 08 section D — TMF embankment construction
INDICES
INDICES | Statistics Canada — Building Construction Price Index (BCPI), quarterly | Sheet 03 / 14 — Q2-2020 → Q2-2026 x1.25 escalation
INDICES | Natural Resources Canada (NRCan) — Diesel Pricing, weekly | Sheet 03 — diesel price by region
INDICES | Bank of Canada — USD/CAD exchange rate | Sheet 03 / 14 — currency basis
AUTHORITIES
AUTHORITIES | Canada Border Services Agency — Notices 24-26 and 25-22 (steel / rebar surtax) | Sheet 03 / 14 — 25% surtax on Chinese-origin material
AUTHORITIES | Provincial WCB / WSIB / CNESST / WorkSafeBC / WorkplaceNL — premium rate tables | Sheet 12 — WCB by province
AUTHORITIES | Nova Scotia Energy Regulatory Board — Atlantic diesel price | Sheet 03 / 14 — Atlantic diesel
INTERNAL
INTERNAL | Rev G workbook — RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 (Contractor Bid Tool) | Source: Bid Summary, Missing Unit Rates, Bonding & Ins., Overhead, Standby, Bid Screening
INTERNAL | Rev E workbook — RMM-CIVIL-CANADA-2026-REV0 (EPCM Benchmark Estimator) | Source: Crew, Labour, Equipment Rates, Heavy Civil Unit Rates, SME Factors
INTERNAL | Ausenco go-by Q2-2020 (Senior PD / EPCM reference) | Sheet 04 — crew rate baseline pre-escalation
SUPPLIERS
SUPPLIERS | Armtec — CSP culvert and flow guard pricing (Dec-2025) | Sheet 08 section E — culvert pricing
SUPPLIERS | Various HDPE pipe suppliers — Jan-2026 quotes +15% install factor | Sheet 08 section E — HDPE pipe pricing
BENCHMARKS
BENCHMARKS | SME benchmark observations 2024-2026 — NL, NS, NB, ON, MB, BC, NT mining civil contracts | Sheet 10 — bid screening floors/ceilings
METHODOLOGY
METHODOLOGY | Standard industry practice — contractor markup stack and CDI percentages | Sheet 15 — 6-layer bid model
METHODOLOGY | CCDC 2 GC 6.2 / 6.4 / 6.5 — change order provisions | Sheet 20 — change order pricing

## 25 Real Market Benchmark
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Rev 4 — End-to-End Mining Heavy Civil ¦ Consolidated SoR + Real Market Benchmark Cross-Reference ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
REAL MARKET BENCHMARK — SME RANGES vs PUBLIC TENDER ACTUALS — CANADA 2026
Primary source: Alberta Transportation 2026 Unit Price Averages — weighted avg of 3 lowest bids on tenders awarded May 1, 2024 – Sep 30, 2025. Province-wide value. Supplementary: BC Road Builders 2026 awards, NRCan diesel pricing, public tender platforms.
Match Cat. | AB UPA Item Code | AB UPA Description | UOM | AB UPA 2026 Province Avg ($) | AB Contracts (n) | AB Total Qty | SME Floor (CAD) | SME Ceiling (CAD) | Verdict / Variance Note
EARTHWORKS
EARTHWORKS | B100 | Subgrade Excavation | m³ | 22.25 | 3 | 10230 | — | — | No direct SME match (subgrade prep only). See Sheet 08 C-30-002 (haul road sub-grade $14-$22/m²).
EARTHWORKS | C064 | Wet Excavation - Type 2 | m³ | 14.74 | 1 | 7500 | — | — | Wet excav in saturated ground. No direct match — SME common excav ~$24-$32/m³ (C-10-002) is dry-haul.
EARTHWORKS | G225 | Common Excavation | m³ | 8.2 | 10 | 1722910 | 24 | 32 | AB UPA $8.20 well below SME $24-$32. Note: AB UPA is balanced cut-and-fill on highway projects (no haul); SME C-10-002 includes 1-3 km haul. AB G248+G249 (excav loaded + truck haul) sums $15.22 + $0.44/m³·km = ~$17-$22 for 5-10 km — within SME range.
EARTHWORKS | G248 | Common/Borrow Excavation Loaded to Trucks | m³ | 15.22 | 5 | 392400 | 24 | 32 | Excav+load only (no haul). Add ~$0.44/m³·km for haul (G249). At 2 km haul = $16.10/m³; at 10 km = $19.62/m³. SME range covers.
EARTHWORKS | G236 | Borrow Excavation - Contractor Supplied | m³ | 24.4 | 6 | 237400 | 22 | 45 | Engineered fill from contractor borrow. AB UPA mid-range matches SME C-40-002 ($22-$32/m³) — WITHIN.
EARTHWORKS | G230 | Borrow Topsoil Excavation | m³ | 4.67 | 2 | 448700 | — | — | Topsoil strip only; no direct SME match (SME C-10-008 overburden strip $18-$28/m³ includes haul).
EARTHWORKS | G239 | Overhaul (cubic metre-kilometre) | m³·km | 1.78 | 3 | 453800 | — | — | Haul-distance premium — applies to all mass earthworks. AB UPA Northern Region. Multiply by km if >1 km haul.
EARTHWORKS | G300 | Topsoil Placement | m² | 0.93 | 10 | 1770250 | — | — | Per m² spread. Convert to m³ at 200mm depth: $0.93/0.2 = $4.65/m³. SME C-10-012 $55-$80/m³ INCLUDES supply — AB UPA is placement only.
GRANULAR
GRANULAR | A805 | Supply of Aggregate - No Option | tonne | 0.3 | 5 | 850070 | — | — | Mine-mouth supply rate (royalty only). SME crushing operating B-09-002 $4.50-$9.50/t — different scope.
GRANULAR | B282 | Granular Base Course Des.2 Cl.25 | tonne | 34.27 | 10 | 811950 | — | — | Per tonne placed. Convert at 2.0 t/m³ density: $34.27 × 2.0 = $68.54/m³. SME C-10-009 Granular A $105-$135/m³ is ABOVE AB UPA — SME includes higher mining-grade haul, mining-site overheads.
GRANULAR | B152 | Granular Fill | tonne | 36.67 | 1 | 1500 | — | — | Per tonne; basis comparable to B282.
GRANULAR | B180 | Preparing Subgrade Surface (First Layer) | m² | 2.01 | 8 | 879450 | — | — | Grade and compact only. SME C-30-002 haul road sub-grade $14-$22/m² includes cut+fill — AB UPA is finish-grade only.
GRANULAR | D235 | Granular Backfill - Culverts | tonne | 59.8 | 1 | 1960 | — | — | Trench backfill premium (smaller qty). Compares vs SME C-10-005 Type 2 $55-$68/m³ (at 2.0t/m³ = $27-$34/t). AB UPA HIGHER — culvert backfill is specialty work.
CULVERTS
CULVERTS | D405 | Culvert S+I (500 mm dia. CSP) | m | 616.67 | 1 | 8 | — | — | No SME 500mm match (SME C-50-002 starts at 750mm $580-$750/m). 500mm extrapolated ~$430-$580.
CULVERTS | D410 | Culvert S+I (600 mm dia. CSP) | m | 362.17 | 5 | 2683 | — | — | No direct SME 600mm. Comparable to SME C-50-002 (750mm $580-$750/m) — AB UPA LOWER, reflects high-vol highway pricing.
CULVERTS | D415 | Culvert S+I (700 mm dia. CSP) | m | 510 | 1 | 22 | 580 | 750 | Below SME floor by 12%. AB UPA = highway volume; SME C-50-002 includes mining-site indirects + bedding spec.
CULVERTS | D425 | Culvert S+I (800 mm dia. CSP) | m | 566.74 | 6 | 996 | 580 | 750 | AB UPA just below SME C-50-002 floor — high-volume pricing. SME floor justified for mining-site setting.
CULVERTS | D430 | Culvert S+I (900 mm dia. CSP) | m | 720.58 | 3 | 101 | 680 | 880 | AB UPA $720 WITHIN SME C-50-003 $680-$880. ✓
CULVERTS | D431 | Culvert S+I (1000 mm dia. CSP) | m | 824.24 | 2 | 100 | 800 | 1020 | AB UPA $824 WITHIN SME C-50-004 $800-$1,020. ✓
CULVERTS | D500 | Smooth Wall Steel Pipe S+I (750 mm dia.) | m | 1893 | 1 | 370 | — | — | Specialty large steel pipe — no SME match. Outside heavy civil typical.
CULVERTS | D520 | Smooth Wall Steel Pipe S+I (800 mm dia.) | m | 1554.67 | 1 | 540 | — | — | Specialty steel pipe.
CULVERTS | D540 | Grouting of Abandoned Culverts | m³ | 740.17 | 8 | 1153 | — | — | Specialty work — abandoning existing culverts. No SME match.
CULVERTS | D615 | Perforated Pipe - Supply and Install | m | 197.89 | 3 | 356 | — | — | Toe drain / underdrain. Compares to SME T-20-008 toe drain $165-$285/m — WITHIN.
CULVERTS | D787 | Concrete Storm Sewer - Supply and Install | m | 494.69 | 1 | 319 | — | — | Reinforced concrete storm sewer. No direct SME match.
RIPRAP
RIPRAP | F500 | Heavy Rock Riprap (Class 1, D50 = 150 mm) | m³ | 313.41 | 13 | 1799 | 65 | 100 | AB UPA $313 vs SME C-20-002 / HY-80-002 $65-$140. AB UPA dramatically HIGHER — AB UPA is bridge-spec quarried rock with strict size grading + haul; SME is mining-site bulk rip-rap. SME floor justified for mining bulk; AB UPA for spec'd structures.
RIPRAP | F505 | Heavy Rock Riprap (Class 1M) | m³ | 297.62 | 3 | 319 | 65 | 100 | Same comment as F500 — quarried spec rock.
RIPRAP | F515 | Heavy Rock Riprap (Class 2, D50 = 300 mm) | m³ | 265.82 | 3 | 1640 | 75 | 120 | AB UPA still dramatically higher than mining-site SME. Use SME range for tailings/WRSA riprap; use AB UPA for engineered structural rip-rap.
RIPRAP | F595 | Concrete Slope Protection | m² | 501.1 | 2 | 640 | — | — | Concrete slope protection — premium scope. No direct SME match.
RIPRAP | X346 | Hand-Laid Riprap - Other Locations | m² | 122.86 | 2 | 659 | — | — | Hand-laid premium; small areas. No SME match.
CONCRETE
CONCRETE | F775 | Deck Overlay Concrete - Supply | m³ | 2058.93 | 2 | 105 | 2200 | 3500 | AB UPA just BELOW SME floor for foundation/wall. Deck overlay is thinner / higher-strength (different mix). Reasonable cross-check.
CONCRETE | F822 | Concrete - Pile (cast-in-place) | m³ | 794.5 | 5 | 683 | 2200 | 3500 | Pile concrete includes drilling — different unit. NOT directly comparable to SME.
CONCRETE | F834 | Concrete - Class C (footings/grade beams) | m³ | 1951.01 | 9 | 1192 | 2200 | 3500 | AB UPA $1,951 BELOW SME floor $2,200. SME range C-60-002 reflects mining-site indirects + cold-weather pours + remoteness.
CONCRETE | F841 | Concrete - Class HPC (high performance) | m³ | 2692.3 | 5 | 1449 | 2200 | 3500 | AB UPA $2,692 WITHIN SME range $2,200-$3,500. ✓
CONCRETE | X440 | Median Concrete Surfacing | m² | 182.47 | 2 | 5330 | — | — | Median paving — no SME match. Comparable lighter concrete.
ASPHALT
ASPHALT | F980 | Asphalt Concrete Pavement | tonne | 564.57 | 4 | 456 | — | — | Small qty bridge approach asphalt — premium. SME C-30-005 $45-$62/m² (at 0.115 t/m² × $565 = $65/m²) — WITHIN.
ASPHALT | Q998 | Asphalt Concrete Pavement - Superpave | tonne | 147.89 | 5 | 173100 | — | — | Bulk highway asphalt — $147.89/t. Convert at 100mm × 2.3 t/m³ = $34/m². SME C-30-005 $45-$62/m² is for thinner 50mm HL3 — mining-site SME includes more indirects.
ASPHALT | Q990 | Asphalt Concrete Pavement - EPS Mix Type H1 | tonne | 90.37 | 1 | 148400 | — | — | Highest-volume bid (148,400 t) — biggest discount possible at scale.
ASPHALT | Q991 | Asphalt Concrete Pavement - EPS Mix Type H2 | tonne | 110.29 | 2 | 93600 | — | — | Volume discount tier
TRENCHING
TRENCHING | U100 | Trenching and Backfilling | m | 25.83 | 5 | 20160 | — | — | Bare trenching only (electrical conduit context). SME B-03-004 sanitary sewer $380-$520/m INCLUDES pipe + bedding + manhole — different scope.
ESC
ESC | E435 | Erosion Control Barrier (Silt Fence) | m | 15.16 | 9 | 3575 | 18 | 28 | AB UPA $15.16 just BELOW SME C-20-008 floor $18. AB UPA highway volumes vs mining-site SME bracket — both reasonable.
ESC | E452 | Non-Woven Geotextile - Supply and Install | m² | 2.82 | 1 | 7600 | 3 | 6 | AB UPA $2.82 BELOW SME C-20-007 floor $3 by ~6%. AB UPA used as cushion; SME is for separation + slightly heavier 6 oz. CLOSE — WITHIN tolerance.
FENCING
FENCING | G452 | Remove and Dispose of Existing Fence | km | 3901.31 | 7 | 42 | — | — | Demolition, not new install.
FENCING | G470 | New Fence S+I - Class A (highway) | km | 13211.8 | 2 | 11 | — | — | Highway fencing per km. SME B-05-002 chain link 2.4m security $110-$165/m = $110,000-$165,000/km. AB UPA much lower — different fence type (lighter highway, not security).
FENCING | G475 | New Fence S+I - Class B | km | 13956.52 | 9 | 26 | — | — | Light highway fencing.
SEEDING
SEEDING | E608 | Broad-Cast Seeding | ha | 2083.45 | 10 | 196 | — | — | Per hectare = $0.21/m². SME C-10-013 $4-$8/m² includes hydroseeding + spreading — different scope.
SEEDING | E609 | Hydro-Seeding | ha | 22420.09 | 3 | 2 | — | — | Per hectare = $2.24/m². SME C-10-013 $4-$8/m² ABOVE AB UPA — SME includes provincial spec restoration.
MILLING
MILLING | Q554 | Cold Milling Asphalt Pavement (≤50mm) | m² | 3.03 | 3 | 650050 | — | — | Existing pavement demolition. No SME match.
Q565
Q565 | Q565 | Cold Milling Asphalt Pavement | m² | 6.38 | 9 | 320676 | — | — | Larger cold milling depth.
CURB
CURB | X320 | Concrete Curb | m | 170.32 | 2 | 3145 | 185 | 265 | AB UPA $170 WITHIN ~10% of SME B-04-003 floor $185. SME includes mining-site indirects. ✓ CLOSE WITHIN.
CURB | X235 | Concrete Curb - Remove and Dispose | m | 42.05 | 2 | 3125 | — | — | Demolition only — no SME match.
ELECTRICAL
ELECTRICAL | S400 | Underground Electrical Conduit Trench Excavation | m | 65.34 | 5 | 1313 | — | — | Per metre trench for electrical only — limited cross-ref.
ELECTRICAL | U120 | Cast-In-Place Concrete Street Light Base | ea | 4759.94 | 3 | 47 | 1850 | 3500 | AB UPA $4,760 ABOVE SME EL-70-003 ceiling $3,500. Street light bases include sleeves, bolt patterns, conduit — premium scope.
ELECTRICAL | U122 | Pre-Cast Concrete Street Light Base | ea | 3480.95 | 3 | 223 | 1850 | 3500 | AB UPA $3,481 WITHIN SME range. ✓
BENCHMARK SUMMARY — INTERPRETATION
1. Where AB UPA falls WITHIN the SME range (green): the SME range is well-calibrated to real Canadian public-tender market. Use SME confidently.
2. Where AB UPA falls BELOW the SME floor (amber): SME range is conservative — typically because mining-site SME includes additional camp/LOA, remote indirects, mining-spec QA, and risk premium. SME floor justified for remote mining; consider lower bound for accessible drive-in projects.
3. Where AB UPA falls ABOVE the SME ceiling (red): typically the AB UPA item has additional specialty scope (bridge-grade quarry rock, specialty steel pipe, deck overlay) — not directly comparable. Review SME scope inclusion.
4. AB UPA is HIGHWAY tender data, not mining tender data. It is the closest available public benchmark for civil unit rates in Canada. NI 43-101 filings have aggregate capex but rarely line-item unit rates publicly. Detailed mining tender unit rates are commercial-in-confidence.
5. Adjust AB UPA to mining-site context by adding: (a) camp/LOA per Sheet 05 if remote; (b) regional adjustor per Sheet 14 if not Alberta; (c) mining-spec QC overhead if applicable.
DATA SOURCES & PROVENANCE
WEB | Alberta Transportation Unit Price Averages 2026 (XLSX) |  |  |  | https://www.alberta.ca/system/files/custom_downloaded_images/trans-unit-price-averages.xlsx
WEB | Alberta Transportation — Unit Prices and Cost Adjustments page |  |  |  | https://www.alberta.ca/unit-prices-and-cost-adjustments
WEB | BC Road Builders — Tender Report (BC highway awards) |  |  |  | https://www.roadbuilders.bc.ca/tender-report/
WEB | CanadaBuys / MERX — Federal procurement portal |  |  |  | https://canadabuys.canada.ca/
WEB | SaskTenders — Saskatchewan public sector tendering |  |  |  | https://sasktenders.ca/
WEB | Manitoba Infrastructure — Tendering & Contracts (bid results) |  |  |  | https://www.gov.mb.ca/mti/contracts/bidresults.html
WEB | MERX — Saskatchewan, Manitoba and federal opportunities |  |  |  | https://www.merx.com/
WEB | Natural Resources Canada — Mining Capital Expenditures |  |  |  | https://natural-resources.canada.ca/minerals-mining/mining-data-statistics-analysis/minerals-mining-publications/capital-expenditures
WEB | Statistics Canada — Building Construction Price Index (BCPI) |  |  |  | https://www.statcan.gc.ca/
WEB | CBSA — Notices on Chinese steel/rebar surtax (24-26 / 25-22) |  |  |  | https://www.cbsa-asfc.gc.ca/
WEB | Bank of Canada — Exchange rates (USD/CAD) |  |  |  | https://www.bankofcanada.ca/rates/exchange/