RICK MILLER SME STANDARD

CANADA 2026 MINING HEAVY CIVIL
ESTIMATING MANUAL & RATE LIBRARY

Consolidated Schedule of Rates, Bid Support Package & Estimating Standard

AACE 18R-97 Class 3 Baseline | Canada-wide Q2-2026 | All figures CAD

| DOCUMENT NUMBER | RMM-CIVIL-CANADA-2026-MANUAL-REV2 |
| --- | --- |
| REVISION | Rev 2 — End-to-End Mining Civil + Real Market Benchmark |
| PREPARED BY | Rick Miller, Senior Project Director / EPCM |
| ISSUE DATE | Q2 2026 |
| BASE CURRENCY | Canadian Dollar (CAD) |
| ESTIMATE CLASS BASIS | AACE 18R-97 Class 3 (±20% / +30%) |
| ESCALATION BASIS | Ausenco go-by Q2-2020 × 1.25 BCPI cumulative → Q2-2026 |
| SOURCE DATA | RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 + RMM-CIVIL-CANADA-2026-REV0 |
| INTENDED USERS | Contractor estimators, EPCM cost engineers, owner cost teams, bid evaluators |
| CONFIDENTIALITY | Internal — not for public quotation issue without project-specific validation |

TABLE OF CONTENTS

1.  Executive Summary

2.  Document Control, Basis & Source Data Provenance

3.  Estimating Standards & Methodology (AACE 18R-97)

4.  Crew Compositions & Production Assumptions

5.  Labour Rates — Canada 2026 (Fully Burdened)

6.  Equipment Rates — Canada 2026 (Fully Operated)

7.  Equipment Spreads by Scope

8.  Master Schedule of Rates (Heavy Civil + Contractor Scope)

9.  Unit Rate Build-Up Methodology

10.  Bid Screening — Floors, Ceilings & Sense-Checks

11.  Contractor Indirects (CDI) & Overhead Build-Up

12.  Bonding & Insurance

13.  Standby Rates, Acceleration, Winter Premiums & Owner-Caused Delay

14.  SME Factors — Design Growth, Wastage, Regional, Escalation, Accuracy

15.  Contractor Bid Cost Structure — 6-Layer Markup Model

16.  Mobilization & Demobilization Logic

17.  Constructability & Execution Assumptions

18.  Scope Inclusions, Exclusions & Clarifications Register

19.  Bid Leveling & Tender Comparison Framework

20.  Change Order Pricing Methodologies

21.  Project Estimate Roll-Up Template

22.  Risk & Contingency Register

23.  Glossary & Abbreviations

24.  Sources & References

25.  Real Market Benchmark — SME Ranges vs Alberta Transportation 2026 UPA [Rev 2]

1.  EXECUTIVE SUMMARY

1.1  Purpose

This document is the consolidated, internally-maintained estimating standard and rate library for Canadian mining heavy civil construction. It is designed to be used by contractors, EPCMs, and owner cost teams across the full project lifecycle: budgetary pricing, feasibility-class estimates, tender support, bid evaluation, change pricing, and unit-rate validation.

1.2  Baseline Content (Extracted from Source Workbooks)

The following content is drawn directly from the two source workbooks authored by the same author:

12 crew codes (B1–N1) — labour + equipment all-in $/hr with 2020 → 2026 escalation;

27 fully-burdened labour positions covering supervision, civil trades, drilling/blasting, mechanical, trades, electrical, instrumentation, PM and HSE;

30 fully-operated equipment items with fuel burn, mob/demob flags, and effective availability;

~78 Heavy Civil unit rates across 8 sections (earthworks, water management, roads, WRSA/TMF, drainage, concrete, steel, closure);

~22 contractor-scope unit rates (blasting, dewatering, buried services, paving, fencing, signage, rock support, culvert structures, crushing);

29 bid-screening floors/ceilings for tender evaluation;

19 bonding & insurance line items including WCB rates by province;

25 contractor overhead build-up items (field office, PM staff, QC, environmental);

19 standby & schedule items (equipment standby, OT, winter cost, owner-caused delay);

SME factors covering design growth (Class 4 → Class 1), wastage, 10 Canadian regional adjustment zones, escalation, and AACE accuracy ranges.

1.3  Framework Templates (Authored in This Manual)

The following sections are industry-standard scaffolding sections, clearly marked as [TEMPLATE] in the corresponding Excel tabs. They are not drawn from the source workbooks — they are blank or sample structures to be populated per project:

Equipment spreads by scope (Section 7);

Unit rate build-up calculator (Section 9);

Constructability and execution assumptions (Section 17);

Scope inclusions, exclusions and clarifications register (Section 18);

Bid leveling tender comparison (Section 19);

Change order pricing methodologies (Section 20);

Project estimate roll-up sheet (Section 21);

Risk and contingency register (Section 22).

1.4  Estimate Class Applicability

| AACE Class | Project Stage | Application in This Manual |
| --- | --- | --- |
| Class 5 | Concept screening / ROM | Use floor/ceiling ranges; apply +15-20% design growth |
| Class 4 | Pre-feasibility / study | Mostly stochastic; equipment-factored; +15-20% DG |
| Class 3 | Feasibility / budget (this baseline) | Mid-range unit rates; +10-15% DG |
| Class 2 | Sanction / AFE / pre-FID | Use mid-low range; +5-10% DG; firm quotes long-leads |
| Class 1 | Tender / check estimate | Project-specific RFQ; low end of range; +2-5% DG |

1.5  Key 2026 Benchmarks (mid-range)

Mass earthworks rock (blasted): $55–$120 / m³

Engineered fill compacted: $22–$45 / m³

Haul road full build (sub-grade to surface): $65–$120 / m²

TMF embankment Zone A/B: $22–$45 / m³

HDPE 2 mm liner (full S+I+CQA): $28–$55 / m²

CSP culvert 1200 mm: $1,000–$1,600 / m

Concrete wall / grade beam: $2,500–$3,200 / m³

Rebar Grade 400 (S+I): $4,000–$6,500 / tonne — CBSA 25% surtax exposure

Performance bond medium contract ($5–$25M): 1.0–1.8% of contract value

Regional adjustor range: 1.00 (MB/SK baseline) → 1.55 (Yukon/NWT/Nunavut)

Winter construction premium: 10–25% (all Canada)

1.6  Boundaries of Use

This manual provides a defensible baseline for internal estimating and bid evaluation. It is not a public quotation. Do not issue any unit rate as fixed pricing without project-specific validation, including supplier RFQs for long-lead and bulk materials, confirmation of WCB classification by province, verification of CBSA surtax exposure on steel and rebar, and site-specific productivity assumptions.

2.  DOCUMENT CONTROL, BASIS & SOURCE DATA PROVENANCE

2.1  Source Workbooks

This manual consolidates and extends two source workbooks authored by the same author:

| File Code | Title | Content |
| --- | --- | --- |
| RMM-CIVIL-CANADA-2026-REV0 | EPCM Benchmark Estimator (Rev E) | Crew Rates (12), Labour Rates (27), Equipment Rates (30), Heavy Civil Unit Rates (78), SME Factors |
| RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 | Contractor Bid Tool (Rev G) | Bid Summary (6-layer markup), Additional Unit Rates (22), Bonding & Insurance (19), Overhead Build-Up (25), Standby & Schedule (19), Bid Screening (29) |

2.2  Currency, Base Period & Exchange

All figures are in Canadian Dollars (CAD), basis Q2-2026. USD/CAD reference: 1.36–1.37 (Bank of Canada, May 2026).

2.3  Escalation Basis

Unit rates inherited from a Q2-2020 go-by have been escalated by a single cumulative factor of x1.25, representing the BCPI midpoint to Q2-2026. Rates for labour, equipment, and material that have been re-baselined to 2026 directly (per supplier quotes or current published WCB / fuel tables) are flagged in the Source/Basis column of each tab.

2.4  Currency of Pricing

Pricing in this manual is current to Q2-2026. Major price exposure items (diesel, steel, rebar) are subject to re-pricing per the Escalation section of Sheet 14. The cumulative escalation factor (x1.23 to x1.27) should be re-validated each quarter against published BCPI.

2.5  Confidentiality & Use

This document is intended for internal estimating, bid support and benchmarking. Distribution beyond a project team should be limited and approved. Any external use must include a current price-validity statement and exclusions register (Section 18).

3.  ESTIMATING STANDARDS & METHODOLOGY (AACE 18R-97)

3.1  Estimate Classification Framework

This manual adopts AACE International Recommended Practice 18R-97 (Cost Estimate Classification System — As Applied to Engineering, Procurement, and Construction for the Process Industries) as its classification framework. The 5-class scheme is interpreted for mining heavy civil work as follows:

| Class | Stage | Project Def. | Methodology | Accuracy Range | Typical Use |
| --- | --- | --- | --- | --- | --- |
| Class 5 | Concept screening | 0–2% | Stochastic / parametric / per-unit-capacity factors | -50% / +100% | ROM / order of magnitude |
| Class 4 | Pre-feasibility / study | 1–15% | Mostly stochastic; equipment factored; some unit rates | -30% / +50% | Concept evaluation; site selection |
| Class 3 | Feasibility / budget | 10–40% | Semi-detailed; mostly unit rates; MTOs from PFD/general arr. | -20% / +30% | Budget authorization (this baseline) |
| Class 2 | Sanction / AFE | 30–75% | Detailed unit rates; near-complete MTOs; firm quotes long-leads | -10% / +20% | FID / sanction approval |
| Class 1 | Tender / check | 65–100% | Detailed; IFC drawings; firm RFQ pricing; full crew/equip build-up | -5% / +10% | Tender bid; check estimate |

3.2  Design Growth Allowances

Design growth is applied at quantity-take-off level to compensate for undefined scope at the estimate class. Use values from the following table:

| Class | Discipline | Low | High | Notes |
| --- | --- | --- | --- | --- |
| Class 5 / 4 | Earthworks / civil | 15% | 20% | Limited geotech; preliminary drawings |
| Class 3 | Earthworks / civil (this baseline) | 10% | 15% | Standard level for feasibility / budget |
| Class 2 | Earthworks / civil | 5% | 10% | Pre-FID; IFC packages near complete |
| Class 1 | Earthworks / civil | 2% | 5% | Full detailed design completed |
| All classes | Concrete works (additive) | +5% | +5% | Add 5% incremental to earthworks DG |

3.3  Wastage Factors

Wastage factors are applied to material take-offs (not to labour or equipment).

| Material | Low | High | Basis |
| --- | --- | --- | --- |
| Granular aggregate | 5% | 10% | Rounding + delivery variance |
| Concrete (formed) | 8% | 12% | Pump waste + edge loss |
| Rebar | 3% | 7% | Cutting waste; depends on bar size and complexity |
| Geomembrane liner | 5% | 10% | Panel overlaps + anchor trench + QA sampling |
| Geotextile | 10% | 15% | ASTM D4439 — 6-inch overlap minimum |

3.4  Escalation & Market Basis (Q2-2026)

All cumulative cost escalation from Q2-2020 go-by data is applied at x1.25 (BCPI midpoint, range x1.23 to x1.27). Live market signals at issue date are:

| Item | Low | High | Source |
| --- | --- | --- | --- |
| Diesel — NS (May 2026) | $2.13/L | $2.21/L | NS Energy Regulatory Board |
| Diesel — AB (May 2026) | $1.68/L | $1.78/L | NRCan |
| Diesel — BC Metro (May 2026) | $2.15/L | $2.35/L | NRCan |
| USD/CAD (May 2026) | 1.36 | 1.37 | Bank of Canada |
| CBSA surtax — Chinese structural steel | 25% | 25% | CBSA Notices 24-26 / 25-22 |
| CBSA surtax — Chinese rebar | 25% | 25% | Confirm supplier origin certificate |
| Labour CBA escalation 2024–2026 (NL) | 3.5% | 5.5% | Per trade — see Section 5 |

4.  CREW COMPOSITIONS & PRODUCTION ASSUMPTIONS

Twelve standard crew codes are defined. Crew rates are reported both at the 2020 go-by basis and at the 2026 escalated basis (x1.25). Productivity (Prod Factor) is applied at the unit rate level (Section 8).

| Code | Description | Avg Size | 2020 Total $/hr | 2026 Total $/hr |
| --- | --- | --- | --- | --- |
| B1 | Civil Works — Light | 26.1 | $127.50 | $159.37 |
| B2 | Civil Works — Medium | 28.1 | $158.90 | $198.63 |
| B3 | Civil Works — Heavy | 37.7 | $161.30 | $201.63 |
| B4 | Civil Liner & Pipeline | 28.1 | $116.10 | $145.12 |
| C1 | Concrete | 22.6 | $109.40 | $136.75 |
| D1 | Structural Steel | 17.6 | $114.10 | $142.63 |
| E1 | Architectural | 19.6 | $100.30 | $125.37 |
| G1 | Mechanical Services | 17.6 | $111.30 | $139.13 |
| H1 | Mechanical Equipment | 23.6 | $115.80 | $144.76 |
| J1 | Piping | 13.7 | $110.50 | $138.12 |
| K1 | Electrical | 10.8 | $117.80 | $147.25 |
| N1 | Instrumentation | 10.3 | $123.80 | $154.75 |

Crew composition by trade is shown in Section 5. The crews above are SME averages for benchmarking and unit-rate composition — not a fixed roster. For tender or sanction-class estimates, build the project-specific crew from Section 5 labour rates and Section 6 equipment rates.

5.  LABOUR RATES — CANADA 2026 (FULLY BURDENED)

Labour rates are fully burdened: base wage + statutory burdens (CPP, EI, EHT, vacation, statutory holidays) + employer benefits + WCB (province-specific, see Section 12) + small tools allowance + supervision ratio. Camp/LOA is shown as an additive per-person cost (rows O2 and O3) and is not duplicated inside the trade rates.

| Ref | Position | Class | 2026 Low ($/hr or /day) | 2026 High ($/hr or /day) |
| --- | --- | --- | --- | --- |
| S1 | General Superintendent | Supervisor | $154 | $172 |
| S2 | Superintendent | Supervisor | $136 | $155 |
| S3 | General Foreman | Supervisor | $125 | $140 |
| C1 | Civil Work Lead | Civil | $116 | $132 |
| C2 | Equip Op — Heavy Duty | Civil | $110 | $128 |
| C3 | Equip Op — Medium Duty | Civil | $101 | $116 |
| C4 | Equip Op — Light Duty | Civil | $93 | $106 |
| C5 | Labourer — Journeyman | Civil | $82 | $95 |
| C6 | Labourer — 2yr Apprentice | Civil | $73 | $84 |
| C7 | Labourer — 1st yr Apprentice | Civil | $64 | $74 |
| D1 | Driller — Journeyman | Civil/Blast | $93 | $108 |
| D2 | Blaster — Journeyman | Civil/Blast | $93 | $108 |
| M1 | Mechanic — Heavy Duty | Mechanical | $84 | $98 |
| M2 | Mechanic — Medium Duty | Mechanical | $92 | $106 |
| T1 | Carpenter — Journeyman | Trades | $109 | $125 |
| T3 | Concrete Lead | Trades | $125 | $140 |
| T4 | Concrete Finisher | Trades | $95 | $108 |
| T5 | Ironworker (rebar/struct) | Trades | $115 | $132 |
| T6 | Welder / Pipefitter | Trades | $113 | $130 |
| T8 | Rodman — Reinforcement | Trades | $94 | $108 |
| E1 | Electrician — Journeyman | Electrical | $127 | $145 |
| I1 | Instrumentation Tech | Instrumentation | $127 | $145 |
| P1 | Project Engineer — Field | PM/Eng | $109 | $125 |
| P2 | Project Engineer — Senior | PM/Eng | $123 | $140 |
| O1 | Safety Officer (NCSO) | HSE | $110 | $125 |
| O2 | Camp — all-in per person/day | Indirect | $220 | $300 |
| O3 | LOA subsistence — non-camp | Indirect | $180 | $250 |

6.  EQUIPMENT RATES — CANADA 2026 (FULLY OPERATED)

Equipment rates are fully operated (operator wage already burdened). Fuel is shown in L/hr; multiply by site diesel price for fuel-cost portion. Availability % drives effective hours per shift. Mob/demob: 'Required' = additional cost per Section 16; 'Included' = built into hourly rate; 'By truck' = transport on flatbed at nominal cost.

| Cat | Equipment | Size | Low $/hr | High $/hr | Fuel L/hr | Mob | Util |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HT | Tandem dump truck | 18-20T | $140 | $165 | 45-65 | Required | 85% |
| HT | Tri-axle dump truck | 25T | $155 | $180 | 55-75 | Required | 85% |
| HT | Wiggle wagon / Super B | 45T | $185 | $215 | 65-90 | Required | 80% |
| HT | Off-road haul truck | 40-100T | $320 | $500 | 80-140 | Included | 85% |
| EX | Hydraulic excavator | Cat 320 20-25T | $250 | $330 | 18-25 | Required | 85% |
| EX | Hydraulic excavator | Cat 336 35-40T | $340 | $430 | 25-35 | Required | 85% |
| EX | Hydraulic excavator | Cat 390 50-65T | $460 | $580 | 38-50 | Required | 82% |
| EX | Long-reach excavator | 20T 18m reach | $290 | $380 | 18-25 | Required | 82% |
| DO | Track dozer | Cat D6N 17T | $250 | $320 | 20-30 | Required | 88% |
| DO | Track dozer | Cat D8T 37T | $380 | $480 | 35-48 | Required | 88% |
| DO | Track dozer | Cat D10T 58T | $520 | $650 | 50-68 | Required | 85% |
| GR | Motor grader | Cat 140M | $280 | $360 | 18-26 | Required | 88% |
| GR | Motor grader | Cat 16M large | $360 | $450 | 22-32 | Required | 88% |
| CP | Vib roller single drum | Cat CS56B 12T | $200 | $270 | 15-22 | Required | 88% |
| CP | Padfoot compactor | Cat CS74B 17T | $240 | $310 | 18-26 | Required | 88% |
| CP | Plate compactor / jumping jack | 0.5-1T | $45 | $75 | 5-8 | By truck | 90% |
| WL | Wheel loader | Cat 930M 10T | $200 | $270 | 18-26 | Required | 87% |
| WL | Wheel loader | Cat 950M 16T | $250 | $320 | 22-30 | Required | 87% |
| WL | Wheel loader | Cat 980M 22T | $320 | $400 | 28-38 | Required | 87% |
| DR | Rotary drill rig | Atlas 120mm hole | $550 | $750 | 35-50 | Included | 80% |
| SK | Skid steer | Cat 262D | $95 | $135 | 10-15 | By truck | 90% |
| WP | Diesel submersible pump | 4-inch 150mm | $55 | $85 | 10-16 | By truck | 90% |
| WP | Diesel submersible pump | 8-inch 200mm | $120 | $180 | 20-30 | By truck | 90% |
| CR | Rough terrain crane | Grove RT 60T | $650 | $900 | 30-45 | Required | 80% |
| CR | Lattice boom crawler crane | Liebherr 150T | $1800 | $2600 | 60-90 | Included | 78% |
| MI | Rock breaker / hyd hammer | Cat 345 + hammer | $480 | $620 | 28-40 | Required | 80% |
| MI | Air compressor diesel tow. | 375 cfm | $75 | $110 | 12-18 | By truck | 90% |
| MI | Light tower diesel | 8-10 kW | $35 | $55 | 5-8 | By truck | 95% |
| MI | Fuel tanker site supply | 10,000L | $180 | $250 | 30-40 | Required | 90% |
| MI | Water truck dust suppression | 10,000L | $160 | $220 | 30-40 | Required | 90% |

7.  EQUIPMENT SPREADS BY SCOPE  [TEMPLATE — validate per project]

Typical SME spreads for Class 3 estimating. Validate fleet sizing against site access, haul distance, geotechnical conditions, climate window, and crew availability before committing to a bid.

| Scope | Primary + Support Equipment | Crew | Production |
| --- | --- | --- | --- |
| Mass earthworks — rock | 1× DR rotary, 1× EX Cat 390, 4–6× off-road 40-100T | B3 | 800–1,500 m³/shift |
| Mass earthworks — common | 1× EX Cat 336, 4–6× tandem/tri-axle, 1× D8T | B3 | 1,200–2,000 m³/shift |
| Engineered fill placement | 1× EX Cat 320 or WL 950M, 2–4× tandem, 1× CS74B | B2 | 600–1,000 m³/shift |
| Haul road build | 1× D8T (sub-base), 1× 140M grader (surface) | B2 | 150–300 m/day full build |
| HDPE liner install (TMF) | 1× WL 930M (panel handling), 1× SK, welding crew | B4 | 1,500–3,000 m²/day |
| Culvert install (≥900 mm CSP) | 1× EX Cat 320, 1× WL 930M, 2× tandem, dewatering | B4 | 20–40 m/day |
| Buried services trenching | 1× EX Cat 320, 1× tandem, 1× WL 930M, plate compactor | B4 | 60–120 m/day |
| Concrete pour — foundation | 1× crane RT 60T, 1× concrete pump, 1× vibrator | C1 | 12–25 m³/day |
| Rock support — shotcrete | 1× shotcrete pump, 1× EX (mesh handling), 1× SK | C1 | 120–250 m²/day |
| Drill + blast rock anchors | 1× drill rig (anchor), 1× EX, 1× grout plant | D1 | 8–15 anchors/day |
| Buried HDPE forcemain | 1× EX Cat 320, 1× WL, 1× fusion machine, 1× tandem | B4 | 80–150 m/day |
| Demolition / strip and grub | 1× D8T, 1× EX Cat 336, 1× tandem | B3 | 0.5–1.5 ha/day |

8.  MASTER SCHEDULE OF RATES

This section presents the consolidated Heavy Civil + Contractor scope Schedule of Rates. The full line-item table — including unit man-hours, productivity factor, labour / equip / material / sub build-up columns, CDI %, design growth %, wastage %, and crew code — is provided in the companion Excel workbook (sheet '08 SoR Master'). The summary below shows the section structure and 2026 range bands.

8.1  Section Structure

| Section | Scope | Source | Approx Items |
| --- | --- | --- | --- |
| A — Earthworks & Mass Excavation | Common/rock excavation, fill, granular, drill+blast (holes only) | Rev E | 15 |
| B — Water Management / SWM & ESC | Riprap, geotextile, silt fence, sediment control, temp dewatering | Rev E | 10 |
| C — Roads, Pads & Working Surfaces | Sub-grade, granular base, asphalt, equip pads, ditching | Rev E | 8 |
| D — WRSA / TMF Embankment | Embankment fill, HDPE liner, drainage layers, riprap ditching | Rev E | 8 |
| E — Drainage, Culverts & Piping | CSP, HDPE, flow guards, discharge piping | Rev E | 15 |
| F — Concrete | Walls, piers, footings, shotcrete, rebar | Rev E | 5 |
| G — Structural Steel | Beams, columns, grating, handrail, stairs, deck, cladding | Rev E | 8 |
| H — Closure & Reclamation | Cap, cover, topsoil, HDPE cap liner | Rev E | 4 |
| I — Blasting (full scope) | Drill, charge, blast, clear, controlled / presplit, secondary | Rev G | 4 |
| J — Permanent Dewatering | Pump stations, forcemains, wellpoint systems | Rev G | 5 |
| K — Buried Services | Water, sewer, manholes, thrust blocks, valves, hydrants | Rev G | 7 |
| L — Concrete Paving & Curbing | Paving, curb & gutter, wheel wash | Rev G | 3 |
| M — Fencing, Security & Wildlife | Chain link, wildlife exclusion electrified, gates | Rev G | 4 |
| N — Site Signage & Traffic Mgmt | Flagging, dust suppression (calcium chloride) | Rev G | 2 |
| O — Rock Anchors & Stabilization | Rock anchors, wire mesh, shotcrete + mesh | Rev G | 4 |
| P — Culvert Structures | Precast box, arch, headwalls | Rev G | 3 |
| Q — Aggregate Crushing On-Site | Granular A/B, riprap D50 — crushing operating cost | Rev G | 2 |
| R — Underground Civil [Rev 2] | Shaft sinking, lateral dev, raise bore, ground support, mucking | Rev 2 | 12 |
| S — Tailings Dam Zoned Construction [Rev 2] | Zoned starter dam + raises, internal drainage, instrumentation, spillway | Rev 2 | 13 |
| T — Heap Leach Pad Construction [Rev 2] | Multi-liner system, drain rock, manifolds, PLS pond, drip irrigation | Rev 2 | 10 |
| U — Process Plant Civil [Rev 2] | Mill / crusher / thickener / flotation foundations, conveyor structures, slabs | Rev 2 | 11 |
| V — Slurry / Concentrate / Fuel Pipeline [Rev 2] | ROW clearing, trenching, HDPE/steel pipe, valve stations, HDD crossings | Rev 2 | 10 |
| W — Mine Site Bridges & Crossings [Rev 2] | Modular bridges, concrete bridges, haul road bridges, abutments / piers, large box culverts | Rev 2 | 6 |
| X — Power Line & Substation Civil [Rev 2] | Tower foundations, distribution poles, substation pads & grounding, ROW clearing | Rev 2 | 7 |
| Y — Hydraulic Structures [Rev 2] | Diversion channels, riprap classes, energy dissipators, spillway weirs, inlet structures | Rev 2 | 9 |

Rev 2 totals: 185 line items across 25 sections (A–Y). Specialty mining sections (R–Y) added in Rev 2 from SME judgement; ranges are Class 3 SME baselines pending project-specific RFQ confirmation.

8.2  How to Use the Master SoR

Each line item carries: Total LOW (CAD) and Total HIGH (CAD) — these are all-in unit prices already including labour + equipment + material + subcontract + CDI (where shown). For Rev E items (sections A–H) the labour / equipment / material build-up is decomposed; for Rev G items (sections I–Q) the build-up is presented as direct $/UOM range only — use the Unit Rate Build-Up Calculator (Section 9) to reverse-engineer if a full build-up is required for a tender estimate.

9.  UNIT RATE BUILD-UP METHODOLOGY

The standard SME unit-rate composition is a six-element build-up:

| Element | Symbol | Source | Application |
| --- | --- | --- | --- |
| Unit Labour | L | Crew rate × (Unit MH / Productivity) | Section 4–5 |
| Unit Equipment | E | Same crew driver — included in crew total | Section 4 / 6 |
| Unit Material | M | Supplier quote × (1 + Wastage) | Section 3.3 / supplier RFQ |
| Unit Subcontract | S | Sub quote (bare, before markup) | Per sub |
| Contractor Indirect | I | % of (L+E+M+S) — CDI overhead | Section 11 / 14 |
| Total direct unit rate | U | = (L + E + M + S) × (1 + I) | Sheet 09 calculator |

Two further factors are applied at unit-rate level before roll-up:

| Factor | Symbol | Range | Notes |
| --- | --- | --- | --- |
| Design growth % | DG | 2–20% depending on AACE class | Apply to quantity, not to unit rate |
| Regional adjustor | R | 1.00 – 1.55 | Apply to direct unit rate × (1+DG) |

Final unit rate = U × (1 + DG) × R. The 6-layer markup stack (Section 15) is then applied at project roll-up, not at line level. The companion Excel workbook (sheet '09 Unit Rate Calculator') provides a live calculator with formulas.

10.  BID SCREENING — FLOORS, CEILINGS & SENSE-CHECKS

Use the following benchmarks to validate tender pricing before award. Any bid line item priced more than 20% below the floor or 20% above the ceiling warrants a clarification request. Items priced below the floor most commonly indicate missing scope (insulation, CQA, supply, etc.).

| Category | Benchmark Item | UOM | Floor | Ceiling |
| --- | --- | --- | --- | --- |
| EARTHWORKS | Mass earthworks — rock (blasted) | $/m³ | $55 | $120 |
| EARTHWORKS | Engineered fill compacted Zone A/B | $/m³ | $22 | $45 |
| EARTHWORKS | Granular road base 150mm | $/m² | $22 | $42 |
| EARTHWORKS | Haul road full build (sub-grade to surface) | $/m² | $65 | $120 |
| EARTHWORKS | Strip and grub per hectare | $/ha | $8,500 | $18,000 |
| WRSA / TMF | TMF embankment engineered fill | $/m³ | $22 | $45 |
| WRSA / TMF | HDPE liner 2mm supply+install | $/m² | $28 | $55 |
| WRSA / TMF | TMF perimeter ditch riprap lined | $/m | $280 | $500 |
| DRAINAGE | CSP culvert 1200mm supply+install | $/m | $1,000 | $1,600 |
| DRAINAGE | HDPE 150mm above grade insulated | $/m | $230 | $380 |
| DRAINAGE | Flow guard 600mm supply+install | $/ea | $2,200 | $3,500 |
| DRAINAGE | Flow guard 1200mm supply+install | $/ea | $8,000 | $12,000 |
| CONCRETE | Concrete foundation/wall | $/m³ | $2,200 | $3,500 |
| CONCRETE | Shotcrete with fibre 75mm | $/m² | $90 | $160 |
| CONCRETE | Rebar supply+install | $/tonne | $3,800 | $6,500 |
| BLASTING | Pre-blast survey per structure | $/struct | $3,000 | $9,000 |
| FENCING | Wildlife exclusion electrified 2.4m | $/m | $150 | $280 |
| BURIED SERVICES | Sanitary manhole precast 1200mm | $/ea | $4,000 | $8,000 |
| OVERHEAD CHECK | Contractor OH+profit — $50M project | % dir. | 14% | 22% |
| OVERHEAD CHECK | Performance + L&M bond (>$25M) | % cont. | 0.75% | 1.25% |

11.  CONTRACTOR INDIRECTS (CDI) & OVERHEAD BUILD-UP

Contractor field indirects (CDI) are the site-administrative and supervisory costs allocated across all direct work. Typical project total: 12–18% of direct cost. The detail build-up below is from the source workbook (Rev G).

| Category | Item | UOM | 2026 Range (CAD) |
| --- | --- | --- | --- |
| FIELD OFFICE | Site trailer — lunchroom / dryroom | month | $1,500–$2,500 |
| FIELD OFFICE | Temp power — generator 100 kW diesel | month | $4,500–$8,500 |
| FIELD OFFICE | Temp power — 250 kW generator large camp | month | $9,500–$16,000 |
| FIELD OFFICE | Site IT, internet, comms (Starlink/repeater) | month | $850–$2,500 |
| FIELD OFFICE | Site vehicle — project pickup truck | month | $1,200–$1,800 |
| FIELD OFFICE | Site vehicle — 20-seat crew bus | month | $3,500–$6,500 |
| FIELD OFFICE | Mob/demob — site setup + teardown | LS | $35,000–$85,000 |
| PM STAFF | Senior Project Engineer | month | $14,000–$20,000 |
| PM STAFF | Field / QC Engineer | month | $11,000–$16,000 |
| PM STAFF | Site Safety Officer (NCSO certified) | month | $12,000–$17,000 |
| PM STAFF | Senior Superintendent | month | $16,000–$24,000 |
| PM STAFF | General Foreman | month | $13,000–$19,000 |
| PM STAFF | Document Controller / Field Admin | month | $7,500–$11,000 |
| QC & TESTING | Nuclear density testing — crew/day | day | $850–$1,500 |
| QC & TESTING | Concrete cylinder testing — per set | set | $185–$350 |
| QC & TESTING | Aggregate gradation testing | test | $250–$450 |
| QC & TESTING | Geomembrane weld testing (spark test) | m weld | $2.50–$4.50 |
| QC & TESTING | Survey control — survey crew/day | day | $2,500–$4,500 |
| ENVIRONMENTAL | Spill kit and containment supplies | month | $350–$750 |
| ENVIRONMENTAL | Environmental water sampling | sample | $450–$950 |
| ENVIRONMENTAL | Environmental coordinator (part-time) | month | $5,500–$9,500 |
| HEAD OFFICE | Warranty / deficiency holdback allowance | % cont. | 0.5%–1.0% |

12.  BONDING & INSURANCE

Bonding and insurance rates for Canadian mining heavy civil contractors at typical 2026 rates. WCB is province-specific — confirm classification and base rate against the relevant authority before pricing.

| Category | Item | Basis | Rate (CAD) |
| --- | --- | --- | --- |
| SURETY | Performance Bond — small (<$5M) | % of contract | 1.5%–2.5% |
| SURETY | Performance Bond — medium ($5–$25M) | % of contract | 1.0%–1.8% |
| SURETY | Performance Bond — large (>$25M) | % of contract | 0.75%–1.25% |
| SURETY | Labour & Material Payment Bond | % of contract | 0.5%–1.0% |
| SURETY | Maintenance/Warranty Bond — 12 month | % of contract | 0.5%–1.0% |
| LIABILITY | Contractor's Pollution Liability | Annual policy | $1,500–$3,500 |
| WCB | Labourer — Alberta WCB Industry 41 | Per $100 payroll | $3.80–$5.20 |
| WCB | Labourer — BC WorkSafeBC Class 711001 | Per $100 payroll | $4.50–$6.00 |
| WCB | Labourer — NS WCB NS | Per $100 payroll | $3.80–$5.50 |
| WCB | Labourer — NL WorkplaceNL | Per $100 payroll | $4.00–$5.80 |
| WCB | Labourer — Quebec CNESST | Per $100 payroll | $5.50–$8.00 |
| WCB | Equipment Operator — all provinces | Per $100 payroll | $3.50–$5.00 |
| WCB | Blaster / Driller — elevated risk | Per $100 payroll | $5.50–$8.00 |
| PROPERTY | Contractor's Equipment Floater | % of fleet repl/yr | 0.5%–1.2% |

13.  STANDBY RATES, ACCELERATION & DELAY

Standby rates apply when equipment and crew are held on site for owner-caused delay, weather hold, or force majeure. Acceleration premiums apply when work is compressed or pushed into night / weekend windows. Cold-weather and winter premiums apply where work proceeds in Nov–Mar.

| Category | Item | UOM | 2026 Range (CAD) |
| --- | --- | --- | --- |
| EQUIP STANDBY | Excavator Cat 320 — standby | hr | $110–$155 |
| EQUIP STANDBY | Excavator Cat 336 — standby | hr | $140–$200 |
| EQUIP STANDBY | Track dozer D8T — standby | hr | $155–$215 |
| EQUIP STANDBY | Motor grader Cat 140M — standby | hr | $110–$155 |
| EQUIP STANDBY | RT crane 60T — standby | hr | $320–$480 (min 4hr call-out) |
| EQUIP STANDBY | Crawler crane 150T — standby | hr | $850–$1,300 |
| LABOUR STANDBY | Equipment operator — standby | hr | $93–$128 |
| LABOUR STANDBY | B3 heavy civil crew of 10 — standby | day | $7,000–$10,000 |
| ACCELERATION | Overtime — double time (Sun/holiday) | % add | 100% / 100% |
| ACCELERATION | Afternoon shift premium | % add | 5%–10% |
| ACCELERATION | Night shift premium | % add | 10%–15% |
| WINTER | Cold weather heating — LP heaters | day | $450–$850 |
| WINTER | Cold weather enclosure — concrete | m² enclosed | $8–$18 |
| WINTER | Winter freeze protection — earthworks | m³ thaw | $3.50–$8.50 |
| OWNER DELAY | Equip demob + remob per event | event | $15,000–$65,000 |
| OWNER DELAY | Extended project overhead | week | $12,000–$35,000 |
| OWNER DELAY | Material restocking / escalation impact | % mat | 2%–8% (>3 mo) |

14.  SME FACTORS — REGIONAL ADJUSTORS & MARKUPS

14.1  Regional Adjustors (Canada 2026)

Apply the regional adjustor to the direct unit rate (after design growth). The adjustor captures regional labour market premia, material logistics, remoteness, and CBA / union density. Baseline is Manitoba / Saskatchewan = 1.00–1.08.

| Region | Low | High |
| --- | --- | --- |
| Ontario (Greater Toronto / Ottawa) | 1.05 | 1.15 |
| Ontario (Northern — Thunder Bay / Sudbury) | 1.02 | 1.10 |
| Quebec (Montreal) | 1.03 | 1.12 |
| Quebec (Northern — Chibougamau / James Bay) | 1.08 | 1.22 |
| Manitoba / Saskatchewan | 1.00 | 1.08 |
| Alberta (Edmonton / Calgary) | 1.05 | 1.18 |
| Alberta (Oil Sands / Fort McMurray) | 1.15 | 1.35 |
| British Columbia (Metro Vancouver) | 1.10 | 1.20 |
| British Columbia (Interior / Northern) | 1.15 | 1.30 |
| Yukon / NWT / Nunavut | 1.30 | 1.55 |
| Winter construction premium — all Canada | 10% | 25% |

14.2  Indirect / GC Markup Reference

| Item | Low | High | Notes |
| --- | --- | --- | --- |
| Mob/demob major earthwork fleet (% of equip) | 2% | 5% | Or flat LS per fleet assembly |
| Mob/demob RT crane 60T | $4,000 | $8,000 | Flat rate per mob |
| Mob/demob crawler crane 150T | $25,000 | $55,000 | Incl. partial disassembly |
| Camp/LOA markup on direct labour | 8% | 12% | Add for remote sites |
| Small tools and consumables on direct labour | 2.5% | 4% | Blades, hoses, bits, PPE |
| Supervision markup on direct labour | 8% | 12% | Foreman + super ratio |
| Contractor distributable (CDI) on direct cost | 6% | 10% | Temp facilities, insurance, site admin |

15.  CONTRACTOR BID COST STRUCTURE — 6-LAYER MARKUP MODEL

All contractor bids in this manual are composed of six stacked cost layers. The first layer (Direct Field Costs) is built up from the Schedule of Rates (Section 8); the remaining five layers apply % markups in the following sequence:

| Layer | Scope | Low (% of direct) | High (% of direct) |
| --- | --- | --- | --- |
| 1 — Direct Field Costs | Unit rates × MTO quantities | — | 100% (basis) |
| 2 — Contractor Field Indirects (CDI) | Temp facilities, supervision, small tools, QC, environmental, camp | 12% | 18% |
| 3 — Company Overhead | Bid & proposal costs, warranty, head office allocation | 6% | 12% |
| 4 — Bonding & Insurance | Performance bond, L&M bond, CGL, WCB, Builder's Risk | 2% | 4% |
| 5 — Contingency & Risk | Ground conditions, weather, escalation, subcontractor default | 8% | 15% |
| 6 — Contractor Profit | Profit / fee — varies by risk and competitive position | 8% | 15% |

Total bid = Direct + CDI + OH + Bond/Ins + Contingency + Profit. Sense-check the total against the unit-rate floor/ceiling table in Section 10. For mid-size mining civil projects (~$50M direct), total OH + profit typically falls in the 14–22% range — values outside this band warrant review.

16.  MOBILIZATION & DEMOBILIZATION LOGIC

Mob/demob is typically priced as a separate lump-sum line, not absorbed in unit rates. For remote / fly-in sites, add freight allowance. For multi-phase work, charge re-mob per phase. Sheet 13 (Standby & Schedule) handles owner-caused re-mob.

| Category | Asset / Activity | Basis | 2026 Range (CAD) |
| --- | --- | --- | --- |
| Earthwork fleet | Major earthwork fleet mob/demob | % of equip value or flat LS | 2%–5% |
| Earthwork fleet | Heavy haul move per low-bed trip | Per round-trip | $1,800–$3,500 |
| Earthwork fleet | Off-road haul truck (40–100T) move | Per unit / round-trip | $8,000–$18,000 |
| Cranes | Rough terrain crane RT 60T | Flat per mob | $4,000–$8,000 |
| Cranes | Lattice boom crawler 150T | Flat per mob (incl. disassembly) | $25,000–$55,000 |
| Camps | Camp setup — fly-in remote (40-bed) | LS | $250,000–$500,000 |
| Camps | Camp setup — drive-in (40-bed) | LS | $120,000–$220,000 |
| Specialty subs | HDPE liner sub (incl. CQA crew) | LS | $25,000–$60,000 |
| Specialty subs | Blasting sub (drill + powder magazine) | LS | $35,000–$90,000 |
| Specialty subs | Aggregate crushing plant | LS | $150,000–$400,000 |
| Insurance / WCB | Provincial registration + WCB account | LS | $5,000–$15,000 |

17.  CONSTRUCTABILITY & EXECUTION ASSUMPTIONS  [TEMPLATE]

This section captures the standing assumptions that frame each estimate. Populate per project — the headings below are mandatory; the example detail is illustrative.

17.1  Work Calendar

Site works 10-hr shift, 14-on / 7-off (FIFO) OR 4-on / 3-off (drive-in)

Effective hours per shift after breaks & travel: 8.5–9.0 productive hr

Winter weather window (no work): Nov–Mar productivity factor 0.70–0.85

Spring break-up moratorium (haul road restrictions): early Apr to mid-May

17.2  Access & Logistics

Primary access road condition (paved / gravel / seasonal) and weight rating

Fly-in vs drive-in — confirm chartered air freight cost & frequency

Material laydown sufficient for 60–90 days inventory at site

Fuel resupply schedule — confirm tanker turnaround and on-site storage capacity

17.3  Sequencing

Earthworks completion before liner install (no traffic post-liner)

Concrete cure times: 7 days form-strip; 28 days full strength; cold weather double

Steel erection cannot proceed until anchor bolts surveyed and accepted

Culvert installs during low-flow window per provincial fisheries authorization

17.4  Geotechnical

Bedrock encountered at depth X m — drill+blast assumption from elevation Y

Water table at depth X m — dewatering required for excavations deeper than Y m

Acid-generating waste rock requires segregation and encapsulation (geomembrane base)

17.5  Environmental

Fish habitat compensation work in Year 1 — site-specific permits required

SWPPP / ESCP plan controlling discharge to receiving water; weekly inspection minimum

Wildlife protocol (bear / caribou / grizzly) — daily site clearance

17.6  Construction Methods

Roll-on / roll-off compaction at 95% Std Proctor; 98% for process pads

Concrete supplied from on-site batch plant (if vol >2,000 m³) else ready-mix from X km

Aggregate supplied from on-site quarry/crusher (if vol >50,000 t) else from X km

Blasting confined per pattern; pre-blast survey for structures within 500m radius

17.7  Interface

Owner-supplied items (e.g. process plant equipment)

Existing facility tie-ins coordinated during scheduled outage windows

17.8  Labour / IR

Open shop / CLAC / Building Trades — confirm market and CBA obligations

Indigenous community engagement commitment — % local hire / IBA obligations

17.9  HSE

Site induction 4 hr per worker; site-specific safety standards apply

Fire watch protocol for hot work; permit-to-work system in operation

Critical lifts >75% chart capacity require lift plan + engineer approval

17.10 Productivity

Apply 0.85–0.95 productivity factor for first 4 weeks of project (learning curve)

Confined working areas: derate output by 10–30% depending on access

17.11 Quality

All concrete pours: nuclear density + 4-cyl set per pour

All HDPE liner seams: 100% non-destructive (spark / vacuum) + destructive sample 1/150 m

18.  SCOPE INCLUSIONS, EXCLUSIONS & CLARIFICATIONS  [TEMPLATE]

The following register defines a typical contractor scope position. Populate INCLUDED / EXCLUDED / CLARIFY in each row per project. This register travels with the bid and is referenced in the contract documents.

| Discipline | Item | Status |
| --- | --- | --- |
| EARTHWORKS | Mass excavation common soil | INCLUDED |
| EARTHWORKS | Rock excavation including drill & blast | INCLUDED |
| EARTHWORKS | Removal of contaminated soil | EXCLUDED |
| EARTHWORKS | Temporary site dewatering | CLARIFY |
| WATER MGMT | Permanent stormwater pond construction | INCLUDED |
| WATER MGMT | Operating sediment treatment chemicals | EXCLUDED |
| ROADS | Haul road sub-base + surface course | INCLUDED |
| ROADS | Permanent asphalt paving | CLARIFY |
| WRSA/TMF | TMF embankment construction Zones A, B, C | INCLUDED |
| WRSA/TMF | HDPE 2mm liner with CQA | INCLUDED |
| WRSA/TMF | Dam Safety Officer (DSO) services | EXCLUDED |
| DRAINAGE | CSP culverts up to 1200mm diameter | INCLUDED |
| DRAINAGE | Precast box / arch culverts > 1500mm | CLARIFY |
| CONCRETE | Cast-in-place foundations, walls, footings | INCLUDED |
| CONCRETE | Precast concrete (process plant) | EXCLUDED |
| STEEL | Building enclosures + equipment platforms | INCLUDED |
| STEEL | Process plant structural steel | EXCLUDED |
| GEOSYNTHETICS | HDPE liner systems (TMF, ponds, closure) | INCLUDED |
| GEOSYNTHETICS | Geomembrane CQA Engineer of Record | EXCLUDED |
| BLASTING | Drill, blast, clear of rock excavation | INCLUDED |
| BLASTING | Pre-blast condition surveys | INCLUDED |
| BURIED SVCS | Site potable water, sewer, process water | INCLUDED |
| BURIED SVCS | Electrical / instrumentation underground | EXCLUDED |
| FENCING | Site perimeter chain link + wildlife excl. | INCLUDED |
| FENCING | Process plant area security fencing | EXCLUDED |
| CLOSURE | Final cover system + topsoil + seeding | INCLUDED |
| CLOSURE | Long-term water treatment infrastructure | EXCLUDED |
| INDIRECTS | Site offices, lunchrooms, dryrooms | INCLUDED |
| INDIRECTS | Camp accommodation (incl. food) | CLARIFY |
| INDIRECTS | Owner inspection / EPCM offices | EXCLUDED |
| PERMITS | Routine construction permits | INCLUDED |
| PERMITS | Environmental authorization (EA, water license) | EXCLUDED |
| PERMITS | Provincial blasting permits, magazine licenses | INCLUDED |
| WARRANTY | 12-month warranty | INCLUDED |
| WARRANTY | Extended warranty beyond 12 months | EXCLUDED |

19.  BID LEVELING — TENDER COMPARISON FRAMEWORK  [TEMPLATE]

Use a side-by-side worksheet (per the companion Excel sheet '19 Bid Leveling') to compare bidder pricing against the SME benchmark. Convert each bidder's Form of Tender into a common UOM before comparison. Flag any item more than ±20% from the benchmark for clarification. Apply Section 10 floor/ceiling tests as hard out-of-range triggers.

19.1  Process

1) Common UOM normalization — strip lump sums, convert per-unit, align UOM.

2) Build the comparison table: Item | Qty | Bidder A | Bidder B | Bidder C | SME Benchmark.

3) Compute variance % vs benchmark for each bidder line.

4) Aggregate top 10 deviation items by absolute $ — these drive total bid difference.

5) Compile clarification / deviation log per bidder; request written response.

6) Re-level after clarifications: this is the 'normalized bid' that goes forward to commercial evaluation.

7) Run sense-check: bidder total ÷ direct quantity ($/m³ aggregate) against Section 10 ranges.

19.2  Deviation Categories

Typical sources of bid deviation: missing inclusions, different productivity assumption, different supplier source (especially steel/rebar after CBSA), regional adjustor misapplication, unbalanced bidding (front-loaded mobilization), and exclusion of CQA, surveys, or testing.

20.  CHANGE ORDER PRICING METHODOLOGIES

Five methodologies are recognized for pricing a change. The methodology used should be agreed with the Contract Administrator at project start.

| Method | When to Use | Build-Up |
| --- | --- | --- |
| Unit-rate based | Quantum well-defined; existing rate covers scope | Qty × rate × (1+DG) |
| Time & Materials | Scope uncertain or schedule-critical; no firm quantum | LEM hr × $/hr + Mat × (1+wastage) + Sub × (1+markup) + OH% |
| Lump-sum quotation | Discrete, well-defined; firm quote possible | Direct + Indirect 10–15% + OH+P 10–20% |
| Negotiated rates | Recurring change category | Pre-agreed rate schedule × Qty |
| Force account | Disputed scope; owner directs work pending resolution | T&M as above + auditable records |

20.1  Standard Markup Stack (CCDC 2 GC 6.2.4)

| Layer | Element | % Range | Apply To |
| --- | --- | --- | --- |
| 1 | Direct labour + equip + material | 100% | Cost of work |
| 2 | Contractor field overhead | 8–12% | Direct labour |
| 3 | Head office overhead | 5–10% | Total direct + CFO |
| 4 | Contractor profit / fee | 8–15% | Total direct + OH |
| 5 | Bond + insurance adjustment | 1.5–3% | Total contract increase |
| 6 | Sub-tier markup (flow-through subs) | 5–10% | Sub price |

Daily T&M sheets must be co-signed within 48 hours of work performed. Lump-sum change quotations must include itemised breakdown of LEMSC + indirect + OH+P. Time-impact analysis is required if the change affects critical path (CCDC 2 GC 6.5).

21.  PROJECT ESTIMATE ROLL-UP TEMPLATE  [TEMPLATE]

Roll-up format mirroring the 6-layer bid model. Populate the Direct field cost lines from MTO × unit rate (Section 8). Apply markups within the bands shown in Section 15. Apply the regional adjustor (Section 14) to direct lines before summing if site is outside the MB/SK baseline. The live formulas are in the companion Excel sheet '21 Project Roll-Up'.

| Layer | Formula |
| --- | --- |
| 1 — DIRECT FIELD COSTS | Σ Earthworks + WaterMgmt + Roads + WRSA + Drainage + Concrete + Steel + Geosynth + Blast + Buried + Fencing + Dewater + Closure |
| 2 — CONTRACTOR FIELD INDIRECTS | = Direct × CDI% (typ. 12-18%) |
| 3 — COMPANY OVERHEAD | = Direct × OH% (typ. 6-12%) |
| 4 — BONDING & INSURANCE | = (Direct + CDI + OH) × B+I% (typ. 2-4%) |
| 5 — CONTINGENCY & RISK | = Direct × Cont.% (typ. 8-15%) |
| 6 — CONTRACTOR PROFIT | = (Direct + CDI + OH + B+I + Cont.) × Profit% (typ. 8-15%) |
| TOTAL BID | = Σ of layers 1-6 |

22.  RISK & CONTINGENCY REGISTER  [TEMPLATE]

Typical risk categories for Canadian mining heavy civil projects with illustrative likelihood / impact ranking and mitigation/allocation guidance. Total cost-weighted exposure drives the contingency carry in Section 15 Layer 5.

| ID | Cat. | Description | L (1-5) | I (1-5) | Mitigation / Allocation |
| --- | --- | --- | --- | --- | --- |
| R-01 | Geotechnical | Unforeseen rock below estimated quantity | 4 | 4 | 3-8% earthworks contingency; rate adjustment per CCDC GC 6.4 |
| R-02 | Geotechnical | Acid-generating waste rock encountered | 3 | 5 | Owner-led environmental mgmt; 1-3% allowance |
| R-03 | Weather | Extended winter shutdown beyond plan | 4 | 3 | 2-5% weather contingency; review work calendar |
| R-04 | Market/Escalation | Diesel >15% above bid basis | 3 | 3 | 3-8% materials escalation; index fuel surcharge |
| R-05 | Market/Tariff | CBSA 25% surtax extended on steel/rebar | 3 | 3 | Source Canadian/US; 5-10% on steel |
| R-06 | Subcontractor | Specialty sub default or delay | 2 | 4 | 1-3% sub default contingency; pre-qualify alts |
| R-07 | Permits | Environmental permit delay for fish habitat | 3 | 4 | Phase work; engage authority early |
| R-08 | Labour | Skilled trades shortage (Electrician/Welder) | 4 | 3 | Lock supply via early subs; 5% labour premium |
| R-09 | Indigenous | IBA / community engagement delay | 3 | 4 | Engage early; capture in schedule |
| R-10 | Owner | Owner-supplied materials late | 3 | 4 | Daily T&M / standby for owner-caused delay |
| R-11 | Quality/Rework | HDPE liner CQA failures | 2 | 3 | Pre-qualify installer; third-party CQA |
| R-12 | HSE | Major incident causing site stop-work | 1 | 5 | Strong safety culture; carry incident allowance |

23.  GLOSSARY & ABBREVIATIONS

| Term | Definition |
| --- | --- |
| AACE | Association for the Advancement of Cost Engineering International |
| AACE 18R-97 | Cost Estimate Classification System — process industries |
| AFE | Authorization for Expenditure — owner approval at sanction |
| BCPI | Building Construction Price Index (Statistics Canada) |
| CAD | Canadian Dollar |
| CBSA | Canada Border Services Agency — administers steel/rebar surtax |
| CDI | Contractor Distributable Indirects (site indirects) |
| CGL | Commercial General Liability insurance |
| CLAC | Christian Labour Association of Canada (open shop) |
| CCDC | Canadian Construction Documents Committee (CCDC 2 = stipulated sum) |
| CQA | Construction Quality Assurance (typically third-party) |
| DR-11 / DR-17 | HDPE pipe Dimension Ratio (wall thickness class) |
| EHT | Employer Health Tax (Ontario / BC) |
| EPCM | Engineering, Procurement and Construction Management |
| ESC | Erosion & Sediment Control |
| FID | Final Investment Decision |
| FIFO | Fly-in / Fly-out (typically 14-on / 7-off rotation) |
| HDPE | High-Density Polyethylene |
| HSE | Health, Safety, Environment |
| IBA | Impact Benefit Agreement (Indigenous communities) |
| IFC | Issued For Construction (drawing status) |
| LOA | Living Out Allowance (per-diem) for non-camp remote work |
| MTO | Material Take-Off (quantity survey from drawings) |
| NCSO | National Construction Safety Officer (Canadian certification) |
| NRCan | Natural Resources Canada |
| ROM | Rough Order of Magnitude (Class 5/4 estimate) |
| SoR | Schedule of Rates |
| SWM | Stormwater Management |
| SWPPP | Stormwater Pollution Prevention Plan |
| TMF | Tailings Management Facility |
| WBS | Work Breakdown Structure |
| WCB / WSIB | Workers' Compensation Board / Ontario WSIB |
| WRSA | Waste Rock Storage Area |
| S+I | Supply + Install |
| S+F+P | Supply + Form + Pour |

24.  SOURCES & REFERENCES

| Category | Reference |
| --- | --- |
| STANDARDS | AACE Recommended Practice 18R-97 — Cost Estimate Classification System |
| STANDARDS | ASTM D698 — Standard Proctor; ASTM D1557 — Modified Proctor |
| STANDARDS | ASTM D4439 — Geosynthetics terminology |
| STANDARDS | CCDC 2 — Stipulated Sum Contract |
| STANDARDS | Canadian Dam Association Dam Safety Guidelines |
| INDICES | Statistics Canada — Building Construction Price Index (BCPI), quarterly |
| INDICES | NRCan — Diesel Pricing, weekly |
| INDICES | Bank of Canada — USD/CAD exchange rate |
| AUTHORITIES | CBSA — Notices 24-26 and 25-22 (steel / rebar surtax) |
| AUTHORITIES | Provincial WCB / WSIB / CNESST / WorkSafeBC / WorkplaceNL |
| AUTHORITIES | NS Energy Regulatory Board — Atlantic diesel price |
| INTERNAL | Rev G workbook — RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 (Contractor Bid Tool) |
| INTERNAL | Rev E workbook — RMM-CIVIL-CANADA-2026-REV0 (EPCM Benchmark Estimator) |
| INTERNAL | Ausenco go-by Q2-2020 (Senior PD / EPCM reference) |
| SUPPLIERS | Armtec — CSP culvert and flow guard pricing (Dec-2025) |
| SUPPLIERS | Various HDPE pipe suppliers — Jan-2026 quotes +15% install factor |
| BENCHMARKS | SME benchmark observations 2024-2026 — Canadian mining civil contracts |
| METHODOLOGY | Standard industry practice — contractor markup stack and CDI percentages |
| METHODOLOGY | CCDC 2 GC 6.2 / 6.4 / 6.5 — change order provisions |

Public-Tender Data Sources (Rev 2 — for benchmark cross-reference)

| Category | Reference |
| --- | --- |
| PUBLIC TENDER | Alberta Transportation — Unit Price Averages 2026 (XLSX) — weighted avg of 3 low bids, tenders May 1, 2024 – Sep 30, 2025 |
| PUBLIC TENDER | Alberta Transportation — Unit Prices and Cost Adjustments — https://www.alberta.ca/unit-prices-and-cost-adjustments |
| PUBLIC TENDER | BC Road Builders — Tender Report 2026 awards — https://www.roadbuilders.bc.ca/tender-report/ |
| PUBLIC TENDER | CanadaBuys (federal procurement portal) — https://canadabuys.canada.ca/ |
| PUBLIC TENDER | SaskTenders (Saskatchewan public sector tendering) — https://sasktenders.ca/ |
| PUBLIC TENDER | Manitoba Infrastructure — Tendering & Contracts (bid results) — https://www.gov.mb.ca/mti/contracts/bidresults.html |
| PUBLIC TENDER | MERX (Saskatchewan, Manitoba and federal opportunities) — https://www.merx.com/ |
| MINING DATA | Natural Resources Canada — Mining Capital Expenditures |
| MINING DATA | SEDAR+ — NI 43-101 Technical Reports (filed Feasibility Studies for comparable projects) |

25.  REAL MARKET BENCHMARK — SME RANGES vs PUBLIC TENDER ACTUALS  [Rev 2]

This section cross-references the SME unit-rate ranges in this manual against the highest-quality public-tender benchmark dataset available in Canada: Alberta Transportation's 2026 Unit Price Averages (UPA), which publishes the weighted average of the three lowest bids on highway/civil tenders awarded between May 1, 2024 and September 30, 2025. The Excel workbook (sheet '25 Real Market Benchmark') contains the full table with colour-coded variance flags; this section summarises the conclusions.

25.1  Top-Level Read

Where AB UPA falls WITHIN the SME floor/ceiling: the SME range is well-calibrated to real Canadian public-tender market. Use confidently.

Where AB UPA falls BELOW the SME floor (most common case): SME range is conservative — typically because mining-site SME includes additional camp / LOA, remote indirects, mining-spec QA, and risk premium. SME floor is justified for remote mining; consider the lower bound for accessible drive-in projects.

Where AB UPA falls ABOVE the SME ceiling: typically the AB UPA item has additional specialty scope (bridge-grade quarry rock, specialty steel pipe, deck overlay) — not directly comparable. Review scope inclusion.

AB UPA is HIGHWAY tender data, not mining tender data. It is the closest available public benchmark for civil unit rates in Canada. NI 43-101 filings have aggregate capex but rarely line-item unit rates publicly. Detailed mining-tender unit rates are commercial-in-confidence.

To adapt AB UPA to a mining-site context, add: camp / LOA (Section 5 rows O2/O3) if remote; regional adjustor (Section 14) if outside Alberta; mining-spec QC and indirects.

25.2  Cross-Reference Highlights (Selected)

| Item | AB UPA 2026 ($) | SME Range (CAD) | Verdict |
| --- | --- | --- | --- |
| Common excavation balanced cut/fill (G225) | $8.20 / m³ | $24–$32 / m³ (C-10-002) | AB lower — no haul. With haul to 5-10 km adds $0.44/m³·km → $10–$13. Mining indirects make up the difference. |
| Excavation loaded to truck (G248) + haul (G249) | $15.22 + $0.44/km | $24–$32 / m³ (C-10-002) | AB excav+load+haul at 5 km = $17.42 / m³. WITHIN SME at the floor. |
| Borrow excavation contractor-supplied (G236) | $24.40 / m³ | $22–$45 / m³ (C-40-002) | WITHIN ✓ — strong calibration |
| Granular base course (B282) | $34.27 / tonne | $105–$135 / m³ (C-10-009) | At 2.0 t/m³ AB = $68.54/m³ vs SME $105-$135. SME higher — mining-site haul and OH. |
| CSP culvert 900 mm S+I (D430) | $720.58 / m | $680–$880 / m (C-50-003) | WITHIN ✓ |
| CSP culvert 1000 mm S+I (D431) | $824.24 / m | $800–$1,020 / m (C-50-004) | WITHIN ✓ |
| Heavy rock riprap Class 1 (F500) | $313.41 / m³ | $65–$100 / m³ (C-20-002) | AB much higher — bridge-spec quarried + sized rock. SME is mining-site bulk rip-rap. Both valid in their domain. |
| Concrete Class HPC (F841) | $2,692.30 / m³ | $2,200–$3,500 / m³ (C-60-002) | WITHIN ✓ |
| Concrete Class C footings (F834) | $1,951.01 / m³ | $2,200–$3,500 / m³ (C-60-002) | AB just below SME floor. SME mining-site indirects + cold weather pour included. |
| Asphalt Superpave (Q998) | $147.89 / tonne | $45–$62 / m² (C-30-005) | At 100mm × 2.3 t/m³ AB = $34/m². SME $45-$62 is for thinner 50mm HL3 — mining-site SME higher with indirects. |
| Erosion silt fence (E435) | $15.16 / m | $18–$28 / m (C-20-008) | AB $15.16 just below SME floor — CLOSE WITHIN. |
| Non-woven geotextile (E452) | $2.82 / m² | $3–$6 / m² (C-20-007) | AB just below SME floor (~6%) — WITHIN tolerance. |
| Concrete curb (X320) | $170.32 / m | $185–$265 / m (B-04-003) | AB just below SME floor — CLOSE WITHIN. |
| Pre-cast street light base (U122) | $3,480.95 / ea | $1,850–$3,500 / ea (EL-70-003) | WITHIN ✓ |

25.3  Conclusion

The SME ranges in this manual are well-calibrated against real Canadian public-tender data, with reasonable upward bias to reflect mining-site indirects, remoteness, and risk premium relative to accessible highway projects. Where the SME range and the AB UPA disagree by more than 30%, the discrepancy is almost always explained by scope difference (e.g. bridge-grade rip-rap vs mining-site bulk rip-rap) or by mining-site indirect / camp / haul-distance loading. Use the SME range as the working benchmark; use AB UPA as a sanity check to question whether a project-specific quote is contaminated by scope creep or by a misapplied indirect.

— END OF DOCUMENT —

RMM-CIVIL-CANADA-2026-MANUAL-REV2 | Rev 2 — End-to-End + Real Market Benchmark | Q2-2026