## 00 Cover
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
DOCUMENT TITLE | Rick Miller SME Standard — Canada 2026 Mining Heavy Civil Estimating Manual & Rate Library
DOCUMENT NUMBER | RMM-CIVIL-CANADA-2026-MANUAL-REV1
REVISION | Rev 1 — Consolidated
PREPARED BY | Rick Miller, Senior Project Director / EPCM
PURPOSE | Provide an internally-maintained, contractor-grade Schedule of Rates and bid-support package for Canadian mining heavy civil projects. Supports budgetary estimates (Class 5/4), feasibility estimates (Class 3), AFE/sanction estimates (Class 2), tender support, contractor benchmarking, bid evaluation, change pricing and unit-rate validation.
BASE CURRENCY | Canadian Dollar (CAD) ¦ Q2 2026
ESTIMATE CLASS — BASIS | AACE 18R-97 Class 3 Benchmark (±20% / +30%); Class 2 and Class 1 conversion factors provided in Section 14
ESCALATION BASIS | Ausenco go-by Q2-2020 escalated x1.25 (BCPI cumulative midpoint) to Q2-2026
DIESEL — ATLANTIC | $2.13–$2.21 / L (NS ERB May 2026)
DIESEL — ALBERTA | $1.68–$1.78 / L (NRCan May 2026)
DIESEL — BC METRO | $2.15–$2.35 / L (NRCan May 2026)
USD/CAD | 1.36 – 1.37 (Bank of Canada May 2026)
CBSA TARIFF | 25% surtax — Chinese structural steel and rebar (CBSA Notices 24-26 / 25-22, Oct 2024 ongoing)
DATA SOURCE | Consolidated from RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 (Contractor Bid Tool) and RMM-CIVIL-CANADA-2026-REV0 (EPCM Benchmark Estimator) — both authored by Rick Miller
INTENDED USERS | Contractor estimators, EPCM cost engineers, owner cost teams, bid evaluators, project controls
INTENDED USE | Internal reference / bid-support / sense-check tool. Not a public quotation. Do not issue cells as fixed pricing without project-specific validation.
WORKBOOK CELL COLOUR LEGEND
White / no shading | Reference data extracted directly from the Rev G and Rev E source workbooks (baseline).
Light yellow (italic grey text) | [TEMPLATE] section — industry-standard framework provided as scaffolding to be populated per project.
Light blue | [INPUT] cell — user enters a project-specific quantity, rate, or factor.
Light green | [CALCULATED] cell — driven by formula from inputs; do not overwrite.
Navy bar | Section or sub-section header.

## 01 Contents
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
# | Section | Description
00 | Cover | Document control, basis, currency, source workbooks, cell legend.
01 | Contents | Tab index and navigation map (this sheet).
02 | Executive Summary | One-page summary of the package, intended use, and key benchmarks.
03 | Estimating Standards | AACE 18R-97 classes, accuracy ranges, design growth, escalation, exchange basis.
04 | Crew Compositions | 12 crew codes (B1–N1), 2020 vs 2026 escalated all-in rates, crew sizing.
05 | Labour Rates | 27 positions fully burdened, Camp/LOA flags, classification, 2026 low/high.
06 | Equipment Rates | 30 fleet items, fully operated rate, fuel burn, mob/demob, availability.
07 | Equipment Spreads | [TEMPLATE] Typical spreads by scope (mass earth, fill placement, road, liner).
08 | Schedule of Rates — Master | ~120 line-item consolidated SoR (Heavy Civil + Contractor scope) with build-up columns.
09 | Unit Rate Build-Up Calculator | [TEMPLATE] Working calculator — assemble new unit rates from crew × MH + equip + mat + sub + indirects.
10 | Bid Screening Floors & Ceilings | 29 benchmark $/m3, $/m2, $/m sense-checks for tender evaluation.
11 | Contractor Indirects (CDI) | Field office, PM staff, QC, environmental, mob/demob, head office allocation.
12 | Bonding & Insurance | Surety, CGL, WCB by province, Builder's Risk, contractor equipment floater.
13 | Standby & Schedule | Equipment & labour standby, OT/shift premiums, winter costs, owner-caused delay.
14 | SME Factors | Design growth (Class 4–1), wastage, regional adjustors (11 zones), escalation, accuracy.
15 | Bid Cost Structure (Markup Stack) | 6-layer markup model: Direct → CDI → OH → Bond/Ins → Contingency → Profit.
16 | Mob / Demob Logic | Equipment-specific mob/demob rules, fleet vs single-piece, remote site logic.
17 | Constructability Assumptions | [TEMPLATE] Execution philosophy, sequencing, access, productivity, work calendar.
18 | Scope Inclusions / Exclusions | [TEMPLATE] Discipline-by-discipline inclusion / exclusion / clarification register.
19 | Bid Leveling Comparison | [TEMPLATE] Side-by-side tender evaluation worksheet (3 bidders + benchmark).
20 | Change Order Pricing | [TEMPLATE] CCDC-style change order build-up: T&M, unit-rate, lump-sum methodologies.
21 | Project Estimate Roll-Up | [TEMPLATE] WBS roll-up sheet — direct + CDI + OH + bond + contingency + profit = total bid.
22 | Risk & Contingency Register | [TEMPLATE] Project risk log with cost/schedule impact and contingency allocation.
23 | Glossary & Abbreviations | Terms, acronyms, units of measure used throughout the manual.
24 | Sources & References | AACE, BCPI, NRCan, CBSA, WCB sources, supplier quotes, internal benchmarks.

## 02 Executive Summary
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
PURPOSE
This manual is a consolidated, internally-maintained estimating standard and rate library for Canadian mining heavy civil work. It is designed to be used by contractors, EPCMs, and owners for budgetary pricing, feasibility-class estimates, tender support, bid evaluation, and change pricing.
WHAT IS INCLUDED — BASELINE (FROM SOURCE WORKBOOKS)
• 12 crew codes (B1–N1) with 2020-to-2026 escalation; • 27 fully-burdened labour positions; • 30 fully-operated equipment items with fuel burn and mob/demob flags; • ~78 Heavy Civil unit rates across 8 sections (earthworks → closure); • ~22 contractor-scope unit rates (blasting → crushing); • 29 bid-screening floors/ceilings; • 19 bonding & insurance lines (WCB by province); • 25 overhead lines; • 19 standby & schedule items; • SME factors: design growth, wastage, 10 regional zones, escalation, AACE accuracy ranges.
WHAT IS INCLUDED — FRAMEWORK TEMPLATES (AUTHORED HERE)
Scaffolding sections clearly marked [TEMPLATE]: • Equipment spreads; • Unit rate build-up calculator; • Constructability & execution assumptions; • Scope inclusions/exclusions register; • Bid leveling comparison; • Change order pricing; • Project estimate roll-up; • Risk & contingency register. These are blank/sample structures — populate per project.
INTENDED ESTIMATE CLASSES
Class 5/4 (screening / budgetary) — use floor/ceiling ranges and apply +15–20% design growth. Class 3 (feasibility / budget) — THIS DOCUMENT'S BASELINE. Apply +10–15% design growth. Class 2 (sanction / AFE / pre-FID) — use mid-range rates with +5–10% design growth. Class 1 (tender check / detailed) — use low end of range or project-specific quotes; +2–5% design growth.
HOW TO USE
1) Identify scope and WBS items. 2) Pull unit rates from Sheet 08 (Master SoR). 3) Apply quantity × rate. 4) Add Contractor Indirects (Sheet 11) and apply markup stack (Sheet 15). 5) Apply regional adjustor (Sheet 14). 6) Sense-check against Sheet 10 floors/ceilings. 7) Roll up in Sheet 21.
KEY 2026 BENCHMARKS
Mass earthworks rock (blasted): $55–$120/m3. Engineered fill: $22–$45/m3. Haul road full build: $65–$120/m2. TMF embankment Zone A/B: $22–$45/m3. HDPE 2mm liner (S+I+CQA): $28–$55/m2. CSP culvert 1200mm: $1,000–$1,600/m. Concrete wall/grade beam: $2,500–$3,200/m3. Rebar (S+I): $4,000–$6,500/tonne (CBSA 25% surtax exposure). Performance bond medium contract: 1.0–1.8% of contract.
REGIONAL ADJUSTOR RANGE
MB/SK 1.00–1.08 (baseline) → Yukon/NWT/Nunavut 1.30–1.55 (extreme remote). Winter premium: 10–25% all Canada.
DO NOT USE FOR
• Public/fixed quotations without project-specific validation; • Lump-sum tender submission without supplier confirmation; • Class 1 detailed estimates without complete IFC drawings and supplier RFQs; • Projects outside Canadian mining heavy civil scope without re-baselining.

## 03 Estimating Standards
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
AACE 18R-97 — ESTIMATE CLASSIFICATION FRAMEWORK (mining heavy civil interpretation)
AACE Class | Project Stage | Definition Level (% project def.) | Methodology | Accuracy Low | Accuracy High | Typical Use
Class 5 | Concept screening | 0%–2% | Stochastic / parametric / per-unit-capacity factors | -50% | +100% | Order of magnitude; screening; ROM
Class 4 | Pre-feasibility / study | 1%–15% | Mostly stochastic; equipment factored; some unit rates | -30% | +50% | Concept evaluation; site selection
Class 3 | Feasibility / budget | 10%–40% | Semi-detailed; mostly unit rates; MTOs from PFD/general arr. | -20% | +30% | Budget authorization; this baseline
Class 2 | Sanction / AFE | 30%–75% | Detailed unit rates; near-complete MTOs; firm quotes on long-leads | -10% | +20% | FID / sanction approval
Class 1 | Tender / check | 65%–100% | Detailed; IFC drawings; firm RFQ pricing; full crew/equip build-up | -5% | +10% | Tender bid; check estimate
DESIGN GROWTH ALLOWANCES (by class) — SOURCE: SME Factors tab
Class | Discipline / Scope | Design Growth Low | Design Growth High | Notes
Class 5/4 | Earthworks / civil | 15% | 20% | Limited geotech; preliminary drawings
Class 3 | Earthworks / civil (this baseline) | 10% | 15% | Standard level for feasibility / budget
Class 2 | Earthworks / civil | 5% | 10% | Pre-FID; IFC packages near complete
Class 1 | Earthworks / civil | 2% | 5% | Full detailed design completed
All | Concrete works (additive) | +5% | +5% | Add 5% incremental to earthworks DG
WASTAGE FACTORS — SOURCE: SME Factors tab
Material | Wastage Low | Wastage High | Basis
Granular aggregate | 5% | 10% | Rounding + delivery variance
Concrete (formed) | 8% | 12% | Pump waste + edge loss
Rebar | 3% | 7% | Cutting waste; depends on bar size and complexity
Geomembrane liner | 5% | 10% | Panel overlaps + anchor trench + QA sampling
Geotextile | 10% | 15% | ASTM D4439 6-inch overlap minimum
ESCALATION & MARKET BASIS — Q2-2026 — SOURCE: SME Factors tab
Item | Low | High | Basis / Source
Go-by Q2-2020 → Q2-2026 cumulative escalation factor | x1.23 | x1.27 | BCPI cumulative; use x1.25 midpoint
Labour CBA escalation 2024–2026 (NL trades) | 3.5% | 5.5% | Per trade; see Sheet 05
Diesel — Nova Scotia (May 2026) | $2.13/L | $2.21/L | NS Energy Regulatory Board
Diesel — Alberta (May 2026) | $1.68/L | $1.78/L | NRCan
Diesel — BC Metro (May 2026) | $2.15/L | $2.35/L | NRCan
USD/CAD exchange rate (May 2026) | 1.36 | 1.37 | Bank of Canada
CBSA surtax — Chinese structural steel | 25% | 25% | CBSA Notices 24-26/25-22 (Oct 2024 ongoing)
CBSA surtax — Chinese rebar | 25% | 25% | Verify supplier origin certificate

## 04 Crew Compositions
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION CREW RATES — CANADA 2026 (CAD/HR) — SOURCE: Rev E Crew Rates tab
Code | Crew Description | Avg Size | Lab. 2020 ($/hr) | Equip 2020 ($/hr) | Total 2020 ($/hr) | Esc. Factor | Lab. 2026 ($/hr) | Equip 2026 ($/hr) | Total 2026 ($/hr) | Source / Basis
B1 | Civil Works — Light (strip, grade, compact light) | 26.1 | 90.9 | 36.6 | 127.5 | x1.25 | 113.62 | 45.75 | 159.37 | Ausenco go-by Q2-2020 x1.25 BCPI
B2 | Civil Works — Medium (cut, fill, haul <2km) | 28.1 | 90.7 | 68.2 | 158.9 | x1.25 | 113.38 | 85.25 | 198.63 | Ausenco go-by Q2-2020 x1.25 BCPI
B3 | Civil Works — Heavy (mass earth, rock, blast) | 37.7 | 90.2 | 71.1 | 161.3 | x1.25 | 112.75 | 88.88 | 201.63 | Ausenco go-by Q2-2020 x1.25 BCPI
B4 | Civil Liner & Pipeline (HDPE, geomem, culverts) | 28.1 | 92.8 | 23.3 | 116.1 | x1.25 | 116 | 29.12 | 145.12 | Ausenco go-by Q2-2020 x1.25 BCPI
C1 | Concrete (slab, wall, pier, footing all-in) | 22.6 | 88.6 | 20.8 | 109.4 | x1.25 | 110.75 | 26 | 136.75 | Ausenco go-by Q2-2020 x1.25 BCPI
D1 | Structural Steel (erect, weld, bolt-up) | 17.6 | 91.9 | 22.2 | 114.1 | x1.25 | 114.88 | 27.75 | 142.63 | Ausenco go-by Q2-2020 x1.25 BCPI
E1 | Architectural (cladding, doors, windows) | 19.6 | 89.4 | 10.9 | 100.3 | x1.25 | 111.75 | 13.62 | 125.37 | Ausenco go-by Q2-2020 x1.25 BCPI
G1 | Mechanical Services (HVAC, plumbing, utility) | 17.65 | 95.8 | 15.5 | 111.3 | x1.25 | 119.75 | 19.38 | 139.13 | Ausenco go-by Q2-2020 x1.25 BCPI
H1 | Mechanical Equipment (install, align, grout) | 23.55 | 102.3 | 13.5 | 115.8 | x1.25 | 127.88 | 16.88 | 144.76 | Ausenco go-by Q2-2020 x1.25 BCPI
J1 | Piping | 13.7 | 95.7 | 14.8 | 110.5 | x1.25 | 119.62 | 18.5 | 138.12 | Ausenco go-by Q2-2020 x1.25 BCPI
K1 | Electrical | 10.75 | 103.4 | 14.4 | 117.8 | x1.25 | 129.25 | 18 | 147.25 | Ausenco go-by Q2-2020 x1.25 BCPI
N1 | Instrumentation | 10.35 | 106.2 | 17.6 | 123.8 | x1.25 | 132.75 | 22 | 154.75 | Ausenco go-by Q2-2020 x1.25 BCPI
Notes: Crew rates are average all-in (labour + equipment) per crew-hour. Productivity (Prod Factor) is applied at the unit-rate level (see Sheet 08). Crew composition by trade is shown on Sheet 05 and 06 — these crews are SME averages for benchmarking, not a fixed roster.

## 05 Labour Rates
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION LABOUR RATES — CANADA 2026 FULLY BURDENED (CAD/HR) — SOURCE: Rev E Labour Rates tab
Ref | Trade / Position | Classification | 2026 Low (CAD/hr) | 2026 High (CAD/hr) | Camp/LOA | SME Notes
S1 | General Superintendent | Supervisor | 154 | 172 | LOA+Camp | All burdens+O&P. Remote mining site.
S2 | Superintendent | Supervisor | 136 | 155 | LOA+Camp
S3 | General Foreman | Supervisor | 125 | 140 | LOA+Camp
C1 | Civil Work Lead | Civil | 116 | 132 | LOA+Camp
C2 | Equip Operator — Heavy Duty (dozer/exc/grader) | Civil | 110 | 128 | LOA+Camp | D8/336/140M class. 2026 burdened.
C3 | Equip Operator — Medium Duty (loader/backhoe) | Civil | 101 | 116 | LOA+Camp | 930M/320D class
C4 | Equip Operator — Light Duty (skidsteer/roller) | Civil | 93 | 106 | LOA+Camp
C5 | Labourer — Journeyman | Civil | 82 | 95 | LOA+Camp | Base civil crew rate
C6 | Labourer — 2yr Apprentice | Civil | 73 | 84 | LOA+Camp
C7 | Labourer — 1st yr Apprentice | Civil | 64 | 74 | LOA+Camp
D1 | Driller — Journeyman (blast hole) | Civil/Blast | 93 | 108 | LOA+Camp | Licensed; Atlas/Sandvik rig
D2 | Blaster — Journeyman | Civil/Blast | 93 | 108 | LOA+Camp | Provincial certificate required
M1 | Mechanic — Heavy Duty | Mechanical | 84 | 98 | LOA+Camp | Plant/fleet mechanic
M2 | Mechanic — Medium Duty | Mechanical | 92 | 106 | LOA+Camp
T1 | Carpenter — Journeyman (formwork) | Trades | 109 | 125 | LOA+Camp
T3 | Concrete Lead | Trades | 125 | 140 | LOA+Camp
T4 | Concrete Finisher — Journeyman | Trades | 95 | 108 | LOA+Camp
T5 | Ironworker — Journeyman (rebar/structural) | Trades | 115 | 132 | LOA+Camp
T6 | Welder/Pipefitter — Journeyman | Trades | 113 | 130 | LOA+Camp
T8 | Rodman — Reinforcement Journeyman | Trades | 94 | 108 | LOA+Camp
E1 | Electrician — Journeyman | Electrical | 127 | 145 | LOA+Camp | 2026 shortage premium applied
I1 | Instrumentation Tech — Journeyman | Instrumentation | 127 | 145 | LOA+Camp
P1 | Project Engineer — Field | PM/Eng | 109 | 125 | LOA+Camp
P2 | Project Engineer — Senior Field | PM/Eng | 123 | 140 | LOA+Camp
O1 | Safety Officer (NCSO certified) | HSE | 110 | 125 | LOA+Camp | NCSO cert + site-specific induction
O2 | Camp — all-in per person/day | Indirect | 220 | 300 | Included | Bunk, food, laundry, rec. Remote mine.
O3 | LOA subsistence — non-camp | Indirect | 180 | 250 | N/A | Per-diem where camp not provided
Labour rates are fully burdened: base wage + statutory burdens (CPP, EI, EHT, vacation, stat holidays) + employer benefits + WCB (province-specific, see Sheet 12) + small tools allowance + supervision ratio. Camp/LOA is shown as an additive per-person cost; subsistence is per-diem where camp not provided. Use Sheet 12 to validate WCB rate by province before pricing.

## 06 Equipment Rates
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTION EQUIPMENT RATES — CANADA 2026 FULLY OPERATED (CAD/HR) — SOURCE: Rev E Equipment Rates tab
Cat. | Equipment | Size / Capacity | 2026 Low ($/hr) | 2026 High ($/hr) | Fuel (L/hr) | Mob/Demob | Availability | SME Notes
HT | Tandem dump truck | 18-20T | 140 | 165 | 45-65 | Required | 85% | Fully operated; Canada-wide May 2026
HT | Tri-axle dump truck | 25T | 155 | 180 | 55-75 | Required | 85%
HT | Wiggle wagon / Super B | 45T | 185 | 215 | 65-90 | Required | 80% | Field confirmed Q2-2026
HT | Off-road haul truck | 40-100T | 320 | 500 | 80-140 | Included | 85% | Komatsu/CAT; payload class dependent
EX | Hydraulic excavator | Cat 320 20-25T | 250 | 330 | 18-25 | Required | 85% | Production dig/load
EX | Hydraulic excavator | Cat 336 35-40T | 340 | 430 | 25-35 | Required | 85% | Rock + bulk earthworks
EX | Hydraulic excavator | Cat 390 50-65T | 460 | 580 | 38-50 | Required | 82% | Mass excavation
EX | Long-reach excavator | 20T 18m reach | 290 | 380 | 18-25 | Required | 82% | Pond, ditch, shoreline
DO | Track dozer | Cat D6N 17T | 250 | 320 | 20-30 | Required | 88% | Clear, rough grade, push
DO | Track dozer | Cat D8T 37T | 380 | 480 | 35-48 | Required | 88% | Production push, rip rock
DO | Track dozer | Cat D10T 58T | 520 | 650 | 50-68 | Required | 85% | Mass earthworks, stripping
GR | Motor grader | Cat 140M | 280 | 360 | 18-26 | Required | 88% | Road maint, final grade
GR | Motor grader | Cat 16M large | 360 | 450 | 22-32 | Required | 88% | Large platform grading
CP | Vib. roller single drum | Cat CS56B 12T | 200 | 270 | 15-22 | Required | 88% | 200-300mm lift
CP | Padfoot compactor | Cat CS74B 17T | 240 | 310 | 18-26 | Required | 88% | Cohesive soils
CP | Plate compactor / jumping jack | 0.5-1T | 45 | 75 | 5-8 | By truck | 90% | Trench zones, tight access
WL | Wheel loader | Cat 930M 10T | 200 | 270 | 18-26 | Required | 87% | Aggregate load, general
WL | Wheel loader | Cat 950M 16T | 250 | 320 | 22-30 | Required | 87% | General load-out
WL | Wheel loader | Cat 980M 22T | 320 | 400 | 28-38 | Required | 87% | High production
DR | Rotary drill rig | Atlas 120mm hole | 550 | 750 | 35-50 | Included | 80% | Blast hole drilling
SK | Skid steer | Cat 262D | 95 | 135 | 10-15 | By truck | 90% | Tight access, site clean
WP | Diesel submersible pump | 4-inch 150mm | 55 | 85 | 10-16 | By truck | 90% | Site dewatering
WP | Diesel submersible pump | 8-inch 200mm | 120 | 180 | 20-30 | By truck | 90% | Large dewatering
CR | Rough terrain crane | Grove RT 60T | 650 | 900 | 30-45 | Required | 80% | Lifts, precast, equip set
CR | Lattice boom crawler crane | Liebherr 150T | 1800 | 2600 | 60-90 | Included | 78% | Heavy lift
MI | Rock breaker / hyd hammer | Cat 345 + hammer | 480 | 620 | 28-40 | Required | 80% | Rock fragmentation
MI | Air compressor diesel towable | 375 cfm | 75 | 110 | 12-18 | By truck | 90% | Drill assist, pneumatics
MI | Light tower diesel | 8-10 kW | 35 | 55 | 5-8 | By truck | 95% | Nightshift / portal safety
MI | Fuel tanker site supply | 10,000L | 180 | 250 | 30-40 | Required | 90% | Incl. driver
MI | Water truck dust suppression | 10,000L | 160 | 220 | 30-40 | Required | 90% | Incl. driver
Equipment rates are fully operated (operator wage already burdened; see Sheet 05 for standalone labour). Fuel is shown in L/hr; multiply by site diesel price (Sheet 03) for fuel-cost portion. Availability % drives effective hours per shift. Mob/demob: 'Required' = additional cost per Sheet 16; 'Included' = built into hourly rate; 'By truck' = transport on flatbed at nominal cost.

## 07 Equipment Spreads
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
TYPICAL EQUIPMENT SPREADS BY SCOPE [TEMPLATE — verify against project conditions]
Scope / Operation | Spread Description | Primary Equipment | Support Equipment | Crew Code | Productivity Range | Util. | Notes
Mass earthworks — rock | Drill + blast + load + haul | 1x DR rotary, 1x EX Cat 390, 4-6x off-road 40-100T | 1x D10T, 1x water truck, 1x grader | B3 | 800-1,500 m3/shift | 75% | Rock blasted/m3; cycle <2km
Mass earthworks — common | Cut/fill/place/compact | 1x EX Cat 336, 4-6x tandem/tri-axle | 1x D8T, 1x CS56B roller, 1x water truck | B3 | 1,200-2,000 m3/shift | 80% | Engineered fill <250mm
Engineered fill placement | Lift placement and compaction | 1x EX Cat 320 or WL 950M, 2-4x tandem | 1x D6N, 1x CS74B padfoot, 1x water truck | B2 | 600-1,000 m3/shift | 82% | 300mm lift; Zone A/B; nuclear density
Haul road build | Sub-grade → surface course | 1x D8T (sub-base), 1x grader 140M (surface) | 1x CS56B roller, 1x water truck | B2 | 150-300 m/day full build | 82% | 8m wide single lane; all lifts
HDPE liner install (TMF) | Panel deploy + weld + CQA | 1x WL 930M (panel handling), 1x SK | 1x air compressor 375cfm | B4 | 1,500-3,000 m2/day | 75% | Specialty sub; CQA per project
Culvert install (≥900 mm CSP) | Trench, bed, install, backfill | 1x EX Cat 320, 1x WL 930M, 2x tandem | 1x plate compactor, 1x dewatering pump | B4 | 20-40 m/day | 75% | Cofferdam + dewatering if creek live
Buried services trenching | Trench, bed, lay, backfill | 1x EX Cat 320, 1x tandem, 1x WL 930M | 1x plate compactor, 1x trench box | B4 | 60-120 m/day | 78% | HDPE 150-200mm; depth <2.5m
Concrete pour — foundation | Form, place, pour, finish | 1x crane RT 60T (if precast/heavy form) | 1x concrete pump, 1x vibrator | C1 | 12-25 m3/day | 75% | Formed walls / grade beams
Rock support — shotcrete | Apply 50-100mm with mesh | 1x shotcrete pump, 1x EX (mesh handling) | 1x SK (mix supply) | C1 | 120-250 m2/day | 70% | Fibre or wire mesh embedded
Drill+blast rock anchors | Drill, install, grout, tension | 1x drill rig (anchor-specific), 1x EX | 1x grout plant | D1 | 8-15 anchors/day | 70% | Active tensioned 32mm strand
Buried HDPE forcemain | Trench, bed, fuse, lay, backfill | 1x EX Cat 320, 1x WL, 1x fusion machine, 1x tandem | 1x plate compactor | B4 | 80-150 m/day | 78% | Site dewatering may be required
Demolition / strip and grub | Clear, grub, stockpile | 1x D8T, 1x EX Cat 336 | 1x tandem (haul) | B3 | 0.5-1.5 ha/day | 78% | Light bush; rock/timber additive
[TEMPLATE — verify per project] These are typical SME spreads for Class 3 estimating. Validate fleet sizing against site access, haul distance, geotechnical conditions, climate window, and crew availability before committing to a bid.

## 08 SoR Master
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
MASTER SCHEDULE OF RATES — HEAVY CIVIL + CONTRACTOR SCOPE — CANADA 2026 (CAD) — SOURCE: Rev E HCUR + Rev G Missing Unit Rates
Section | WBS Ref | Item Description | UOM | Unit MH | Prod Factor | Unit Labour | Unit Equip | Unit Material | Unit Subcon. | CDI % | Total LOW (CAD) | Total HIGH (CAD) | DG % | Wastage % | Crew | Pricing Source / Basis
A — EARTHWORKS & MASS EXCAVATION
A — EARTHWORKS & MASS EXCAVATION | C-10-002 | Excavation common soil — stockpile haul 1-3km | m3 | 0.1 | 0.91 | 9.35 | 12.89 | 0 | 0 | 6% | 24 | 32 | 10% | 0% | B3 | Longer haul cycle
A — EARTHWORKS & MASS EXCAVATION | C-10-003 | Backfill common — spread and compact | m3 | 0.11 | 0.91 | 9.99 | 13.77 | 0 | 0 | 6% | 22 | 28 | 10% | 0% | B2 | Go-by x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-004 | Backfill Type 1 <250mm — spread and compact | m3 | 0.1 | 0.91 | 8.58 | 12.32 | 16.35 | 0 | 6% | 40 | 52 | 10% | 5% | B2 | Mat=$13.08 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-005 | Backfill Type 2 <100mm — spread and compact | m3 | 0.11 | 0.91 | 9.99 | 13.77 | 27.5 | 0 | 6% | 55 | 68 | 10% | 5% | B2 | Mat=$22.00 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-006 | Backfill Type 3 engineered — spread and compact | m3 | 0.21 | 0.91 | 19.09 | 26.31 | 18.96 | 0 | 6% | 72 | 88 | 10% | 5% | B2 | Mat=$15.17 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-007 | Rock excavation — blasted and loaded to truck | m3 | 0.35 | 0.88 | 31.83 | 43.88 | 0 | 0 | 6% | 38 | 58 | 10% | 0% | B3 | SME benchmark; drill+blast separate
A — EARTHWORKS & MASS EXCAVATION | C-10-008 | Overburden strip — doze + rip + stockpile | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 18 | 28 | 10% | 5% | B3 | Dozer push
A — EARTHWORKS & MASS EXCAVATION | C-10-009 | Granular A base <19mm — supply+place+compact | m3 | 0.25 | 0.91 | 22.73 | 31.31 | 43.75 | 0 | 6% | 105 | 135 | 5% | 5% | B2 | Mat=$35 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-010 | Granular B sub-base <75mm — supply+place+compact | m3 | 0.2 | 0.91 | 18.19 | 25.07 | 37.5 | 0 | 6% | 88 | 115 | 5% | 5% | B2 | Mat=$30 x1.25 avg
A — EARTHWORKS & MASS EXCAVATION | C-10-011 | Sand bedding layer — supply+place+compact | m3 | 0.22 | 0.91 | 20.01 | 27.57 | 52.5 | 0 | 6% | 115 | 145 | 5% | 0% | B2 | Mat=$42 x1.25
A — EARTHWORKS & MASS EXCAVATION | C-10-012 | Topsoil placement — supply+spread | m3 | 0.35 | 0.91 | 31.83 | 43.88 | 20 | 0 | 6% | 55 | 80 | 5% | 5% | B1 | Supply+spread; seed separately
A — EARTHWORKS & MASS EXCAVATION | C-10-013 | Seeding and restoration — hydraulic | m2 | 0.02 | 0.91 | 1.82 | 1.25 | 1.5 | 0 | 5% | 4 | 8 | 5% | 0% | B1 | Per provincial restoration spec
A — EARTHWORKS & MASS EXCAVATION | C-10-014 | Cut-fill balanced earthworks — large-scale | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 22 | 30 | 10% | 0% | B3 | On-site haul <1km; GPS
A — EARTHWORKS & MASS EXCAVATION | C-10-015 | Settling pond / water management excavation | m3 | 0.09 | 0.91 | 8.19 | 11.28 | 0 | 0 | 6% | 22 | 28 | 10% | 0% | B3 | No mob/demob assumed
A — EARTHWORKS & MASS EXCAVATION | C-10-016 | Drill and blast — holes only (excav separate) | m3 | 0.3 | 0.88 | 27.28 | 37.59 | 4.5 | 0 | 6% | 42 | 65 | 10% | 0% | B3 | Explosives approx $3.60/m3 x1.25
B — WATER MANAGEMENT / SWM & ESC
B — WATER MANAGEMENT / SWM & ESC | C-20-002 | Riprap D50 150mm entrance/exit — supply+place | m3 | 0.4 | 0.88 | 36.38 | 50.13 | 0 | 0 | 6% | 65 | 100 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-003 | Riprap D50 300mm — supply+place | m3 | 0.5 | 0.88 | 45.47 | 62.66 | 0 | 0 | 6% | 75 | 120 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-004 | Riprap D50 600mm heavy — supply+place | m3 | 0.6 | 0.88 | 54.56 | 75.19 | 0 | 0 | 6% | 85 | 140 | 5% | 0% | B3
B — WATER MANAGEMENT / SWM & ESC | C-20-005 | Energy dissipator riprap — full supply+place | m3 | 0.75 | 0.88 | 68.19 | 93.98 | 50 | 0 | 6% | 120 | 200 | 5% | 0% | B3 | Incl. quarried rock supply
B — WATER MANAGEMENT / SWM & ESC | C-20-006 | 10oz non-woven geotextile cushion — S+I | m2 | 0.05 | 0.91 | 4.55 | 1.3 | 3.75 | 0 | 6% | 4 | 9 | 0% | 10% | B4 | Mat per supply quote Jan-2026
B — WATER MANAGEMENT / SWM & ESC | C-20-007 | 6oz non-woven geotextile separator — S+I | m2 | 0.04 | 0.91 | 3.64 | 1.04 | 2.5 | 0 | 6% | 3 | 6 | 0% | 10% | B4
B — WATER MANAGEMENT / SWM & ESC | C-20-008 | Silt fence heavy duty — supply+install | m | 0.15 | 0.91 | 13.64 | 3.9 | 6.25 | 0 | 6% | 18 | 28 | 5% | 0% | B1
B — WATER MANAGEMENT / SWM & ESC | C-20-009 | Straw bale flow check dam — supply+install | m | 0.2 | 0.91 | 18.19 | 5.2 | 8 | 0 | 5% | 22 | 32 | 5% | 0% | B1 | Temp ESC measure
B — WATER MANAGEMENT / SWM & ESC | C-20-010 | Sediment dewatering bag — supply+install | ea | 4 | 0.85 | 336 | 48 | 550 | 0 | 5% | 1200 | 1600 | 5% | 0% | B4 | Supply dominant cost
B — WATER MANAGEMENT / SWM & ESC | C-20-011 | Temp pump diesel submersible 8-week rental | ea | 0 | 0 | 0 | 0 | 0 | 7500 | 5% | 7500 | 9500 | 5% | 0% | N/A | Subcontract / dry hire
C — ROADS, PADS & WORKING SURFACES
C — ROADS, PADS & WORKING SURFACES | C-30-002 | Haul road — sub-grade preparation only | m2 | 0.12 | 0.91 | 10.91 | 15.04 | 0 | 0 | 6% | 14 | 22 | 10% | 0% | B2 | Cut+fill+compact 95% Proctor
C — ROADS, PADS & WORKING SURFACES | C-30-003 | Granular sub-base 300mm — supply+place+compact | m2 | 0.2 | 0.91 | 18.19 | 25.07 | 12 | 0 | 6% | 32 | 45 | 5% | 5% | B2
C — ROADS, PADS & WORKING SURFACES | C-30-004 | Granular surface course 150mm — supply+place | m2 | 0.15 | 0.91 | 13.64 | 18.8 | 9 | 0 | 6% | 22 | 32 | 5% | 5% | B2
C — ROADS, PADS & WORKING SURFACES | C-30-005 | Asphalt paving 50mm HL3 surface course | m2 | 0.2 | 0.91 | 18.19 | 25.07 | 18 | 0 | 5% | 45 | 62 | 5% | 2% | B2 | NS/ON/BC hot mix plant avail.
C — ROADS, PADS & WORKING SURFACES | C-30-006 | Equipment pad granular 600mm — heavy duty | m2 | 0.45 | 0.91 | 40.93 | 56.42 | 22 | 0 | 8% | 50 | 70 | 10% | 5% | B2 | Process plant; 98% Proctor
C — ROADS, PADS & WORKING SURFACES | C-30-007 | Equipment pad concrete 300mm slab on grade | m2 | 2.5 | 0.9 | 218.75 | 54 | 95 | 0 | 8% | 185 | 265 | 10% | 10% | C1 | Gran base+rebar+pour+cure
C — ROADS, PADS & WORKING SURFACES | C-30-008 | Geotextile separation under road base — S+I | m2 | 0.03 | 0.91 | 2.73 | 0.78 | 1.88 | 0 | 5% | 3 | 5 | 5% | 10% | B4 | 5oz woven
C — ROADS, PADS & WORKING SURFACES | C-30-009 | Road crown and ditching — motor grader finish | m | 0.06 | 0.91 | 5.46 | 7.52 | 0 | 0 | 5% | 5 | 10 | 5% | 0% | B1 | Shoulder ditch included
D — WRSA / TMF EMBANKMENT
D — WRSA / TMF EMBANKMENT | C-40-002 | TMF embankment common fill Zone A/B | m3 | 0.11 | 0.91 | 10 | 13.78 | 0 | 0 | 6% | 22 | 32 | 10% | 0% | B2 | 300mm lift; nuclear density; Dam Safety
D — WRSA / TMF EMBANKMENT | C-40-003 | TMF embankment random rockfill Zone C | m3 | 0.08 | 0.91 | 7.28 | 10.03 | 0 | 0 | 6% | 18 | 28 | 10% | 0% | B3 | 500mm lift; vibrating roller
D — WRSA / TMF EMBANKMENT | C-40-004 | HDPE 2mm (80mil) liner — full S+I+CQA | m2 | 0.2 | 0.91 | 18.19 | 5.2 | 20 | 0 | 5% | 30 | 48 | 5% | 5% | B4 | Full scope incl. Ind. CQA
D — WRSA / TMF EMBANKMENT | C-40-005 | HDPE 1.5mm liner — full S+I+CQA | m2 | 0.18 | 0.91 | 16.37 | 4.68 | 14 | 0 | 5% | 22 | 34 | 5% | 5% | B4 | Secondary / lower-risk pond
D — WRSA / TMF EMBANKMENT | C-40-006 | Filter zone drainage blanket 19mm — supply+place | m3 | 0.45 | 0.91 | 40.93 | 56.42 | 62.5 | 0 | 6% | 120 | 175 | 10% | 0% | B4 | Clean crushed behind liner
D — WRSA / TMF EMBANKMENT | C-40-007 | Geonet / geocomposite drainage layer — S+I | m2 | 0.08 | 0.91 | 7.28 | 2.08 | 8.75 | 0 | 5% | 16 | 24 | 5% | 5% | B4 | Leachate/drainage over liner
D — WRSA / TMF EMBANKMENT | C-40-008 | Protective cover soil over liner — place+compact | m3 | 0.22 | 0.91 | 20.01 | 27.57 | 0 | 0 | 6% | 30 | 45 | 5% | 0% | B2 | 600mm min. cover
D — WRSA / TMF EMBANKMENT | C-40-009 | TMF perimeter ditch — cut+shape+riprap lined | m | 1.2 | 0.88 | 109.13 | 150.38 | 35 | 0 | 6% | 280 | 420 | 10% | 5% | B3 | Incl. riprap lining
E — DRAINAGE, CULVERTS & PIPING
E — DRAINAGE, CULVERTS & PIPING | C-50-002 | CSP culvert 750mm — supply+install+bedding | m | 2 | 0.91 | 181.88 | 51.98 | 368.75 | 0 | 8% | 580 | 750 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-003 | CSP culvert 900mm — supply+install+bedding | m | 2.5 | 0.91 | 227.35 | 64.97 | 437.5 | 0 | 8% | 680 | 880 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-004 | CSP culvert 1050mm — supply+install+bedding | m | 3 | 0.91 | 272.82 | 77.97 | 537.5 | 0 | 8% | 800 | 1020 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-005 | CSP culvert 1200mm — supply+install+bedding | m | 3.5 | 0.91 | 318.28 | 90.96 | 787.5 | 0 | 8% | 1100 | 1400 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-006 | CSP flow guard 600mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 2750 | 0 | 8% | 2500 | 3200 | 5% | 0% | B4 | Armtec Dec-2025
E — DRAINAGE, CULVERTS & PIPING | C-50-007 | CSP flow guard 750mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 11375 | 0 | 8% | 10500 | 13000 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-008 | CSP flow guard 900mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 15750 | 0 | 8% | 14000 | 17500 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-009 | CSP flow guard 1200mm — supply+install | ea | 8 | 0.85 | 672 | 192 | 9500 | 0 | 8% | 8500 | 10500 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-010 | HDPE 100mm DR11 buried — excav+install+backfill | m | 1.5 | 0.91 | 136.41 | 38.98 | 68.75 | 0 | 8% | 310 | 400 | 5% | 0% | B4 | Trench+bedding+install+BF
E — DRAINAGE, CULVERTS & PIPING | C-50-011 | HDPE 150mm DR11 above grade + insulation | m | 1.2 | 0.91 | 109.13 | 31.18 | 275 | 0 | 8% | 250 | 330 | 5% | 0% | B4 | NE Jan-2026 supply +15% install
E — DRAINAGE, CULVERTS & PIPING | C-50-012 | HDPE 200mm DR11 above grade + insulation | m | 1.5 | 0.91 | 136.41 | 38.98 | 330 | 0 | 8% | 295 | 380 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-013 | HDPE 600mm DR17 above grade + insulation | m | 2 | 0.91 | 181.88 | 51.98 | 297.5 | 0 | 8% | 280 | 370 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-014 | HDPE 1200mm inlet piping — supply+install | m | 4 | 0.88 | 363.75 | 501.25 | 1137.5 | 0 | 8% | 1500 | 1900 | 5% | 0% | B4 | Vendor quote x1.10 +install
E — DRAINAGE, CULVERTS & PIPING | C-50-015 | Clear stone discharge pipe 450mm — S+I | m | 1.8 | 0.91 | 163.69 | 46.78 | 312.5 | 0 | 8% | 400 | 520 | 5% | 0% | B4
E — DRAINAGE, CULVERTS & PIPING | C-50-016 | Discharge trench clear stone — supply+place | m3 | 0.4 | 0.91 | 36.38 | 50.13 | 75 | 0 | 6% | 135 | 175 | 5% | 0% | B4 | 10% mat markup
F — CONCRETE
F — CONCRETE | C-60-002 | Concrete wall and grade beam — supply+pour+cure | m3 | 14.57 | 0.9 | 1310.63 | 409.78 | 854.03 | 0 | 6% | 2500 | 3200 | 10% | 10% | C1
F — CONCRETE | C-60-003 | Concrete pier — drill+form+pour | m3 | 25.49 | 0.9 | 2294.1 | 726.28 | 639.59 | 0 | 6% | 3600 | 4500 | 10% | 10% | C1
F — CONCRETE | C-60-004 | Concrete footing — continuous/isolated | m3 | 14.77 | 0.9 | 1329.63 | 409.78 | 666.74 | 0 | 6% | 2400 | 3000 | 10% | 10% | C1
F — CONCRETE | C-60-005 | Shotcrete rock reinforcement 50mm | m2 | 0.8 | 0.9 | 72 | 18.72 | 25 | 0 | 6% | 90 | 140 | 5% | 5% | C1 | Portal + slope reinforcement
F — CONCRETE | C-60-006 | Rebar Grade 400 — supply+install | tonne | 20 | 0.9 | 1800 | 500 | 2000 | 0 | 6% | 4000 | 6000 | 0% | 5% | D1 | CBSA 25% surtax Chinese rebar
G — STRUCTURAL STEEL
G — STRUCTURAL STEEL | C-70-002 | Steel beams medium 26-65 kg/m — supply+erect | tonne | 28 | 0.9 | 2561.2 | 621.6 | 4500 | 0 | 6% | 8000 | 9000 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-003 | Steel beams heavy 66-125 kg/m — supply+erect | tonne | 22 | 0.9 | 2012 | 488.4 | 4250 | 0 | 6% | 7500 | 8500 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-004 | Steel columns extra-heavy — supply+erect | tonne | 24 | 0.9 | 2194.4 | 532.8 | 4500 | 0 | 6% | 8000 | 9000 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-005 | Steel grating 32x4.8mm — supply+install | m2 | 3.5 | 0.9 | 322.5 | 77.7 | 275 | 0 | 6% | 660 | 750 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-006 | Handrail incl. toe plate and fasteners | m | 4 | 0.9 | 369 | 88.8 | 175 | 0 | 6% | 440 | 500 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-007 | Stairs — stringers and treads (less handrail) | m | 4.5 | 0.9 | 415.13 | 99.9 | 200 | 0 | 6% | 540 | 620 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-008 | Metal roof deck 22ga 76mm — supply+erect | m2 | 2 | 0.9 | 178 | 44.4 | 125 | 0 | 6% | 320 | 380 | 0% | 0% | D1
G — STRUCTURAL STEEL | C-70-009 | Metal cladding 22ga prefinished — supply+erect | m2 | 1.8 | 0.9 | 160.2 | 38.48 | 100 | 0 | 6% | 265 | 320 | 0% | 0% | D1
H — CLOSURE & RECLAMATION
H — CLOSURE & RECLAMATION | C-80-002 | Riprap closure cap D50 300mm — supply+place | m3 | 0.55 | 0.88 | 50.02 | 68.93 | 40 | 0 | 5% | 90 | 150 | 5% | 0% | B3 | Long-term erosion protection
H — CLOSURE & RECLAMATION | C-80-003 | Cover system compacted clay 600mm | m3 | 0.35 | 0.91 | 31.83 | 43.88 | 12 | 0 | 8% | 58 | 95 | 10% | 0% | B2 | Perm ≤1x10-7 cm/s; nuclear density
H — CLOSURE & RECLAMATION | C-80-004 | Topsoil replacement — spread+seed | m2 | 0.05 | 0.91 | 4.55 | 1.3 | 3.75 | 0 | 5% | 5 | 12 | 10% | 5% | B1 | 300mm depth; provincial spec
H — CLOSURE & RECLAMATION | C-80-005 | HDPE cap liner 2mm — supply+install+CQA | m2 | 0.2 | 0.91 | 18.19 | 5.2 | 20 | 0 | 5% | 30 | 48 | 5% | 5% | B4 | Closure liner; same as TMF
I — BLASTING (FULL SCOPE)
I — BLASTING (FULL SCOPE) | B-01-002 | Drill blast hole 89-115mm — rotary drill | m | 0.25 | — | — | — | — | — | — | 25 | 45 | 10% | 0% | D1 | Rate per lineal metre of hole
I — BLASTING (FULL SCOPE) | B-01-003 | Rock blasting — drill+charge+blast+clear (all-in) | m3 | 0.65 | — | — | — | — | — | — | 45 | 85 | 10% | 0% | B3 | Full scope; self-perform or sub
I — BLASTING (FULL SCOPE) | B-01-004 | Controlled blasting near structures — presplit | m | 0.8 | — | — | — | — | — | — | 55 | 95 | 10% | 0% | D1 | Presplit perimeter holes
I — BLASTING (FULL SCOPE) | B-01-005 | Secondary breakage / pop shooting | ea | 2 | — | — | — | — | — | — | 250 | 550 | 5% | 0% | D2 | Large boulders
J — PERMANENT DEWATERING
J — PERMANENT DEWATERING | B-02-002 | Submersible pump station — small <50 L/s | ea | — | — | — | — | — | — | — | 45000 | 85000 | 10% | 0% | B4 | Prepackaged wet well
J — PERMANENT DEWATERING | B-02-003 | Submersible pump station — large >50 L/s | ea | — | — | — | — | — | — | — | 120000 | 250000 | 10% | 0% | B4 | Civil structure + mechanical
J — PERMANENT DEWATERING | B-02-004 | Forcemain HDPE 150mm buried — S+I | m | 1.5 | — | — | — | — | — | — | 320 | 420 | 8% | 0% | B4 | Trench+bedding+install+BF
J — PERMANENT DEWATERING | B-02-005 | Forcemain HDPE 200mm buried — S+I | m | 2 | — | — | — | — | — | — | 380 | 500 | 8% | 0% | B4
J — PERMANENT DEWATERING | B-02-006 | Wellpoint dewatering system — install+operate 4wk | LS | — | — | — | — | — | — | — | 35000 | 65000 | 5% | 0% | B4 | Temp system; open excav near water table
K — BURIED SERVICES
K — BURIED SERVICES | B-03-002 | Water line HDPE 150mm buried — S+I | m | 2 | — | — | — | — | — | — | 380 | 500 | 8% | 0% | B4
K — BURIED SERVICES | B-03-003 | Water line HDPE 200mm buried — S+I | m | 2.5 | — | — | — | — | — | — | 450 | 620 | 8% | 0% | B4
K — BURIED SERVICES | B-03-004 | Sanitary sewer PVC 150mm buried — S+I | m | 1.8 | — | — | — | — | — | — | 380 | 520 | 8% | 0% | B4 | Incl. trench, bedding, pipe, BF
K — BURIED SERVICES | B-03-005 | Sanitary manhole precast 1200mm — S+I | ea | 8 | — | — | — | — | — | — | 4500 | 7500 | 8% | 0% | B4 | Incl. excavation, bedding, frame+cover
K — BURIED SERVICES | B-03-006 | Concrete thrust block — supply+form+pour | ea | 4 | — | — | — | — | — | — | 1200 | 2500 | 8% | 10% | C1 | At each bend/tee on pressure main
K — BURIED SERVICES | B-03-007 | Gate valve 150mm buried — S+I | ea | 3 | — | — | — | — | — | — | 2200 | 3500 | 5% | 0% | B4 | Incl. valve box and operating nut
K — BURIED SERVICES | B-03-008 | Hydrant — supply+install | ea | 6 | — | — | — | — | — | — | 8500 | 14000 | 5% | 0% | B4 | Incl. service line, valve, concrete pad
L — CONCRETE PAVING & CURBING
L — CONCRETE PAVING & CURBING | B-04-002 | Concrete paving 250mm reinforced — S+P | m2 | 4.5 | — | — | — | — | — | — | 220 | 300 | 8% | 8% | C1 | Heavy traffic; light rebar mat
L — CONCRETE PAVING & CURBING | B-04-003 | Concrete curb and gutter — S+F+P | m | 2.5 | — | — | — | — | — | — | 185 | 265 | 5% | 8% | C1 | Incl. forming, pour, cure
L — CONCRETE PAVING & CURBING | B-04-004 | Concrete wheel wash pad — supply+construct | ea | 40 | — | — | — | — | — | — | 18000 | 35000 | 5% | 5% | C1 | Truckwash; grate+sump+recirculate pump
M — FENCING, SECURITY & WILDLIFE
M — FENCING, SECURITY & WILDLIFE | B-05-002 | Chain link fence 2.4m security — S+I | m | 1 | — | — | — | — | — | — | 110 | 165 | 5% | 0% | B1 | Security grade; top barbed wire
M — FENCING, SECURITY & WILDLIFE | B-05-003 | Wildlife exclusion fence 2.4m electrified | m | 1.5 | — | — | — | — | — | — | 165 | 260 | 5% | 0% | B1 | Grizzly/caribou/wildlife; energizer sep.
M — FENCING, SECURITY & WILDLIFE | B-05-004 | Fence gate single swing 4m — S+I | ea | 4 | — | — | — | — | — | — | 1800 | 3200 | 5% | 0% | B1
M — FENCING, SECURITY & WILDLIFE | B-05-005 | Fence gate double swing 8m — S+I | ea | 6 | — | — | — | — | — | — | 3500 | 6500 | 5% | 0% | B1 | Truck gate; drop rod + lock
N — SITE SIGNAGE & TRAFFIC MGMT
N — SITE SIGNAGE & TRAFFIC MGMT | B-06-002 | Traffic control — flagging (per shift) | shift | 10 | — | — | — | — | — | — | 850 | 1200 | 5% | 0% | B1 | 2-person crew with truck; per 10hr shift
N — SITE SIGNAGE & TRAFFIC MGMT | B-06-003 | Dust suppression — calcium chloride application | tonne | 0.1 | — | — | — | — | — | — | 450 | 650 | 5% | 0% | B1 | Effective 6-8 weeks per application
O — ROCK ANCHORS & STABILIZATION
O — ROCK ANCHORS & STABILIZATION | B-07-002 | Rock anchor active tensioned 32mm strand | ea | 8 | — | — | — | — | — | — | 2500 | 5500 | 10% | 0% | D1 | Pre-stressed; headplate; torqued to spec
O — ROCK ANCHORS & STABILIZATION | B-07-003 | Wire mesh rockfall protection — supply+pin | m2 | 0.6 | — | — | — | — | — | — | 65 | 120 | 10% | 5% | B3 | Double-twist hex mesh; portal/cut slope
O — ROCK ANCHORS & STABILIZATION | B-07-004 | Shotcrete with fibre 75mm — supply+apply | m2 | 1.2 | — | — | — | — | — | — | 120 | 195 | 5% | 5% | C1 | Steel or polypropylene fibre
O — ROCK ANCHORS & STABILIZATION | B-07-005 | Shotcrete with wire mesh 100mm — supply+apply | m2 | 1.8 | — | — | — | — | — | — | 165 | 250 | 5% | 5% | C1 | Welded wire mesh embedded; heavy support
P — CULVERT STRUCTURES
P — CULVERT STRUCTURES | B-08-002 | Precast box culvert 2400x1800mm — S+I | m | 18 | — | — | — | — | — | — | 6500 | 10500 | 8% | 0% | B4 | Large watercourse crossing
P — CULVERT STRUCTURES | B-08-003 | Precast arch culvert 3000mm span — S+I | m | 14 | — | — | — | — | — | — | 4500 | 8500 | 8% | 0% | B4 | Fish habitat; open bottom design
P — CULVERT STRUCTURES | B-08-004 | Headwall concrete — supply+form+pour | ea | 24 | — | — | — | — | — | — | 8500 | 16000 | 8% | 10% | C1 | Poured in place; per end per culvert
Q — AGGREGATE CRUSHING ON-SITE
Q — AGGREGATE CRUSHING ON-SITE | B-09-002 | Crushing — quarry to Granular A/B | tonne | 0.02 | — | — | — | — | — | — | 4.5 | 9.5 | 5% | 0% | B3 | Operating cost only; excl. mob/demob
Q — AGGREGATE CRUSHING ON-SITE | B-09-003 | Crushing — quarry to rip-rap D50 150-600mm | tonne | 0.02 | — | — | — | — | — | — | 5.5 | 12 | 5% | 0% | B3 | Incl. scalping and grading
Notes: 'Total LOW/HIGH' = all-in unit price already including labour + equipment + material + subcontract + CDI (where shown). For Rev G items (sections I–Q) build-up columns are not decomposed in source — use the Unit Rate Build-Up Calculator (Sheet 09) to reverse-engineer if required. 'DG %' = design growth (apply to quantity, see Sheet 03). 'Wastage %' = apply to material take-off. 'Crew' = SME-typical crew code (Sheet 04).

## 09 Unit Rate Calculator
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
UNIT RATE BUILD-UP CALCULATOR [TEMPLATE — enter inputs in blue cells]
Field | Input / Value | Source / Reference
WBS reference (e.g. C-30-002) | <enter> | Project WBS code
Item description | <enter> | Plain English
Unit of measure (UOM) | m3 | m3, m2, m, tonne, ea, LS
Crew code (B1–N1) | B3 | From Sheet 04
Crew total rate ($/hr) | 201.63 | From Sheet 04 — 2026 Total
Unit MH per UOM | 0.1 | Time per unit; SME baseline 0.08-0.50
Productivity factor (0.80–1.00) | 0.91 | Reduces idealized output to realistic
Crew cost per unit ($) [calculated] | 0 | = Unit MH / Prod × Crew $/hr
Unit material cost ($) | 0 | Supplied + delivered
Material wastage (%) | 0.05 | From Sheet 03 — 0% to 15% typical
Adjusted material cost ($) [calc] | 0 | = Mat × (1+wastage)
Unit subcontract cost ($) | 0 | Per sub quote; bare cost
Contractor Distributable Indirect (CDI) % | 0.06 | From Sheet 11 — 6-10% typical
Subtotal direct + CDI ($) [calc] | 0 | = (Crew+Mat+Sub) × (1+CDI)
Design growth (Class 3 baseline) % | 0.1 | From Sheet 03 — 2-20% by class
Regional adjustor (e.g. 1.10) | 1 | From Sheet 14 — 1.00 to 1.55
FINAL UNIT RATE BEFORE MARKUP STACK ($) [calc] | 0 | = Subtotal × (1+DG) × Regional adjustor
[TEMPLATE] This calculator builds a single direct unit rate. The 6-layer markup stack (OH, Bond/Ins, Contingency, Profit) is applied at project roll-up (Sheet 21). For Sheet 08 entries already include CDI in the LOW/HIGH columns. For subcontract-dominant work (e.g. blasting, liner) set Unit MH=0 and place sub quote in Subcontract row.

## 10 Bid Screening
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID SCREENING — UNIT COST SENSE-CHECKS — CANADA 2026 — SOURCE: Rev G Bid Screening tab
Category | Benchmark Item | UOM | Floor (CAD) | Ceiling (CAD) | Bid Screening Guidance
EARTHWORKS | Mass earthworks — rock (blasted) | $/m3 | 55 | 120 | Includes drill, blast, load, haul 1km
EARTHWORKS | Engineered fill compacted Zone A/B | $/m3 | 22 | 45 | Material, place, compact, test
EARTHWORKS | Granular road base 150mm | $/m2 | 22 | 42 | Supply+place+compact; material included
EARTHWORKS | Haul road full build (sub-grade to surface) | $/m2 | 65 | 120 | 8m wide single lane; all lifts
EARTHWORKS | Strip and grub per hectare | $/ha | 8500 | 18000 | Light bush; add for rock; add for timber
WRSA / TMF | TMF embankment engineered fill | $/m3 | 22 | 45 | Zone A/B compacted; nuclear density testing
WRSA / TMF | HDPE liner 2mm supply+install | $/m2 | 28 | 55 | Full scope incl. CQA; verify CQA included
WRSA / TMF | TMF perimeter ditch riprap lined | $/m | 280 | 500 | If below $280 likely missing riprap lining
DRAINAGE | CSP culvert 1200mm supply+install | $/m | 1000 | 1600
DRAINAGE | HDPE 150mm above grade insulated | $/m | 230 | 380 | If below $230 check insulation is included
DRAINAGE | Flow guard 600mm supply+install | $/ea | 2200 | 3500
DRAINAGE | Flow guard 1200mm supply+install | $/ea | 8000 | 12000
CONCRETE | Concrete foundation/wall | $/m3 | 2200 | 3500 | Formed; higher labour content
CONCRETE | Shotcrete with fibre 75mm | $/m2 | 90 | 160 | If below $90 check mix design and CQA
CONCRETE | Rebar supply+install | $/tonne | 3800 | 6500 | CBSA 25% surtax; verify Canadian/US source
BLASTING | Pre-blast survey per structure | $/struct | 3000 | 9000 | Mandatory; missing = liability exposure
FENCING | Wildlife exclusion electrified 2.4m | $/m | 150 | 280 | Energizer and monitoring system separate
BURIED SERVICES | Sanitary manhole precast 1200mm | $/ea | 4000 | 8000 | Incl. excavation, bedding, frame+cover
OVERHEAD CHECK | Contractor OH+profit — $50M project | % of dir. | 14% | 22% | Scale efficiency on larger projects
OVERHEAD CHECK | Performance + L&M bond (>$25M) | % of cont. | 0.75% | 1.25% | Check surety capacity and history

## 11 Contractor Indirects
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONTRACTOR INDIRECTS (CDI) & OVERHEAD BUILD-UP — CANADA 2026 — SOURCE: Rev G Overhead Build-Up tab
Category | Item | UOM | 2026 Low (CAD) | 2026 High (CAD) | SME Notes
FIELD OFFICE & SITE ESTABLISHMENT
FIELD OFFICE & SITE ESTABLISHMENT | Site trailer — lunchroom/dryroom | month | 1500 | 2500
FIELD OFFICE & SITE ESTABLISHMENT | Temporary power — generator 100kW diesel | month | 4500 | 8500 | Incl. fuel; or hook-up to utility sep.
FIELD OFFICE & SITE ESTABLISHMENT | Temp power — 250kW generator large camp | month | 9500 | 16000
FIELD OFFICE & SITE ESTABLISHMENT | Site IT, internet and communication | month | 850 | 2500 | Starlink or repeater; rural mine sites
FIELD OFFICE & SITE ESTABLISHMENT | Site vehicle — project truck leased | month | 1200 | 1800 | Per PU truck; fuel separate
FIELD OFFICE & SITE ESTABLISHMENT | Site vehicle — crew bus leased | month | 3500 | 6500 | 20-seat; daily crew transport
FIELD OFFICE & SITE ESTABLISHMENT | Mob/demob — site setup and teardown | LS | 35000 | 85000 | All temp facilities; charged once
PROJECT MANAGEMENT STAFF
PROJECT MANAGEMENT STAFF | Senior Project Engineer | month | 14000 | 20000
PROJECT MANAGEMENT STAFF | Field Engineer / QC Engineer | month | 11000 | 16000
PROJECT MANAGEMENT STAFF | Site Safety Officer (NCSO certified) | month | 12000 | 17000 | Dedicated; mandatory >20 workers
PROJECT MANAGEMENT STAFF | Senior Superintendent | month | 16000 | 24000
PROJECT MANAGEMENT STAFF | General Foreman | month | 13000 | 19000
PROJECT MANAGEMENT STAFF | Document Controller / Field Admin | month | 7500 | 11000
QUALITY CONTROL & TESTING
QUALITY CONTROL & TESTING | Nuclear density testing — crew/day | day | 850 | 1500 | One tech; one nuclear gauge
QUALITY CONTROL & TESTING | Concrete cylinder testing — per set | set | 185 | 350 | 4 cylinders; 28-day break; per pour
QUALITY CONTROL & TESTING | Aggregate gradation testing | test | 250 | 450 | Per material source change or 500 tonne
QUALITY CONTROL & TESTING | Geomembrane weld testing (spark test) | m weld | 2.5 | 4.5 | 100% of seams; third-party CQA
QUALITY CONTROL & TESTING | Survey control — survey crew/day | day | 2500 | 4500 | Layout, grades, as-builts
ENVIRONMENTAL COMPLIANCE
ENVIRONMENTAL COMPLIANCE | Spill kit and containment supplies | month | 350 | 750 | Per site regulation; replenished monthly
ENVIRONMENTAL COMPLIANCE | Environmental monitoring (water sampling) | sample | 450 | 950 | Lab analysis; site discharge monitoring
ENVIRONMENTAL COMPLIANCE | Environmental coordinator (part-time) | month | 5500 | 9500 | Required near watercourse crossings
COMPANY HEAD OFFICE OVERHEAD
COMPANY HEAD OFFICE OVERHEAD | Warranty/deficiency holdback allowance | % of cont. | 0.5% | 1.0% | 12-month deficiency period
CDI typical totals at bid stage: 12-18% of direct cost for mid-size mining civil. Overhead (Sheet 15 markup) is additional. Camp/LOA cost (see Sheet 05 O2/O3) is shown separately when used and is not duplicated here.

## 12 Bonding & Insurance
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BONDING & INSURANCE RATES — CANADA 2026 — SOURCE: Rev G Bonding & Insurance tab
Category | Item | Basis | Rate Low | Rate High | SME Notes
SURETY BONDS
SURETY BONDS | Performance Bond — small contract (<$5M) | % of contract | 1.5% | 2.5% | Higher rate for smaller contracts
SURETY BONDS | Performance Bond — medium ($5-$25M) | % of contract | 1.0% | 1.8% | Mid-tier; established contractor
SURETY BONDS | Performance Bond — large (>$25M) | % of contract | 0.75% | 1.25% | Volume discount; strong surety history
SURETY BONDS | Labour & Material Payment Bond | % of contract | 0.5% | 1.0% | Required CCDC 2; bundled w/ perf bond
SURETY BONDS | Maintenance/Warranty Bond — 12 month | % of contract | 0.5% | 1.0% | Some mining owners require
SURETY BONDS | Surety capacity rule of thumb | Max single contract | 10x NWC | — | Surety evaluates Character/Capacity/Capital
LIABILITY INSURANCE
LIABILITY INSURANCE | Contractor's Pollution Liability | Annual policy | $1,500 | $3,500 | Fuel/chemical spill; liner failure; contamination
WCB
WCB | Labourer — Alberta WCB Industry 41 | Per $100 payroll | $3.80 | $5.20 | Lower than eastern provinces
WCB | Labourer — BC WorkSafeBC Class 711001 | Per $100 payroll | $4.50 | $6.00 | 2026 WorkSafeBC
WCB | Labourer — NS WCB NS | Per $100 payroll | $3.80 | $5.50 | Atlantic Canada
WCB | Labourer — NL WorkplaceNL | Per $100 payroll | $4.00 | $5.80 | 2026 WorkplaceNL
WCB | Labourer — Quebec CNESST | Per $100 payroll | $5.50 | $8.00 | Higher than national average
WCB | Equipment Operator — all provinces | Per $100 payroll | $3.50 | $5.00 | Lower risk class than labourer
WCB | Blaster / Driller — elevated risk | Per $100 payroll | $5.50 | $8.00 | Elevated risk classification
PROPERTY INSURANCE
PROPERTY INSURANCE | Contractor's Equipment Floater | % of fleet repl/yr | 0.5% | 1.2% | Check if already in equipment hourly rate
Typical bid stage: Bonding 1.5-3.0% of contract (perf + L&M + warranty bundled); General Liability ~$5-$8 / $1,000 payroll; Builder's Risk 0.15-0.35% of contract value. WCB is province-specific — confirm classification and base rate before pricing.

## 13 Standby & Schedule
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
STANDBY RATES & SCHEDULE COST DRIVERS — CANADA 2026 — SOURCE: Rev G Standby & Schedule tab
Category | Item | UOM | 2026 Low (CAD) | 2026 High (CAD) | SME Notes
EQUIPMENT STANDBY RATES
EQUIPMENT STANDBY RATES | Excavator 20-25T (Cat 320) — standby | hr | 110 | 155
EQUIPMENT STANDBY RATES | Excavator 35-40T (Cat 336) — standby | hr | 140 | 200
EQUIPMENT STANDBY RATES | Track dozer D8T — standby | hr | 155 | 215
EQUIPMENT STANDBY RATES | Motor grader Cat 140M — standby | hr | 110 | 155
EQUIPMENT STANDBY RATES | Rough terrain crane RT 60T — standby | hr | 320 | 480 | Minimum 4hr call-out
EQUIPMENT STANDBY RATES | Crawler crane 150T — standby | hr | 850 | 1300 | Minimum 4hr call-out; rigging crew separate
LABOUR STANDBY RATES
LABOUR STANDBY RATES | Equipment operator — standby | hr | 93 | 128 | Full burdened; equipment idle alongside
LABOUR STANDBY RATES | Crew standby — B3 heavy civil crew of 10 | day | 7000 | 10000 | Full crew retained; weather hold or owner delay
DELAY / ACCELERATION PREMIUMS
DELAY / ACCELERATION PREMIUMS | Overtime premium — double time (2x) | % add | 100% | 100% | Sunday + statutory holidays
DELAY / ACCELERATION PREMIUMS | Shift premium — afternoon shift | % add | 5% | 10% | Per CBA; project specific
DELAY / ACCELERATION PREMIUMS | Shift premium — night shift | % add | 10% | 15% | Per CBA; project specific
DELAY / ACCELERATION PREMIUMS | Cold weather heating — LP heaters | day | 450 | 850 | Propane salamander or torpedo heater
DELAY / ACCELERATION PREMIUMS | Cold weather enclosure — concrete pour | m2 enclosed | 8 | 18 | Poly tarp + frame + heat; per pour area
DELAY / ACCELERATION PREMIUMS | Winter freeze protection — earthworks | m3 thaw | 3.5 | 8.5 | Steam or ground thaw blankets
OWNER-CAUSED DELAY
OWNER-CAUSED DELAY | Equipment demob + remob — per event | event | 15000 | 65000 | Equipment size dependent
OWNER-CAUSED DELAY | Extended project overhead — per week | week | 12000 | 35000 | All site OH: trailer, IT, vehicles, staff
OWNER-CAUSED DELAY | Material restocking / escalation impact | % of mat. | 2% | 8% | If materials ordered and delay >3 months

## 14 SME Factors
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SME ESTIMATING FACTORS — CANADA 2026 — SOURCE: Rev E SME Factors tab
Category | Factor / Item | Low | High | SME Notes / Basis
INDIRECT / GC MARKUPS
INDIRECT / GC MARKUPS | Mob/demob — major earthwork fleet (% of equip) | 2% | 5% | Or flat LS per fleet assembly
INDIRECT / GC MARKUPS | Mob/demob — rough terrain crane RT 60T | $4,000 | $8,000 | Flat rate per mob
INDIRECT / GC MARKUPS | Mob/demob — crawler crane 150T | $25,000 | $55,000 | Incl. partial disassembly
INDIRECT / GC MARKUPS | Camp/LOA markup on direct labour | 8% | 12% | Add for remote sites
INDIRECT / GC MARKUPS | Small tools and consumables on direct labour | 2.5% | 4% | Blades, hoses, bits, PPE consumables
INDIRECT / GC MARKUPS | Supervision markup on direct labour | 8% | 12% | Foreman + superintendent ratio
INDIRECT / GC MARKUPS | Contractor distributable (CDI) on direct cost | 6% | 10% | Temp facilities, insurance, site admin
DESIGN GROWTH — AACE 18R-97
DESIGN GROWTH — AACE 18R-97 | Class 4 study (screening/feasibility prep) | 15% | 20% | Limited geotech; prelim drawings
DESIGN GROWTH — AACE 18R-97 | Class 3 budget (feasibility study) | 10% | 15% | THIS DOCUMENT standard level
DESIGN GROWTH — AACE 18R-97 | Class 2 sanction / AFE (pre-FID) | 5% | 10% | Good definition; IFC packages near complete
DESIGN GROWTH — AACE 18R-97 | Class 1 check / tender (detailed design) | 2% | 5% | Full detailed design completed
DESIGN GROWTH — AACE 18R-97 | Concrete works — add to above | +5% | +5% | Add 5% incremental to earthworks DG
WASTAGE FACTORS
WASTAGE FACTORS | Granular aggregate — over-order allowance | 5% | 10% | Rounding + delivery variance
WASTAGE FACTORS | Concrete — over-pour allowance | 8% | 12% | Formed concrete; pump waste + edge loss
WASTAGE FACTORS | Rebar — cutting waste | 3% | 7% | Depends on bar size and cutting complexity
WASTAGE FACTORS | Geomembrane liner — overlap + waste | 5% | 10% | Panel overlaps + anchor trench + QA sampling
WASTAGE FACTORS | Geotextile — overlap + waste | 10% | 15% | 6-inch overlaps min per ASTM D4439
REGIONAL ADJUSTMENTS — CANADA 2026
REGIONAL ADJUSTMENTS — CANADA 2026 | Ontario (Greater Toronto / Ottawa) | 1.05 | 1.15 | Labour + material premium
REGIONAL ADJUSTMENTS — CANADA 2026 | Ontario (Northern — Thunder Bay / Sudbury) | 1.02 | 1.10 | Remote factor; fly-in camp adds $50-80/mhday
REGIONAL ADJUSTMENTS — CANADA 2026 | Quebec (Montreal) | 1.03 | 1.12 | Union density; CCQ wage rates
REGIONAL ADJUSTMENTS — CANADA 2026 | Quebec (Northern — Chibougamau / James Bay) | 1.08 | 1.22 | Remote + northern premium
REGIONAL ADJUSTMENTS — CANADA 2026 | Manitoba / Saskatchewan | 1.00 | 1.08 | Moderate; open-shop market available
REGIONAL ADJUSTMENTS — CANADA 2026 | Alberta (Edmonton / Calgary) | 1.05 | 1.18 | Boom/bust volatility; CLAC + union mix
REGIONAL ADJUSTMENTS — CANADA 2026 | Alberta (Oil Sands / Fort McMurray) | 1.15 | 1.35 | Boom market premium; remote camp intensity
REGIONAL ADJUSTMENTS — CANADA 2026 | British Columbia (Metro Vancouver) | 1.10 | 1.20 | Labour premium; IBEW/UA rates higher
REGIONAL ADJUSTMENTS — CANADA 2026 | British Columbia (Interior / Northern) | 1.15 | 1.30 | Remote + northern premium; winter factor
REGIONAL ADJUSTMENTS — CANADA 2026 | Yukon / NWT / Nunavut | 1.30 | 1.55 | Extreme remote; fly-in; northern allowances
REGIONAL ADJUSTMENTS — CANADA 2026 | Winter construction premium — all Canada | 10% | 25% | Heating, snow clearing, reduced productivity
ESCALATION — CANADA 2026
ESCALATION — CANADA 2026 | Go-by Q2-2020 to Q2-2026 applied factor | x1.23 | x1.27 | BCPI cumulative; use x1.25 midpoint
ESCALATION — CANADA 2026 | Labour CBA escalation 2024-2026 NL trades | 3.5% | 5.5% | Per trade; see Sheet 05
ESCALATION — CANADA 2026 | Diesel — NS May 2026 (NRCan) | $2.13/L | $2.21/L | NS Energy Regulatory Board
ESCALATION — CANADA 2026 | Diesel — AB May 2026 (NRCan) | $1.68/L | $1.78/L | Lower tax base
ESCALATION — CANADA 2026 | Diesel — BC Metro May 2026 (NRCan) | $2.15/L | $2.35/L | Carbon levy + higher base
ESCALATION — CANADA 2026 | USD/CAD exchange rate May 2026 | 1.36 | 1.37 | Bank of Canada
ESCALATION — CANADA 2026 | CBSA surtax — Chinese structural steel (25%) | 25% | 25% | CBSA Notices 24-26/25-22
ESCALATION — CANADA 2026 | CBSA surtax — Chinese rebar (25%) | 25% | 25% | Verify current supplier origin cert.
ACCURACY RANGES — AACE 18R-97
ACCURACY RANGES — AACE 18R-97 | Class 4 study | -30% | +50% | Screening/feasibility
ACCURACY RANGES — AACE 18R-97 | Class 3 budget / feasibility | -20% | +30% | THIS DOCUMENT — standard benchmark
ACCURACY RANGES — AACE 18R-97 | Class 2 sanction / AFE | -10% | +20% | Pre-FID; good definition
ACCURACY RANGES — AACE 18R-97 | Class 1 check / tender | -5% | +10% | Full detailed design completed

## 15 Bid Cost Structure
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID COST STRUCTURE — 6-LAYER CONTRACTOR MARKUP MODEL — SOURCE: Rev G Bid Summary tab
Layer | Bid Cost Element | Basis / Method | Typical Low | Typical High | % of Direct | SME Notes
1 — DIRECT FIELD COSTS
1 — DIRECT FIELD COSTS | 1.2 SWM, ESC & Water Management | Unit rates × MTO quantities | — | — | 5-10%
1 — DIRECT FIELD COSTS | 1.3 Roads, Pads & Working Surfaces | Unit rates × MTO quantities | — | — | 8-15%
1 — DIRECT FIELD COSTS | 1.4 WRSA / TMF Embankment | Unit rates × MTO quantities | — | — | 10-20% | Dam Safety requirements additive
1 — DIRECT FIELD COSTS | 1.5 Drainage, Culverts & Piping | Unit rates × MTO quantities | — | — | 5-10% | Long lead items; confirm supply
1 — DIRECT FIELD COSTS | 1.6 Concrete — Civil | Unit rates × MTO quantities | — | — | 5-12%
1 — DIRECT FIELD COSTS | 1.7 Structural Steel & Building Enclosure | Unit rates × MTO quantities | — | — | 3-8% | CBSA tariff risk — Chinese origin
1 — DIRECT FIELD COSTS | 1.8 Geosynthetics & Liner Systems | Unit rates × MTO quantities | — | — | 3-8% | Specialist sub; include CQA
1 — DIRECT FIELD COSTS | 1.9 Blasting (drill+charge+blast+clear) | Unit rates × MTO quantities | — | — | 2-5% | Licensed sub or self-perform
1 — DIRECT FIELD COSTS | 1.10 Buried Services | Unit rates × MTO quantities | — | — | 2-5%
1 — DIRECT FIELD COSTS | 1.11 Fencing, Security & Wildlife | Unit rates × MTO quantities | — | — | 1-2% | Required all Canadian mine sites
1 — DIRECT FIELD COSTS | 1.12 Permanent Dewatering Systems | Unit rates × MTO quantities | — | — | 1-3%
1 — DIRECT FIELD COSTS | 1.13 Closure & Reclamation | Unit rates × MTO quantities | — | — | 2-5% | If in scope
1 — DIRECT FIELD COSTS | SUBTOTAL — DIRECT FIELD COSTS | Sum above | — | — | 100% | Basis for all markup calculations
2 — CONTRACTOR FIELD INDIRECTS (CDI)
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.2 Temp facilities (offices, lunchrooms) | LS allowance | 0.5% | 1.5% | 0.5-1.5%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.3 Field supervision | 8-12% of direct labour | 8% | 12% | 8-12% of lab | PM, QC, safety officer
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.4 Small tools and consumables | 2.5-4% of direct labour | 2.5% | 4.0% | 2.5-4%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.5 Quality control and testing | 0.5-1.5% of direct | 0.5% | 1.5% | 0.5-1.5% | Nuclear density, concrete cyl, geotech
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.6 Environmental compliance (SWPPP) | 0.3-0.8% of direct | 0.3% | 0.8% | 0.3-0.8% | Monitoring, spill kits, inspection
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.7 Demobilization and site cleanup | 0.5-1.5% | 0.5% | 1.5% | 0.5-1.5%
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.8 Camp setup and operating costs | See Sheet 11 | — | — | Project-specific | Separate line — not in labour rate
2 — CONTRACTOR FIELD INDIRECTS (CDI) | 2.9 Pre-blast surveys | $3,500-$8,500/struct | $3,500 | $8,500 | LS | Required before blasting near structures
2 — CONTRACTOR FIELD INDIRECTS (CDI) | CDI SUBTOTAL | Typically 12-18% of direct | 12% | 18% | 12-18%
3 — COMPANY OVERHEAD
3 — COMPANY OVERHEAD | 3.2 Bid and proposal costs | 0.5-1.5% | 0.5% | 1.5% | 0.5-1.5%
3 — COMPANY OVERHEAD | 3.3 Warranty allowance — 12 month | 0.5-1.0% of contract | 0.5% | 1.0% | 0.5-1%
3 — COMPANY OVERHEAD | OVERHEAD SUBTOTAL | Typically 6-12% of direct | 6% | 12% | 6-12%
4 — BONDING & INSURANCE
4 — BONDING & INSURANCE | 4.2 Performance bond | 0.5-1.5% of contract | 0.5% | 1.5% | 0.5-1.5% | CCDC 2 standard requirement
4 — BONDING & INSURANCE | 4.3 Labour & Material Payment bond | 0.5-1.0% of contract | 0.5% | 1.0% | 0.5-1% | Required CCDC 2
4 — BONDING & INSURANCE | 4.4 General liability insurance | $5-$8 per $1,000 payroll | $5 | $8 | / $1K payroll
4 — BONDING & INSURANCE | 4.5 Workers Compensation — labourers | $4.50-$6.00 per $100 | $4.50 | $6.00 | / $100 payroll
4 — BONDING & INSURANCE | 4.6 Builder's Risk / Course of Const. | 0.15-0.35% of contract | 0.15% | 0.35% | 0.15-0.35%
4 — BONDING & INSURANCE | BONDING & INSURANCE SUBTOTAL | Typically 2-4% of contract | 2% | 4% | 2-4%
5 — CONTINGENCY & RISK
5 — CONTINGENCY & RISK | 5.2 Ground conditions / geotech risk | 3-8% of earthworks direct | 3% | 8% | 3-8% of earth | Unforeseen rock, contamination, groundwater
5 — CONTINGENCY & RISK | 5.3 Weather / schedule risk | 2-5% of total | 2% | 5% | 2-5% | Productivity loss; winter and spring
5 — CONTINGENCY & RISK | 5.4 Escalation / commodity price risk | 3-8% of materials | 3% | 8% | 3-8% of mat. | Diesel, aggregate, steel — long contracts
5 — CONTINGENCY & RISK | 5.5 Subcontractor default risk | 1-3% of sub spend | 1% | 3% | 1-3% of sub $
5 — CONTINGENCY & RISK | CONTINGENCY SUBTOTAL | Typically 8-15% of direct | 8% | 15% | 8-15%
6 — CONTRACTOR PROFIT
6 — CONTRACTOR PROFIT | 6.2 Profit — sole source / preferred | 8-12% of all costs | 8% | 12% | 8-12% | Pre-qualified or sole-source scenario
6 — CONTRACTOR PROFIT | 6.3 Profit — high risk / remote | 10-15% of all costs | 10% | 15% | 10-15% | Northern, fly-in, first-time client
6 — CONTRACTOR PROFIT | TOTAL BID = Direct + CDI + OH + B/I + Contingency + Profit | Bottom-up; sense-check $/m3 or $/m2 | — | — | — | Cross-check with Sheet 10 floors/ceilings

## 16 Mob Demob Logic
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
MOBILIZATION & DEMOBILIZATION LOGIC — CANADA 2026 — SOURCE: Rev E SME Factors + standard practice
Category | Asset / Activity | Basis | Low (CAD) | High (CAD) | SME Notes
EARTHWORK FLEET
EARTHWORK FLEET | Major earthwork fleet mob/demob | % of total equip value | 2% | 5% | Or flat LS per fleet; round-trip
EARTHWORK FLEET | Heavy haul move per low-bed trip | Per round-trip | $1,800 | $3,500 | Within 300 km radius
EARTHWORK FLEET | Off-road haul truck (40-100T) move | Per unit / round-trip | $8,000 | $18,000 | May require permit, escort
CRANES
CRANES | Rough terrain crane RT 60T | Flat per mob | $4,000 | $8,000 | Single-truck low-bed
CRANES | Lattice boom crawler 150T | Flat per mob (incl. disassembly) | $25,000 | $55,000 | Partial disassembly; 5-10 trailer loads
CAMPS
CAMPS | Camp setup — fly-in remote (40-bed) | LS | $250,000 | $500,000 | Mob crew + freight + assembly
CAMPS | Camp setup — drive-in (40-bed) | LS | $120,000 | $220,000
SITE TEMP FACILITIES
SITE TEMP FACILITIES | Trailer offices + lunchrooms + IT | LS | $35,000 | $85,000 | From Sheet 11
SPECIALTY SUBS
SPECIALTY SUBS | HDPE liner sub (incl. CQA crew) | LS | $25,000 | $60,000 | Specialty equipment + technicians
SPECIALTY SUBS | Blasting sub (drill + powder magazine) | LS | $35,000 | $90,000 | Includes permit fees, magazine, powder
SPECIALTY SUBS | Aggregate crushing plant | LS | $150,000 | $400,000 | Move, set, commission
INSURANCE / WCB REG
INSURANCE / WCB REG | Provincial registration + WCB account | LS | $5,000 | $15,000 | Multi-province jobs
Mob/demob is typically priced as a separate LS line — not absorbed in unit rates. For remote/fly-in sites add freight allowance. For multi-phase work, charge re-mob per phase. Confirm haul permit and escort costs for over-dimensional moves in NS/NB/QC/ON/MB. Sheet 13 (Standby & Schedule) handles owner-caused remob.

## 17 Constructability
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CONSTRUCTABILITY & EXECUTION ASSUMPTIONS [TEMPLATE — populate per project]
Category | Assumption / Decision | Project-Specific Notes
WORK CALENDAR
WORK CALENDAR | Site works 10-hr shift, 14-on / 7-off (FIFO) OR 4-on / 3-off (drive-in) | <populate>
WORK CALENDAR | Effective hours per shift after breaks & travel: 8.5-9.0 productive hr | <populate>
WORK CALENDAR | Winter weather window (no work): Nov-Mar productivity factor 0.70-0.85 | <populate>
WORK CALENDAR | Spring break-up moratorium (haul road restrictions): early Apr to mid-May | <populate>
ACCESS & LOGISTICS
ACCESS & LOGISTICS | Primary access road condition (paved / gravel / seasonal) and weight rating | <populate>
ACCESS & LOGISTICS | Fly-in vs drive-in — confirm chartered air freight cost & frequency | <populate>
ACCESS & LOGISTICS | Material laydown sufficient for 60-90 days inventory at site | <populate>
ACCESS & LOGISTICS | Fuel resupply schedule — confirm tanker turnaround & on-site storage capacity | <populate>
SEQUENCING
SEQUENCING | Earthworks completion before liner install (no traffic post-liner) | <populate>
SEQUENCING | Concrete cure times: 7 days form-strip; 28 days full strength; cold weather double | <populate>
SEQUENCING | Steel erection cannot proceed until anchor bolts surveyed and accepted | <populate>
SEQUENCING | Culvert installs during low-flow window per provincial fisheries authorization | <populate>
GEOTECHNICAL
GEOTECHNICAL | Bedrock encountered at depth X m — drill+blast assumption from elevation Y | <populate>
GEOTECHNICAL | Water table at depth X m — dewatering required for excavations deeper than Y m | <populate>
GEOTECHNICAL | Acid-generating waste rock requires segregation and encapsulation (geomembrane base) | <populate>
ENVIRONMENTAL
ENVIRONMENTAL | Fish habitat compensation work in Year 1 — site-specific permits required | <populate>
ENVIRONMENTAL | SWPPP / ESCP plan controlling discharge to receiving water; weekly inspection minimum | <populate>
ENVIRONMENTAL | Wildlife protocol (bear/caribou/grizzly) — daily site clearance | <populate>
CONSTRUCTION METHODS
CONSTRUCTION METHODS | Roll-on / roll-off compaction at 95% Std Proctor; 98% for process pads | <populate>
CONSTRUCTION METHODS | Concrete supplied from on-site batch plant (if vol >2,000 m3) else ready-mix from <X> km | <populate>
CONSTRUCTION METHODS | Aggregate supplied from on-site quarry/crusher (if vol >50,000 t) else from <X> km | <populate>
CONSTRUCTION METHODS | Blasting confined per pattern; pre-blast survey for structures within 500m radius | <populate>
INTERFACE
INTERFACE | Owner-supplied items: <list> (e.g. process plant equipment) | <populate>
INTERFACE | Existing facility tie-ins coordinated during scheduled outage windows | <populate>
LABOUR / IR
LABOUR / IR | Open shop / CLAC / Building Trades — confirm market and CBA obligations | <populate>
LABOUR / IR | Indigenous community engagement commitment — % local hire / IBA obligations | <populate>
HSE
HSE | Site induction 4 hr per worker; site-specific safety standards apply | <populate>
HSE | Fire watch protocol for hot work; permit-to-work system in operation | <populate>
HSE | Critical lifts > 75% chart capacity require lift plan + engineer approval | <populate>
PRODUCTIVITY
PRODUCTIVITY | Apply 0.85-0.95 productivity factor for first 4 weeks of project (learning curve) | <populate>
PRODUCTIVITY | Confined working areas: derate output by 10-30% depending on access | <populate>
QUALITY
QUALITY | All concrete pours: nuclear density + 4-cyl set per pour (Sheet 11) | <populate>
QUALITY | All HDPE liner seams: 100% non-destructive (spark / vacuum) + destructive sample 1/150m | <populate>

## 18 Inclusions Exclusions
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SCOPE INCLUSIONS, EXCLUSIONS & CLARIFICATIONS REGISTER [TEMPLATE — populate per bid]
Discipline | Item | Status (Incl. / Excl. / Clar.) | Description / Reference
EARTHWORKS
EARTHWORKS | Mass excavation common soil | INCLUDED | Per Sheet 08 C-10-002; balanced cut/fill assumed
EARTHWORKS | Rock excavation including drill & blast | INCLUDED | Per Sheet 08 C-10-007 + B-01-003
EARTHWORKS | Removal of contaminated soil | EXCLUDED | Owner responsibility; treated separately
EARTHWORKS | Temporary site dewatering | CLARIFY | Included only where shown on dewatering plan
WATER MGMT
WATER MGMT | Permanent stormwater pond construction | INCLUDED | Per pond MTO
WATER MGMT | Operating sediment treatment chemicals | EXCLUDED | Owner-supplied per operating procedure
ROADS
ROADS | Haul road sub-base + surface course | INCLUDED | Per Sheet 08 C-30-002/3/4
ROADS | Permanent asphalt paving | CLARIFY | Included only on access road; not on haul roads
WRSA/TMF
WRSA/TMF | TMF embankment construction Zones A, B, C | INCLUDED | Per Sheet 08 C-40-002/3
WRSA/TMF | HDPE 2mm liner with CQA | INCLUDED | Per Sheet 08 C-40-004; specialty sub
WRSA/TMF | Dam Safety Officer (DSO) services | EXCLUDED | Owner's appointed DSO; we provide construction records
DRAINAGE
DRAINAGE | CSP culverts up to 1200mm diameter | INCLUDED | Per culvert schedule
DRAINAGE | Precast box / arch culverts > 1500mm | CLARIFY | Included only if drawing shows; supply long-lead
CONCRETE
CONCRETE | Cast-in-place foundations, walls, footings | INCLUDED | Per concrete MTO; ready-mix from <X> km plant
CONCRETE | Precast concrete (process plant) | EXCLUDED | Owner-supplied for plant scope
STEEL
STEEL | Structural steel building enclosures + equipment platforms | INCLUDED | Per steel MTO; supplier TBD
STEEL | Process plant structural steel | EXCLUDED | Owner / mechanical contractor scope
GEOSYNTHETICS
GEOSYNTHETICS | HDPE liner systems (TMF, ponds, closure cap) | INCLUDED | Includes installation + CQA
GEOSYNTHETICS | Geomembrane CQA Engineer of Record | EXCLUDED | Owner-appointed independent
BLASTING
BLASTING | Drill, blast, clear of rock excavation | INCLUDED | Self-perform or licensed sub
BLASTING | Pre-blast condition surveys of nearby structures | INCLUDED | Sheet 11; >500m radius scope
BURIED SVCS
BURIED SVCS | Site potable water, sewer, process water mains | INCLUDED | Per Sheet 08 K series
BURIED SVCS | Electrical / instrumentation underground | EXCLUDED | Per electrical contractor scope
FENCING
FENCING | Site perimeter chain link + wildlife exclusion | INCLUDED | Per Sheet 08 M series
FENCING | Process plant area security fencing | EXCLUDED | By process contractor
CLOSURE
CLOSURE | Final cover system + topsoil + seeding | INCLUDED | Per Sheet 08 H series; one-time cap
CLOSURE | Long-term water treatment infrastructure | EXCLUDED | Owner's operating responsibility
INDIRECTS
INDIRECTS | Site offices, lunchrooms, dryrooms | INCLUDED | Per Sheet 11
INDIRECTS | Camp accommodation (incl. food) | CLARIFY | Included only if remote; sheet 05 O2
INDIRECTS | Owner inspection / EPCM offices on site | EXCLUDED | By owner / EPCM
PERMITS
PERMITS | Routine construction permits (excavation, hot work) | INCLUDED | Standard practice
PERMITS | Environmental authorization (EA, water license) | EXCLUDED | Owner responsibility
PERMITS | Provincial blasting permits, magazine licenses | INCLUDED | Sub responsibility for blasting
WARRANTY
WARRANTY | 12-month material + workmanship warranty | INCLUDED | Standard CCDC 2
WARRANTY | Extended warranty beyond 12 months | EXCLUDED | By negotiation
EXCLUSIONS
EXCLUSIONS | Owner-furnished materials of any kind | EXCLUDED | Receive, store and install only if priced separately
EXCLUSIONS | Force majeure or unknown ground conditions | EXCLUDED | Per CCDC general conditions

## 19 Bid Leveling
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
BID LEVELING — TENDER COMPARISON [TEMPLATE — enter bidder pricing in blue cells]
WBS Ref | Item Description | UOM | Quantity | Bidder A ($/unit) | Bidder B ($/unit) | Bidder C ($/unit) | SME Benchmark ($/unit)
C-10-003 | Backfill common — spread and compact | m3 | <qty> | <enter $> | <enter $> | <enter $> | 25
C-10-007 | Rock excavation — blasted and loaded | m3 | <qty> | <enter $> | <enter $> | <enter $> | 48
C-30-002 | Haul road — sub-grade preparation | m2 | <qty> | <enter $> | <enter $> | <enter $> | 18
C-30-005 | Asphalt paving 50mm HL3 | m2 | <qty> | <enter $> | <enter $> | <enter $> | 54
C-40-002 | TMF embankment Zone A/B | m3 | <qty> | <enter $> | <enter $> | <enter $> | 27
C-40-004 | HDPE 2mm liner with CQA | m2 | <qty> | <enter $> | <enter $> | <enter $> | 39
C-50-005 | CSP culvert 1200mm | m | <qty> | <enter $> | <enter $> | <enter $> | 1250
C-60-002 | Concrete wall / grade beam | m3 | <qty> | <enter $> | <enter $> | <enter $> | 2850
C-60-006 | Rebar Grade 400 | tonne | <qty> | <enter $> | <enter $> | <enter $> | 5000
B-01-003 | Rock blasting all-in | m3 | <qty> | <enter $> | <enter $> | <enter $> | 65
B-05-003 | Wildlife exclusion fence 2.4m elec. | m | <qty> | <enter $> | <enter $> | <enter $> | 213
B-08-002 | Precast box culvert 2400x1800mm | m | <qty> | <enter $> | <enter $> | <enter $> | 8500
[TEMPLATE] Convert bidder Forms of Tender into common UOM and apply: Variance vs SME benchmark (%) = (Bidder $/unit − Benchmark $/unit) / Benchmark $/unit. Flag any item more than ±20% from benchmark for clarification. Use Sheet 10 floors/ceilings for hard out-of-range flags. Append clarifications and exclusions from each bidder to a deviation log.

## 20 Change Order Pricing
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
CHANGE ORDER PRICING METHODOLOGIES — CCDC-STYLE [TEMPLATE]
Method | When to Use | Build-Up Formula | Markup Low | Markup High | SME Notes
Unit-rate based | Quantum is well-defined and existing unit rate covers the work scope | Qty × existing unit rate × (1 + design growth) | 0% | 5% | Preferred where unit rates exist (Sheet 08)
Time & Materials (T&M) | Scope is uncertain and / or schedule-critical; no firm quantum | Crew hr × crew $/hr + Equip hr × equip $/hr + Mat × (1+wastage) + Sub × (1+markup) + OH% | 10% | 15% | Daily LEM log signed by owner rep
Lump-sum quotation | Discrete, well-defined work that can be quoted firm | Direct (build up per Sheet 09) + Indirect (10-15%) + OH+P (10-20%) | 15% | 25% | Submit detailed breakdown; client accepts LS
Negotiated rates | Recurring change category (e.g. additional culvert sizes) | Pre-agreed rate schedule × Qty | 5% | 10% | Capture in change order schedule
Force account | Disputed scope; owner directs work pending resolution | T&M as above + auditable records + retention of receipts | 10% | 15% | Subject to subsequent audit
CHANGE ORDER STANDARD MARKUP STACK (per CCDC 2 GC 6.2.4)
Layer | Element | % of Direct | Apply To | Notes
1 | Direct labour + equip + material | 100% | Cost of work | Build up per Sheet 09
2 | Contractor field overhead | 8-12% | Direct labour | If work managed by existing PM team — lower
3 | Head office overhead | 5-10% | Total direct + CFO | Bid-stage % less if scope handled by existing OH
4 | Contractor profit / fee | 8-15% | Total direct + OH | Project complexity / risk
5 | Bond + insurance adjustment | 1.5-3% | Total contract increase | Only if change increases bonded contract value
6 | Sub-tier markup (if subbed) | 5-10% | Sub price | On flow-through subs only
[TEMPLATE] Methodology selection should be agreed with Contract Administrator at project start. Daily T&M sheets must be co-signed within 48 hours. Lump-sum change quotations to include itemised buildup of LEMSC + indirect + OH+P. Time impact analysis required if change affects critical path (CCDC 2 GC 6.5).

## 21 Project Roll-Up
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
PROJECT ESTIMATE ROLL-UP [TEMPLATE — enter values in blue cells; green cells calculated]
Layer | Item | Amount (CAD) | Notes / Reference
1 — DIRECT FIELD COSTS
1.1 | Earthworks & mass excavation | 0 | From Sheet 08 section A; Σ Qty × Rate
1.2 | SWM, ESC & water management | 0 | From Sheet 08 section B
1.3 | Roads, pads & working surfaces | 0 | From Sheet 08 section C
1.4 | WRSA / TMF embankment | 0 | From Sheet 08 section D
1.5 | Drainage, culverts & piping | 0 | From Sheet 08 section E
1.6 | Concrete — civil | 0 | From Sheet 08 section F
1.7 | Structural steel & enclosure | 0 | From Sheet 08 section G
1.8 | Geosynthetics & liners | 0 | From Sheet 08 section D liner items
1.9 | Blasting (all-in) | 0 | From Sheet 08 section I
1.10 | Buried services | 0 | From Sheet 08 section K
1.11 | Fencing, security & wildlife | 0 | From Sheet 08 section M
1.12 | Permanent dewatering | 0 | From Sheet 08 section J
1.13 | Closure & reclamation | 0 | From Sheet 08 section H
| SUBTOTAL DIRECT | 0
2 — CONTRACTOR FIELD INDIRECTS (CDI)
2.1 | CDI % of direct (input) | 0.15 | Typical 12-18% Sheet 11/15
| CDI AMOUNT | 0 | = Direct × CDI %
3 — COMPANY OVERHEAD
3.1 | Company OH % of direct (input) | 0.08 | Typical 6-12% Sheet 15
| COMPANY OH AMOUNT | 0 | = Direct × OH %
4 — BONDING & INSURANCE
4.1 | Bond + Insurance % of contract (input) | 0.03 | Typical 2-4% Sheet 12/15
| BOND + INSURANCE AMOUNT | 0 | = (Direct + CDI + OH) × B+I %
5 — CONTINGENCY & RISK
5.1 | Contingency % of direct (input) | 0.12 | Typical 8-15% Sheet 15
| CONTINGENCY AMOUNT | 0 | = Direct × Contingency %
6 — CONTRACTOR PROFIT
6.1 | Profit % of all costs (input) | 0.1 | Typical 8-15% Sheet 15
| PROFIT AMOUNT | 0 | = (Direct + CDI + OH + B+I + Cont.) × Profit %
TOTAL BID (CAD) |  | 0 | Cross-check $/m3 or $/m2 against Sheet 10
[TEMPLATE] Populate Direct lines from MTO × unit rates (Sheet 08). Adjust % markups within the bands shown in Sheet 15. For Class 3 baseline use mid-range %. Apply regional adjustor (Sheet 14) to direct cost lines before summing if site is outside MB/SK baseline.

## 22 Risk Register
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
RISK & CONTINGENCY REGISTER [TEMPLATE — populate per project]
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Cost Impact (CAD) | Schedule Impact (wk) | Mitigation / Allocation
R-01 | Geotechnical | Unforeseen rock below estimated quantity | 4 | 4 | 750000 | 4 | Apply 3-8% earthworks contingency; rate adjustment per CCDC GC 6.4
R-02 | Geotechnical | Acid-generating waste rock encountered | 3 | 5 | 1200000 | 6 | Owner-led environmental management; allow 1-3% allowance
R-03 | Weather | Extended winter shutdown / spring break-up beyond plan | 4 | 3 | 350000 | 3 | Apply 2-5% weather contingency; review work calendar
R-04 | Market / Escalation | Diesel price >15% above bid basis over project life | 3 | 3 | 280000 | 0 | Apply 3-8% materials escalation; index fuel surcharge
R-05 | Market / Tariff | CBSA 25% surtax on Chinese steel/rebar extended | 3 | 3 | 420000 | 0 | Source Canadian/US; allow 5-10% on steel
R-06 | Subcontractor | Specialty sub (liner / blasting) default or delay | 2 | 4 | 600000 | 4 | Apply 1-3% sub default contingency; pre-qualify alts
R-07 | Permits | Environmental permit delay for fish habitat work | 3 | 4 | 400000 | 6 | Phase work; engage authority early
R-08 | Labour | Skilled trades shortage — Electrician / Welder | 4 | 3 | 250000 | 4 | Lock supply via early subcontracts; carry 5% labour premium
R-09 | Indigenous | IBA / community engagement delay | 3 | 4 | 350000 | 6 | Engage early; capture commitment in schedule
R-10 | Owner | Owner-supplied materials late | 3 | 4 | 500000 | 6 | Daily T&M / standby for owner-caused delay (Sheet 13)
R-11 | Quality / Rework | HDPE liner CQA failures requiring re-weld / re-install | 2 | 3 | 180000 | 2 | Pre-qualify installer; require third-party CQA
R-12 | HSE | Major incident causing site stop-work | 1 | 5 | 1500000 | 8 | Strong safety culture; carry incident allowance per insurer
[TEMPLATE] Likelihood × Impact = risk score. Items scoring ≥12 require explicit cost allocation. Total cost-weighted exposure (Σ Likelihood × Cost / 5) drives recommended contingency carry. Cross-reference Sheet 15 Layer 5 (Contingency & Risk) allocations.

## 23 Glossary
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
GLOSSARY, ABBREVIATIONS & UNITS OF MEASURE
Term / Abbreviation | Definition
AACE | Association for the Advancement of Cost Engineering International
AACE 18R-97 | Cost Estimate Classification System — process industries (5-class system used here for mining heavy civil)
AFE | Authorization for Expenditure — owner approval at sanction (typically Class 2)
BCPI | Building Construction Price Index (Statistics Canada) — used for escalation
CAD | Canadian Dollar
CBSA | Canada Border Services Agency — administers steel/rebar surtax
CDI | Contractor Distributable Indirects — site indirects allocated across project (offices, supervision, etc.)
CGL | Commercial General Liability insurance
CLAC | Christian Labour Association of Canada — open shop / alternate to Building Trades
CCDC | Canadian Construction Documents Committee — standard forms (CCDC 2 = stipulated sum)
CMS | Construction Management Standard
CQA | Construction Quality Assurance (typically third-party)
DRYROOM | Heated change facility for clothing / gear storage
DR-11 / DR-17 | HDPE pipe Dimension Ratio (wall thickness class)
EHT | Employer Health Tax (Ontario / BC)
EPCM | Engineering, Procurement and Construction Management
ESC | Erosion & Sediment Control
FID | Final Investment Decision
FIFO | Fly-in / Fly-out (typically 14-on / 7-off rotation)
HDPE | High-Density Polyethylene
HSE | Health, Safety, Environment
IBA | Impact Benefit Agreement (Indigenous communities)
IFC | Issued For Construction (drawing status)
LOA | Living Out Allowance (per-diem) for non-camp remote work
MTO | Material Take-Off (quantity survey from drawings)
NCSO | National Construction Safety Officer (Canadian certification)
NRCan | Natural Resources Canada (publishes diesel + commodity pricing)
ROM | Rough Order of Magnitude (Class 5/4 estimate)
SoR | Schedule of Rates
SWM | Stormwater Management
SWPPP | Stormwater Pollution Prevention Plan
TMF | Tailings Management Facility
WBS | Work Breakdown Structure
WCB / WSIB | Workers' Compensation Board / Ontario Workplace Safety & Insurance Board
WRSA | Waste Rock Storage Area
Std Proctor | Standard Proctor density (ASTM D698)
Crew code Bx/Cx | SME crew classifications (see Sheet 04)
Unit MH | Unit Man-Hours per UOM (productivity input)
UOM | Unit of Measure (m, m2, m3, tonne, ea, LS)
LS | Lump Sum
S+I | Supply + Install
S+F+P | Supply + Form + Pour
Std / SoR floor | Lower benchmark in Sheet 10 below which bid is suspect
Std / SoR ceiling | Upper benchmark in Sheet 10 above which bid is suspect

## 24 References
RICK MILLER SME STANDARD — CANADA 2026 MINING HEAVY CIVIL ESTIMATING MANUAL & RATE LIBRARY
Consolidated Schedule of Rates, Bid Support Package & Estimating Standard ¦ AACE 18R-97 Class 3 baseline ¦ Canada-wide Q2-2026 ¦ All figures CAD
SOURCES, REFERENCES & DATA PROVENANCE
Category | Reference | Use in Manual
STANDARDS
STANDARDS | AACE International Recommended Practice 18R-97 — Cost Estimate Classification System | Sheet 03 — Class 5 through Class 1 framework
STANDARDS | ASTM D698 — Standard Proctor; ASTM D1557 — Modified Proctor | Sheet 17 — earthworks compaction acceptance
STANDARDS | ASTM D4439 — Geosynthetics terminology | Sheet 03 / 08 — geotextile overlap allowances
STANDARDS | CCDC 2 — Stipulated Sum Contract (Canadian Construction Documents Committee) | Sheets 12, 18, 20 — bond, warranty, change order provisions
STANDARDS | Canadian Dam Association Dam Safety Guidelines | Sheet 08 section D — TMF embankment construction
INDICES
INDICES | Statistics Canada — Building Construction Price Index (BCPI), quarterly | Sheet 03 / 14 — Q2-2020 → Q2-2026 x1.25 escalation
INDICES | Natural Resources Canada (NRCan) — Diesel Pricing, weekly | Sheet 03 — diesel price by region
INDICES | Bank of Canada — USD/CAD exchange rate | Sheet 03 / 14 — currency basis
AUTHORITIES
AUTHORITIES | Canada Border Services Agency — Notices 24-26 and 25-22 (steel / rebar surtax) | Sheet 03 / 14 — 25% surtax on Chinese-origin material
AUTHORITIES | Provincial WCB / WSIB / CNESST / WorkSafeBC / WorkplaceNL — premium rate tables | Sheet 12 — WCB by province
AUTHORITIES | Nova Scotia Energy Regulatory Board — Atlantic diesel price | Sheet 03 / 14 — Atlantic diesel
INTERNAL
INTERNAL | Rev G workbook — RMM-CIVIL-CONTRACTOR-CANADA-2026-REV0 (Contractor Bid Tool) | Source: Bid Summary, Missing Unit Rates, Bonding & Ins., Overhead, Standby, Bid Screening
INTERNAL | Rev E workbook — RMM-CIVIL-CANADA-2026-REV0 (EPCM Benchmark Estimator) | Source: Crew, Labour, Equipment Rates, Heavy Civil Unit Rates, SME Factors
INTERNAL | Ausenco go-by Q2-2020 (Senior PD / EPCM reference) | Sheet 04 — crew rate baseline pre-escalation
SUPPLIERS
SUPPLIERS | Armtec — CSP culvert and flow guard pricing (Dec-2025) | Sheet 08 section E — culvert pricing
SUPPLIERS | Various HDPE pipe suppliers — Jan-2026 quotes +15% install factor | Sheet 08 section E — HDPE pipe pricing
BENCHMARKS
BENCHMARKS | SME benchmark observations 2024-2026 — NL, NS, NB, ON, MB, BC, NT mining civil contracts | Sheet 10 — bid screening floors/ceilings
METHODOLOGY
METHODOLOGY | Standard industry practice — contractor markup stack and CDI percentages | Sheet 15 — 6-layer bid model
METHODOLOGY | CCDC 2 GC 6.2 / 6.4 / 6.5 — change order provisions | Sheet 20 — change order pricing